## Summary
PROJECT COST TRACKING SHEET
Project Management Toolkit
How to use: Fill the project details and the cream cells on the Cost Detail tab. The grey cells, including everything here, calculate on their own.
PROJECT INFORMATION | HEADLINE METRICS
Project Name | Original Budget | 730000
Project No. | Approved Changes | 8000
Client | Revised Budget | 738000
PM | Actual to Date | 448000
Start Date | Committed | 214000
End Date (Target) | Forecast at Completion | 662000
| Variance (Revised - Forecast) | 76000
| Variance % | 10.3%
Template provided as-is for general reference. Adapt to your project before use. LaVallee SiteWorks Ltd. accepts no liability for use of this document.
LaVallee SiteWorks Ltd. • Build. Manage. Deliver.

## Cost Detail
COST DETAIL
By cost code
How to use: Enter your cost codes and the four cream dollar columns (Original Budget, Approved Changes, Actual, Committed). Forecast, Variance, and the totals calculate on their own. Sample codes shown below; replace with your own.
| Fill these in |  |  | Calculated, do not type here
Cost Code | Description | Category | Unit | Qty | Original Budget | Approved Changes | Actual to Date | Committed (PO/Sub) | Forecast at Completion | Variance
01.01 | Mobilization | Labour | LS | 1 | 25000 | 0 | 25000 | 0 | 25000 | 0
02.01 | Site preparation | Labour | m² |  | 40000 | 0 | 38000 | 2000 | 40000 | 0
02.02 | Excavation (bulk) | Equipment | m³ |  | 120000 | 8000 | 95000 | 20000 | 115000 | 13000
02.03 | Excavation (detail / trench) | Equipment | m³ |  | 60000 | 0 | 45000 | 10000 | 55000 | 5000
03.01 | Granular base supply | Material | t |  | 85000 | 0 | 80000 | 5000 | 85000 | 0
03.02 | Granular base placement | Equipment | m² |  | 45000 | 0 | 30000 | 12000 | 42000 | 3000
04.01 | Subcontractor (concrete) | Subcontractor | LS | 1 | 90000 | 0 | 40000 | 50000 | 90000 | 0
04.02 | Subcontractor (paving) | Subcontractor | m² |  | 110000 | 0 | 0 | 110000 | 110000 | 0
05.01 | Hauling | Equipment | load |  | 55000 | 0 | 48000 | 5000 | 53000 | 2000
06.01 | Site restoration | Labour | m² |  | 35000 | 0 | 5000 | 0 | 5000 | 30000
99.01 | Project management | Labour | hr |  | 50000 | 0 | 42000 | 0 | 42000 | 8000
99.02 | Demobilization | Labour | LS | 1 | 15000 | 0 | 0 | 0 | 0 | 15000
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
| TOTAL |  |  |  | 730000 | 8000 | 448000 | 214000 | 662000 | 76000
Template provided as-is for general reference. Adapt to your project before use. LaVallee SiteWorks Ltd. accepts no liability for use of this document.
LaVallee SiteWorks Ltd. • Build. Manage. Deliver.

## Notes
NOTES / CHANGE LOG
Project Management Toolkit
Log scope notes, decisions, and their cost impact here. Tie each entry to a cost code or change order in the Reference column.
Date | Author | Reference | Note | Cost Impact
Template provided as-is for general reference. Adapt to your project before use. LaVallee SiteWorks Ltd. accepts no liability for use of this document.
LaVallee SiteWorks Ltd. • Build. Manage. Deliver.