## Change Order Log
CHANGE ORDER LOG
Project Management Toolkit
How to use: Fill the cream cells. The grey cells do the math on their own, so leave them alone. Status drives the total: only Approved change orders move the contract value.
| Fill these in |  |  | Calculated, do not type here
PROJECT INFORMATION
Project Name
Owner |  |  |  | Contractor
Original Contract Value ($) |  | 1250000 |  | Project No.
Prepared By |  |  |  | Date
CONTRACT SUMMARY
Original Contract Value ($) |  |  | 1250000 |  |  | Only Approved change orders roll into the Revised Contract Value. Draft, Submitted, Rejected, and Void COs do not change it.
Approved Changes ($) |  |  | 23650
Revised Contract Value ($) |  |  | 1273650
Net Change (%) |  |  | 1.892%
Change Orders (count) |  |  | Approved: 2 Submitted: 1
CHANGE ORDER REGISTER
Sample data shown in the first three rows. Clear them and enter your change orders.
CO No. | Date | Description of Change | Category | Status | CO Amount ($) | Schedule (days) | Revised Contract Value ($)
001 | 2026-05-20 | Added catch basin at Sta 1+200 per site condition | Site Condition | Approved | 8450 | 1 | 1258450
002 | 2026-05-28 | Owner-directed upgrade to Class 25 pipe, north run | Owner Directed | Approved | 15200 | 2 | 1273650
003 | 2026-06-05 | Revised grading at lot 7 per updated IFC drawings | Design Change | Submitted | 6300 | 0 | 1273650
Template provided as-is for general reference. Adapt to your project before use. LaVallee SiteWorks Ltd. accepts no liability for use of this document.
LaVallee SiteWorks Ltd. • Build. Manage. Deliver.
Note on H24: Calculated. Running revised contract value. Only Approved change orders are added to the original.