## Overview
Hospital Preparedness Program (HPP) Health Care Coalition (HCC) Readiness Plan Template Overview
FY24-29 NOFO
Purpose | You may use this readiness plan template to document how you will carry out activities and meet requirements for upcoming projects and acitivities throughout the course of the 5-year budget period (BP). The Office of Health Care Readiness (OHCR) is providing this work plan and budget template as an optional resource.
Notice of Funding Opportunity (NOFO) Instructions | You must submit a detailed fiscal year (FY) 2024 readiness plan in the first BP. Priorities: In this readiness plan, your HCC must describe top strategic priorities of your HCC(s) for each BP. Your HCC(s) should collaborate with you as they develop their top strategic priorities so that their Readiness Plan and the Strategic Plan for FY 2024–2028 are aligned and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments. Implementation Planning: Describe how your HCC(s) will implement activities. This should include your HCC(s)’s method for: • Developing the required materials identified in this NOFO, including approach, timelines, and expected milestones. Note: You and your HCC(s) must adhere to the submission deadlines specified in the timing and deadlines table. • Addressing gaps identified through assessments. Note: This section can be updated on a rolling basis as you and your HCC(s) complete assessments and identify areas for improvement. • Engaging community partners. • Facilitating continuous improvement from the previous BP. HCC Growth and Development: Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: • Manage and improve administrative and financial functions. • Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
Readiness Plan Template Content
Tab | Description
Activity Requirements | A reference table of activity requirements for the FY 2024–2028 HPP NOFO with submission instructions and timeline and administrative oversight activities.
HCC Priorities | Readiness Plan component
HCC Development | Readiness Plan component
Establish Governance | Readiness Plan component
Assess Readiness | Readiness Plan component
Plan and Implement | Readiness Plan component
Exercise and Improve | Readiness Plan component
Training and Exercise (T&E) Plan Instructions | T&E Plan component
T&E Plan | T&E Plan component
Reference Table
HPP NOFO Outcomes | Description
Establish and act on multi-year priorities. | Outcomes include: • Health care delivery system readiness to respond to a shifting threat landscape and community needs over multiple years. • Continuous programmatic and administrative improvement on multi-year priorities.
Enhance and sustain HCCs. | Outcomes include: • HCC governance, management, and operations that reflect community partnerships.
Coordination. | Outcomes include: • Coordinated planning and decision-making among health care delivery system partners. • State, local, tribal, and territorial agencies, HCCs, and other partners provide integrated health care response incident management (Emergency Support Function #8 [ESF-8] – Public Health and Medical Services).
Continuity of health care service delivery. | Outcomes include: • A resilient health care workforce able to safely meet response and recovery demands. • Suficient space, systems, staff, and resources to support patient movement and patient care delivery during response and recovery. Note: As used in the HPP NOFO, “health care workforce” does not refer only to clinical providers, but also includes all those who support the functioning of health care during disasters and emergencies.
HPP NOFO Core Functions | Description
Assessment and risk mitigation. | Anticipate challenges and mitigate risks to support decision-making that meets community or jurisdiction health care needs during a disaster or emergency.
Information sharing. | Collect and share near real-time information to provide multidirectional health care situational awareness during an emergency or disaster.
Specialty care planning and coordination. | Incorporate necessary expertise to support health care readiness planning, disaster and incident management, including for specialty care delivery, and/or to address specific hazards or events.
Respond. | Coordinate and support the implementation of plans, policies, and procedures among recipients, HCCs, HCC members, and their partners to address patient care needs during an emergency or disaster.
Health care workforce support. | Equip, protect, and support the health care workforce by providing access to health care readiness resources, training, and exercises.
Resource management. | Facilitate resource management and planning among recipients, HCCs, HCC members, and their partners to mitigate shortfalls, maintain operations, and sustain delivery of patient care services during an emergency or disaster.
Training, exercise, and evaluation. | Conduct trainings, exercises, and evaluations that incorporate input from assessments, plans, policies, and previous trainings and exercises to evaluate, validate, and improve readiness and response processes.
Continuity and recovery. | Support the improvement of processes and systems that promote continuity of health care operations and aid in recovery.
Organizational development. | Create and carry out strategies to sustain and grow HCCs and their partnerships.
End of Worksheet

## Activity Requirements
FY 2024–2028 HPP NOFO Requirements
The following table is for your reference. Please refer to the HPP NOFO Timing and Deadlines table for activities 1-4 on p. 44-45 of the HPP NOFO. Refer to the Benchmarks table for Recipient and HCC benchmarks on p. 42 of the HPP NOFO.
Activities | Guidance
0. Administrative Oversight Activities | 0. Administrative Oversight – Guidance
0.1 Program Administration | Work with HCCs and pertinent partners to maintain program oversight throughout the period of performance. Please adhere to program requirements listed in the NOFO and the rules listed in 45 Code of Federal Regulations (CFR) Part 75.
0.2 Financial Administration | Develop and administer budgets that support submitted work plans and comply with the rules listed in 45 CFR Part 75, Uniform Administrative Requirements, Cost Principles, and Audit Requirements for U.S. Department of Health and Human Services (HHS) Awards throughout the period of performance.
Activities | Submission Instructions and Timeline | Responsible Owner
1. Establish Governance Activities | 1. Establish Governance – Submission Instructions and Timeline | 1. Establish Governance – Responsible Owner
1.1 HCC Governance Document | Submit by 12/15/2025 (BP1). Review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
1.2 Jurisdiction Information | Submit by 12/15/2025 (BP1). Review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
2. Assess Readiness Activities | 2. Assess Readiness – Submission Instructions and Timeline | 2. Assess Readiness – Responsible Owner
2.1 Risk Assessment (RA) Note: Previously known as Jurisdiction Risk Assessment (JRA) | Submit once every five years. If you submitted a JRA during the prior HPP FY 2019–2023 period of performance, you must submit the RA five years after that submission. | HPP recipient with input from HCCs
2.2 Hazard Vulnerability Assessment (HVA) | Submit by 12/15/2025 (BP2). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.3 Readiness Assessment | Submit by 12/15/2025 (BP2). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.4 Supply Chain Integrity Assessment | Review the current Supply Chain Integrity Assessment and submit updated material each BP. If you and your HCC(s) do not have a supply chain assessment, submit this by December 31, 2026 (BP3). Review and submit updated material each BP from BP4–BP5. | HCC in coordination with HPP recipient
2.5 Workforce Assessment | Submit by 11.30.2026 (BP3). Review each BP from BP4–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
2.6 Cybersecurity Assessment | Due by 5.31.2026 (BP2). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
2.7 Extended Downtime Health Care Delivery Impact Assessment | Due by 5.31.2026 (BP2). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3. Plan and Implement Activities | 3. Plan and Implement – Submission Instructions and Timeline | 3. Plan and Implement – Responsible Owner
3.1 Strategic Plan for FY 2024–2028 | Due by 11.30.2025 (BP2). Review each BP from BP2–BP5 and submit updated material as needed. | HPP recipient with input from HCCs
3.2 Readiness Plan | Due by 12.15.2025 (BP2). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3.2.1 Training and Exercise Plan | Due by 12.25.2025 (BP2). Review and submit updated material each BP from BP2–BP5. | HCC in coordination with HPP recipient
3.3 Response Plan Activities | 3.3 Response Plan – Submission Instructions and Timeline | 3.3 Response Plan – Responsible Owner
3.3.1 Information-Sharing Plan | Review the current information-sharing plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have an information-sharing plan, submit this by 5.31.2026 (BP2). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.2 Resource Management Plan | Review the current resource management plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a resource management plan, submit this by 5.31.2026 (BP2). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.3 Workforce Readiness/Resilience Plan | Due by December 31, 2026 (BP3). Review each BP from BP4–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.4 Medical Surge Support Plan | Review the current medical surge support plan each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a medical surge support plan, submit by 5.31.2026 (BP2). Review each BP from BP2–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.3.5 Patient Movement Plan | You and your HCC(s) must submit for the Patient Movement Plan by 5.31.2026 (BP2). Once submitted, review each BP and submit updated material as needed. | HPP recipient with input from HCCs
3.3.6 Allocation of Scarce Resources Plan | You and your HCC(s) must define the submission deadline for the Allocation of Scarce Resources Plan when you develop your Readiness Plan. Once submitted, review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
3.4 Continuity and Recovery Plan Activities | 3.4 Continuity and Recovery Plan – Submission Instructions and Timeline | 3.4 Continuity and Recovery Plan – Responsible Owner
3.4.1 Continuity of Operations Plan (COOP) | Review the current COOP each BP from BP1–BP5 and submit updated material as needed. If you and your HCC(s) do not have a COOP, complete this by 5.31.2026 (BP2). Once submitted, review each BP and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.2 Cybersecurity Support Plan | Due by May 30, 2027 (BP3). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.3 Extended Downtime Support Plan | Due by 5.30.2027 (BP3). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
3.4.4 Recovery Plan | Due by 5.31.2026 (BP2). Review each BP from BP3–BP5 and submit updated material as needed. | HCC in coordination with HPP recipient
4. Exercise and Improve Activities [1] | 4. Exercise and Improve – Submission Instructions and Timeline | 4. Exercise and Improve – Responsible Owner
4.1 Medical Response and Surge Exercise (MRSE) | Complete the exercise and submit the MRSE Exercise Reporting Tool by June 30 of each BP. | HCC with HPP recipient support
4.2 Patient Movement Exercise | Complete once, within one year of submitting the Patient Movement Plan. | HPP recipient with HCC participation
4.3 Federal Patient Movement Exercise | If applicable, complete once every three years, or as required by other cooperative agreements/programs. | HCC with HPP recipient support
4.4 Cybersecurity Exercise | Complete once by June 30, 2027 (BP3). | HCC with HPP recipient support
4.5 Non-Cyber Extended Downtime Exercise | Complete once between BP3–BP5. | HCC with HPP recipient support
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Complete once in the five-year period of performance. | HPP recipient with HCC participation
4.7 Statewide Exercise | Complete once in the five-year period of performance. | HPP recipient with HCC participation
[1] Please refer to Exercise and Improve section of the HPP NOFO for a full list of requirements for this section.
Please note that certain compliance requirements, like the requirement to conduct at least one exercise that address the needs of at-risk individuals and communities most impacted by disasters, are not listed in this table.
End of Worksheet

## HCC Priorities
Readiness Plan – Priorities
Description | On the priorities tab, describe top strategic priorities of your HCC(s) for each BP. HCCs should collaborate with the recipient as they develop their top strategic priorities so that your Readiness Plan shows alignment to the Strategic Plan for FY 2024–2028 and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments.
Priority | HCC Priorities | Description and Approach
Rank of Priority | Select your priority area from highest priority to lowest. | Describe your approach to address your priority needs including: 1. Primary reason(s) for priority (e.g., critical gap finding, strategic plan alignment, etc.) 2. Briefly summarize how the HCC will approach the priority (e.g., The HCC will complete the patient movement plan in year 1 and perform a detailed gap analysis regarding needs in the region).
1 | 3. Plan and implement | 1. The SCHCC recognizes the critical need to streamline medical coordination at both local and regional levels. Recent events in Colorado, including the Club Q and King Soopers shootings, Eastern Star LTCF fire and evacuation, Parker hospital evacuation, and the extended downtime incident at St Francis Hospital, underscore the increasing necessity for proactive planning to address patient transport, patient placement, and patient care. 2. We will support continued development and sustainability of HCC’s response capabilities and competencies for regional ESF8 medical coordination, which includes patient transport, patient placement and patient care. (operational support, sustainability)
2 | 0.1 Program Administration | 1. The south central region is characterized by a diverse landscape, ranging from areas with robust urban medical infrastructure to medical deserts in the frontier counties. Effectively supporting this region requires addressing the unique needs of these varied areas while fostering interoperability through local, regional, and statewide partnerships. 2. Will improve interoperability between local, regional, and statewide partners to support effective response coordination that meets the needs of Colorado’s medical system. We will continue to build partner diversity across the SCHCC by maintaining and/or improving engagement across existing relationships, with a focus on emergency management, EMS, and healthcare executives. (Engagement)
3 | 0. Administrative Oversight | 1. Through Medical Response Surge Exercise, Hazard Vulnerability Analysis and frequent meetings with our healthcare partners, the SCHCC has found that continuous learning around data interpretation, entry in real-time data dashboards that highlight key metrics, and data literacy discussions with all stakeholders is integral to making informed decisions related to planning, preparation, response and recovery. Further, it will allow for better identification of medical system strengths and weaknesses which will guide future planning and response. 2. In BP1, the SCHCC improved awareness around medical system strengths and weaknesses through data assessments, analysis, and interpretation that informs risk mitigation initiatives that are appropriate to each HCC region, and the state as a whole. (Situational Awareness) The SCHCC will continue to expand the focus of this work through BP2 to incorporate lessons learned through the exercises, and BP2 stop work period, as well as work with rural partners to understand and address their capabilities as well.
4 | 4. Exercise and Improve | 1. The SCHCC will adhere to FEMA’s Homeland Security Exercise and Evaluation Program (HSEEP) when planning and conducting exercises and developing improvement plans. The focus of training, exercises, and improvement planning will be guided by the regional hazard vulnerability assessment, real-world events, exercises, feedback from the SCHCC Steering Team, and the HPP NOFO. 2. In Year 1, the SCHCC completed the multi-year training and exercise plan and conducted a detailed gap analysis regarding needs in the region. In year 2, the SCHCC will continue to work through the MYTEP and address the gaps, strengths and weaknesses observed.
End of Worksheet
Select One
0. Administrative Oversight
0.1 Program Administration
0.2 Financial Administration
1. Establish governance
1.1 HCC Governance Document
1.2 Jurisdiction Information
2. Assess readiness
2.1 Risk Assessment (RA)
2.2 Hazard Vulnerability Assessment (HVA)
2.3 Readiness Assessment
2.4 Supply Chain Integrity Assessment
2.5 Workforce Assessment
2.6 Cybersecurity Assessment
2.7 Extended Downtime Health Care Delivery Impact Assessment
3. Plan and implement
3.1 Strategic Plan for FY 2024-2028
3.2 Readiness Plan
3.2.1 Training and Exercise Plan
3.3 Response Plan
3.3.1 Information-Sharing Plan
3.3.2 Resource Management Plan
3.3.3 Workforce Readiness / Resilience Plan
3.3.4 Medical Surge Support Plan
3.3.5 Patient Movement Plan
3.3.6 Allocation of Scarce Resources Plan
3.4 Continuity and Recovery Plan
3.4.1 Continuity of Operations Plan (COOP)
3.4.2 Cybersecurity Support Plan
3.4.3 Extended Downtime Support Plan
3.4.4 Recovery Plan
4. Exercise and Improve
4.1 Medical Response and Surge Exercise (MRSE)
4.2 Patient Movement Exercise
4.3 Federal Patient Movement Exercise
4.4 Cybersecurity Exercise
4.5 Non-Cyber Extended Downtime Exercise
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
4.7 Statewide Exercise
Other

## Readiness Plan Overview (hidden)
Readiness Plan Overview
HCC Priorities | On the priorities tab, describe top strategic priorities of your HCC(s) for each BP. HCCs should collaborate with the recipient as they develop their top strategic priorities so that your Readiness Plan shows alignment to the Strategic Plan for FY 2024-2028 and can support one another. Your HCC(s) may update their priorities each BP based on the previous assessments.
Implementation Planning | On the activity tabs, develop the required materials identified in the NOFO, including approach, timelines, and expected milestones. • adhere to the submission deadlines specified in the activity requirements tab •
• Use your readiness assessment Addressing gaps identified through assessments. Note: This section can be updated on a rolling basis as you and your HCC(s) complete assessments and identify areas for improvement.
• Engaging community partners.
• Facilitating continuous improvement from the previous BP.
HCC Development
Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: • (HCC) Manage and improve administrative and financial functions. • (HCC) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
• (HCC) Manage and improve administrative and financial functions.
• (HCC) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).

## HCC Development
Readiness Plan – HCC Growth & Development
Activities listed below must support the administrative management and monitoring of the cooperative agreement.
Instructions and reminders:
Describe how your HCC(s) will develop as an organization, including how your HCC(s) will: 1) Manage and improve administrative and financial functions. 2) Communicate the benefits of HCC activities to health care readiness partners, community partners, and other key audiences (e.g., engaging leader “champions”).
Please provide at least one activity for program administration, financial administration, and strategic communication.
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This must be the role title of the personnel responsible for the administration or management activty and can speak to the intended output.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Item Number | HCC Development Activity | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date
1 | HCC Administration | Complete Administration of Strategic Preparedness and Response (ASPR) Notification of Funding Opportunity (NOFO) & subsequent CDPHE HPP Statement of Work (SOW) 2024 - 2028 deliverables | SCHCC will complete all deliverables listed on the 2025-2026 SOW and submit to CDPHE by due date. | schccoalition@gmail.com | 2026-06-30
2 | Financial Administration | SCHCC will defer to the 2022 City of Colorado Springs Financial Policies with respect to the accounting reporting, and documentation of work completed and pertaining to the HPP grant (See ‘2022 City of Colorado Springs Financial Policies; Section 11’). All grant expenses will comply with the terms set forth in the grant application, grant award letter, city procurement policies and the guidelines in the Office of Management and Budget Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards (Uniform Guidance), 2 CFR 200.Per the 2022 City of Colorado Springs Financial Policies, the Readiness and Response Coordinator (as the Employee of the City of Colorado Springs) will carry-out the roles and responsibilities defined above for Department staff. | HCC will submit invoices for reimbursement for completed work on the 2025-2026 SOW. | kschally@plainstopeaks.org | 2026-06-30
3 | Strategic Communication | HCC will utilize CoShare, email, and phone to communicate program status and deliverable completion during BP 1. HCC leadership will conduct outreach to health system and community leadership to increase collaboration and partnership, and engage leader champions. | Monthly reports will be updated on CoShare and include SOW progress and completion. | schccoalition@gmail.com | 2026-06-30
End of Worksheet
Select One
HCC Administration
Financial Administration
Strategic Communication

## Establish Governance
Readiness Plan – Implementation Planning: Establish Governance
Activities listed below must support establishing governance in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | HCC Governance Document | HCC Administrator will update the existing Governance Document annually, ensuring it is updated by 12/15/2025. ASPR NOFO requirements will be used as guidance for keeping the document updated. | The following items are defined: management/ administration, HCC operational roles, funding structure, geographic coverage, membership, community coordination and engagement, response operations, and jurisdiction information. The governance with the aforementioned defined items will be submitted to the SCHCC steering team and Executive Council for review and approval. Upon approval the governance will be signed by the Executive Council and serve as the by-laws for the program. | schccoalition@gmail.com | 2025-12-15 | Organizational development | Enhance and sustain HCCs
2 | Jurisdiction Information | Jurisdiction Information will be updated annually with Governance Document. | City and county boundaries in the SCHCC Region are identified and included in the approved SCHCC Governance Document. | schccoalition@gmail.com | 2025-12-15 | Organizational development | Enhance and sustain HCCs
End of Worksheet

## Assess Readiness
Readiness Plan – Implementation Planning: Assess Readiness
Activities listed below must support assessing readiness in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Work Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Hazard Vulnerability Assessment (HVA) | SCHCC utilizes AAR/IP's, planning initiatives, gap analysis, and partner collaboration to inform and update the regional HVA on an annual basis. Coordinators at the SCHCC work with county Emergency Managers and Hospital Emergency Managers in our region to form a comprehensive HVA which identifies the most prevalent hazards across the region. | The aim is to identify threats and hazards, identify vulnerabilities, estimate probability of occurrence, determine the severity of impact, and estabish priority actions for our region. | schccoalition@gmail.com | 2025-12-15 | Assessment and risk mitigation | Establish and act upon multi-year priorities
2 | Readiness Assessment | SCHCC administrator completed the Readiness Assessment by 1/31/2025. SCHCC Administrator utilized the template provided by CDPHE and the requirements outlined in the NOFO document to complete the readiness assessment. | Identify the SCHCC’s capacity and capability to carry out NOFO activities, conduct health care preparedness and response operations, and address health care readiness gaps. | schccoalition@gmail.com | 2025-12-15 | Organizational development | Coordination
3 | Cybersecurity Assessment | SCHCC coordinators have begun to gather resources for the cybersecurity assessment. The SCHCC will utilize the template provided by ASPR to complete this assessment as well as incorporate SAFECOM Guidelines per CDPHE recommendation. This assessment will be complete by the BP1 due date of 06/30/20215. | We intend to assess use of cybersecurity practices, describe the community impact of a potential incident, and identify mitigation strategies. | schccoalition@gmail.com | 2026-05-31 | Assessment and risk mitigation | Continuity of health care service delivery
4 | Extended Downtime Health Care Delivery Impact Assessment | The SCHCC coordinators will utilize the template provided by ASPR to complete this assessment. This deliverable will be completed by 6/30/2025 in BP1. | We will identify impacted functions (communications, information-sharing, resource management, etc.), community impact, and mitigation strategies. | schccoalition@gmail.com | 2026-05-31 | Information sharing | Continuity of health care service delivery
5 | Supply Chain Integrity Assessment | The SCHCC administrator has completed supply-chain integrity assessment and will continue to update the assessment based on current needs and gaps. The SCHCC will work with CHA to implement information from their report, once it is made available. The final product will be submitted by 12/31/2026, and will be updated annually thereafter. | We will identify resource needs, vulnerabilities, current access and infrastructure, impact on communities, and mitigation strategies. | schccoalition@gmail.com | 2026-11-30 | Resource management | Continuity of health care service delivery
6 | Workforce Assessment | The SCHCC administrator has completed an initial workforce assessment. We will work to include the additional information identified in the current assessment guidelines released by ASPR, as well as the suggestions provided by CDPHE. A final draft will be submitted 12/26/2026, and the document will be annually updated thereafter. | The SCHCC will identify vulnerabilities, ability to provide specialty expertise, ability to provide care to vulnerable communities, training needs, workforce safety and health resources, community impact, and mitigation strategies. | schccoalition@gmail.com | 2026-11-30 | Health care workforce support | Continuity of health care service delivery
End of Worksheet

## Plan and Implement
Readiness Plan – Implementation Planning: Plan and Implement
Activities listed below must support planning and implementation in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Readiness Plan | Coordinators at the SCHCC will collaborate to complete the Readiness Plan by 3/31/2025. CDPHE's template will be used as well as priorities from the Strategic Plan and the NOFO document. After BP1, the readiness plan will be updated annually. | The Readiness Plan serves as a roadmap for the SCHCC to address strategic priorities, implement the cooperative agreement activities, and develop and grow as an organization. It will include the SCHCC's priorities, implementation planning, and HCC development. | schccoalition@gmail.com | 2025-12-15 | Organizational development | Establish and act upon multi-year priorities
2 | Training and Exercise Plan | The SCHCC will collaborate with regional partners to identify training needs within the region. The SCHCC Assistant Coordinator will send out an IPPW survey to healthcare partners in the region for input. The Program Administrator will work with partners at PPROEM and DHS to identify ways to meet the training needs of the HCC and its members. All exercise requirements will be met by the time of their due date. These elements will all be incorporated into the training and exercise plan, which will be submitted by 3/31/2025. | The Training and Exercise Plan will be based on priorities which were identified in the Strategic Plan and the Readiness Plan. It will also describe the indended audience for trainings related to the SCHCC, and will describe any relevant resources and/or partnerships which will be crucial in supporting training for the SCHCC. A calendar with training plans and a NIMS implementation section will also be included. | schccoalition@gmail.com | 2025-12-15 | Training, exercise, and evaluation | Establish and act upon multi-year priorities
3 | Response Plan: Information-Sharing Plan | SCHCC Coordinators will work with clinicians, community partners, health care executives, and additional health care readiness partners to develop the Information-Sharing plan by 6/30/2025. | The Information-Sharing plan will identify situational awareness/ information tools, coordination of roles, clinical knowledge sharing, systems protection, redundant communications, and mitigation techniques for misinformation, disinformation, and mal-information. | schccoalition@gmail.com | 2026-05-31 | Information sharing | Coordination
4 | Response Plan: Resource Management Plan | SCHCC Coordinators will work with clinicians, community partners, health care executives, and additional health care readiness partners to develop the resource management plan by 6/30/2025. | The Resource Management plan will identify the acquiring, storing, and management of supplies, in addition to describing stockpile activation, staffing, volunteer management, alternate care sites, and telemedicine. | schccoalition@gmail.com | 2026-05-31 | Resource management | Enhance and sustain HCCs
5 | Response Plan: Workforce Readiness / Resilience Plan | SCHCC Coordinators will work with clinicians, community partners, health care executives, and additional health care readiness partners to develop the Workforce Readiness / Resilience Plan plan by 12/31/2026. | The Workforce Readiness / Resilience Plan will describe how the SCHCC plans to promote workforce safety and resilience in our region. It will also describe how the SCHCC will engage community healthcare partners in our Training and Exercise Plan. Finally, it will address any gaps identified previosly in the Workforce Assessment. | schccoalition@gmail.com | 2026-12-31 | Health care workforce support | Continuity of health care service delivery
6 | Response Plan: Medical Surge Support Plan | SCHCC Coordinators will work with clinicians, community partners, health care executives, and additional health care readiness partners to develop the Medical Surge Support Plan by 6/30/2025. | The Medical Surge Support Plan will describe how the SCHCC will respond to medical surge and mass casualty incidents. It will also include special annexes for the region, including annexes for pediatric, burn, special pathogen, chemical, and radiological events. | schccoalition@gmail.com | 2026-05-31 | Respond | Coordination
7 | Response Plan: Allocation of Scarce Resources Plan | SCHCC Coordinators will work with clinicians, community partners, health care executives, and additional health care readiness partners to develop the Allocation of Scarce Resources Plan by 6/30/2028. | The Allocation of Scarce Resources Plan will describe scarce resource management, including the management of information, resource requests, healthcare support, and connections with federal, regional, and state-level resources. This Plan will also discuss planning and training for allocation of scarce resources within the region. | schccoalition@gmail.com | 2028-06-30 | Resource management | Continuity of health care service delivery
8 | Continuity and Recovery Plan: Continuity of Operations Plan (COOP) | The SCHCC will update the current COOP for leadership changes and contact information by 6/30/2025. | The COOP includes detailed information on activation, contacts, leadership, supplemental resources, critical infrastructure, and essential records. | schccoalition@gmail.com | 2026-05-31 | Continuity and recovery | Continuity of health care service delivery
9 | Continuity and Recovery Plan: Cybersecurity Support Plan | SCHCC Coordinators will use the Cybersecurity Assessment to inform the Cybersecurity Support Plan in addition to collaborating with coalition partners. | The plan will implement cybersecurity practices and describe the steps being taken to address identified gap areas. | schccoalition@gmail.com | 2027-05-31 | Assessment and risk mitigation | Enhance and sustain HCCs
10 | Continuity and Recovery Plan: Extended Downtime Support Plan | This plan will be informed by the Cybersecurity Assessment and the Extended Downtime Healthcare Delivery Impact Assessment. SCHCC coordinators will collaborate with partners in the development of this plan. | The plan will include how SCHCC will address gaps in extended downtime support, as well as how the SCHCC will mitigate disruptions. | schccoalition@gmail.com | 2027-05-31 | Assessment and risk mitigation | Enhance and sustain HCCs
11 | Continuity and Recovery Plan: Recovery Plan | SCHCC Coordinators will work with clinicians, community partners, health care executives, and additional health care readiness partners to develop this plan by 6/30/2028. | This plan will address: integration with key partners, supporting the workforce, recovering critical infrastructure, managing community impact, and engaging community partners. | schccoalition@gmail.com | 2026-05-30 | Continuity and recovery | Continuity of health care service delivery
End of Worksheet

## Exercise and Improve
Readiness Plan – Implementation Planning: Exercise and Improve
Activities listed below must support exercises and improvement in the cooperative agreement.
Instructions and reminders:
Column B: Select the required activity from the dropdown selection.
Column C: Describe your readiness plan activity. Activities must include who, what, when, where, why, and how.
Column D: Describe your intended output. Outputs must be specific and measurable.
Column E: Provide the activity point of contact. This should be program or contracted personnel; listed individually, by HCC or agency.
Column F: Provide the expected completion date. Use the mm/dd/yyyy format.
Column G: Use the dropdown selection to choose the primary HPP core function.
Column H: Use the dropdown selection to choose the primary HPP outcome supported by your activity.
Item Number | HPP Requirement | Readiness Plan Activity | Intended Output | Activity Point of Contact | Expected Completion Date | Association to Core Function | Supported HPP Outcome
1 | Medical Response Surge Exercise (MRSE) | Activity 4.1 | The Contractor shall submit the MRSE and Exercise Reporting Tool. | schccoalition@gmail.com | 2026-05-31 | Training, exercise, and evaluation | 4.1 Medical Response and Surge Exercise (MRSE)
2 | Patient Movement Exercise | Activity 4.2 | The Contractor shall submit an After Action Report and Improvement Plan (AAR/IP) in CO-SHARE. | schccoalition@gmail.com | TBD | Training, exercise, and evaluation | 4.2 Patient Movement Exercise
3 | Federal Patient Movement Exercise | Activity 4.3 | The Contractor shall submit an After Action Report and Improvement Plan (AAR/IP) in CO-SHARE. |  | TBD | Training, exercise, and evaluation | 4.3 Federal Patient Movement Exercise
4 | Cybersecurity Exercise | Activity 4.4 | The Contractor shall submit an After Action Report and Improvement Plan (AAR/IP) in CO-SHARE. | schccoalition@gmail.com | 2027-06-30 | Training, exercise, and evaluation | 4.4 Cybersecurity Exercise
5 | Non-Cyber Extended Downtime Exercise | Activity 4.5 | The Contractor shall submit an After Action Report and Improvement Plan (AAR/IP) in CO-SHARE. | schccoalition@gmail.com | 2029-06-30 | Training, exercise, and evaluation | 4.5 Non-Cyber Extended Downtime Exercise
6 | Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Activity 4.6 | The Contractor shall submit an After Action Report and Improvement Plan (AAR/IP) in CO-SHARE. | schccoalition@gmail.com | 2029-06-30 | Training, exercise, and evaluation | 4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
7 | Statewide Exercise | Activity 4.7 | The Contractor shall submit an After Action Report and Improvement Plan (AAR/IP) in CO-SHARE. | eileen.brown@state.co.us | 2029-06-30 | Training, exercise, and evaluation | 4.7 Statewide Exercise
End of Worksheet

## T&E Plan Instructions
Hospital Preparedness Program (HPP) HCC T&E Plan Template Overview
Purpose | The Administration for Strategic Preparedness and Response (ASPR)’s OHCR developed a template for the T&E Plan to support you and your HCCs with completing activity requirements for the T&E Plan. Please refer to the FY 2024–2028 HPP NOFO for more information.
NOFO Instructions | Template content: The T&E Plan template contains a detailed table to organize a timeline of all planned and projected trainings and exercises for the FY 2024–2028 period of performance, beginning on July 1, 2024, and ending on June 30, 2029. An example is provided. Submission deadline and updates: The T&E Plan is due by March 31, 2025. You and your HCC(s) must provide information for trainings and exercises for all five BPs. You and your HCC(s) must make updates and submit a revised T&E Plan each BP from BP2–BP5. Please provide the date of your last update in the footer of the template. • Identify the type of exercise, which can be one of the following: • Seminar. • Workshop. • Tabletop exercise. • Drill. • Functional exercise. • Full-scale exercise. • Address communities most impacted by disasters (p. 14 of the HPP NOFO). • Include engagement with health care readiness partners, as appropriate (p. 13-15 of the HPP NOFO). • Describe how you and your HCC(s) will engage the health care workforce in trainings and exercises (p. 30 of the HPP NOFO). • Include, as appropriate, any trainings and exercises in the example list of topics (p. 89 of the HPP NOFO). Please note the following funding policies and limitations (p. 51 of the HPP NOFO): • You may not use funds to support standalone, single-facility exercises. • You may not spend HPP funds on training courses, exercises, and planning resources when similar offerings are available at no cost.
Your T&E Plan must, at a minimum, include the following required trainings and exercises:
Training/Exercise | Submission Instructions and Timeline
National Incident Management System (NIMS) training | Throughout the five-year period of performance.
Medical Response and Surge Exercise (MRSE) | Complete the exercise and submit the MRSE Exercise Reporting Tool by June 30 of each BP.
Patient Movement Exercise | Complete once, within one year of submitting the Patient Movement Plan.
Federal Patient Movement Exercise | If applicable, complete once every three years, or as required by other cooperative agreements/programs.
Cybersecurity Exercise | Complete once by June 30, 2027 (BP3).
Non-Cyber Extended Downtime Exercise | Complete once between BP3–BP5.
Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Complete once in the five-year period of performance.
Statewide Exercise | Complete once in the five-year period of performance.
If you decide to make this the Recipient T&E Plan template, recipients with large numbers of HCCs (e.g., CA) may have an issue with listing every HCC's annual MRSE.
In those situations, we can add a caveat to only list a MRSE in their plan if they have a significant role.
End of Worksheet

## T&E Plan
Readi
HCC name: | South Central Healthcare Coalition
Date of last update: | 3/17/2025 T&E Plan Link
BP1 (July 2024 - June 2025)
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
2025-11-24 | G197 AFN in Emergency Management | In-person class | Access & Functional Needs in Emergency Management | Hospitals, HCCs, EMS, Law Enforcement, Fire, Emergency Management | Department of Homeland Security SCR | fema.gov | Ed Garner edward.garner@coloradosprings.gov
2025-11-24 | EPCPH Chempack FSE | Full-scale exercise | CHEMPACK provides nerve agent antidotes to state and local governments for pre-positioning and rapid response in case of a chemical attack | Hospitals, Public Health, HCCs, EMS, Law Enforcement, Fire, Emergency Management | El Paso County Public Health | El Paso County Chempack Plan | Janel McNair janelmcnair@elpasoco.com
2025-12-24 | PRE 100 - Active Shooter Exercise Development Workshop | Workshop | Addressing the threat of an active shooter | Hospitals, HCCs, EMS, Law Enforcement, Fire, Emergency Management | HCC, Hospitals, Police, Fire, EMS, Schools, PPROEM | fema.gov | Ed Garner edward.garner@coloradosprings.gov
Self-paced online course | National Incident Management System (NIMS) training ICS 100, 200, 700, 800 | Online ICS Training | NIMS provides stakeholders across the whole community with the shared vocabulary, systems and processes to successfully deliver the capabilities described in the National Preparedness System. | All levels of government, nongovernmental organizations, and private sector stakeholders in emergency management | FEMA Emergency Management Institute | National Incident Management System (NIMS) | Ed Garner edward.garner@coloradosprings.gov
2025-01-25 | National Incident Management System (NIMS) training ICS 300 | In-person class | An intermediate course on the Incident Command System for expanding incidents. | All levels of government, nongovernmental organizations, and private sector stakeholders in emergency management | FEMA Emergency Management Institute | National Incident Management System (NIMS) | Ed Garner edward.garner@coloradosprings.gov
2025-01-25 | L-146 HSEEP (Homeland Security Exercise and Evaluation Program) | DHS Course | HSEEP provides a set of guiding principles for exercise and evaluation programs, as well as a common approach to exercise program management, design and development, conduct, evaluation, and improvement planning. | Hospitals, HCCs, EMS, Law Enforcement, Fire, Emergency Management | Department of Homeland Security SCR | fema.gov | Ed Garner edward.garner@coloradosprings.gov
2025-01-25 | EMResource Training | Self-paced online | EMResource is a web-based communications and resource management solution that helps healthcare and emergency response personnel to optimize communication and expedite patient care | HCCs, Fire, EMS, Hospitals, Public Health | CDPHE | cdphe.gov | Kara Prisock kara.prisock@coloradosprings.gov
2025-03-25 | Ancillary Care Extreme Weather Event Exercise | Tabletop Exercise | Discuss extreme weather event planning and preparation with ancillary care partners, with a focus on cross-agency communication and collaboration before, during, and after an extreme weather event. | Ancillary Care Facility Admin & Staff, HCC, CDPHE, CCHN | Colorado Community Health Network | Ancillary Care TTX SitMan | Holly Kingsbury holly@cchn.com
2025-05-25 | Mass Casualty Seminar | Seminar | A seminar directed towards hospitals and first responders on reponding to MCI's, with a focus on triaging and tracking patients. | HCCs, Hospitals, EMS, Fire | Monument Fire Department, Colorado Springs Fire Department, Pikes Peak Regional Office of Emergency Management, Plains to Peaks RETAC | Chief Greg Cassel | Chief Sean Pearson spearson@monumentfire.org
2025-05-25 | SCHCC Summit | Workshop hosted by Cybersecurity & Infrastructure Security Agency (CISA) | CISA's presenters aim to provide audience with "tangible, useful take-away information related to risk-based decision-making and security planning for critical services." | HCCs, Hospitals, Ancillary Care facilities, EMS, Fire | CISA | cisa.gov | Kindra Brewer kindra.brewer@cisa.dhs.gov
2025-06-25 | BP1 Medical Response and Surge Exercise (MRSE) | Functional Exercise | Medical Surge in the rural counties of Lake and Chaffee | Hospitals, EMS, Fire, Emergency Managers | Chaffee County Emergency Management, Heart of the Rockies Medical Center, St. Vincent Hospital | ASPR MRSE Template | Kara Prisock kara.prisock@coloradosprings.gov
BP2 (July 2025 - June 2026)
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
Self-paced online course | National Incident Management System (NIMS) training ICS 300, 700, 800 | Self-paced online course | NIMS provides stakeholders across the whole community with the shared vocabulary, systems and processes to successfully deliver the capabilities described in the National Preparedness System. | All levels of government, nongovernmental organizations, and private sector stakeholders in emergency management | FEMA Emergency Management Institute | National Incident Management System (NIMS) | Ed Garner edward.garner@coloradosprings.gov
2025-07-25 | DHSEM Inclusive Planning for AFN | In-Person Class | Access & Functional Needs in Emergency Management | Hospitals, HCCs, EMS, Law Enforcement, Fire, Emergency Management | Department of Homeland Security SCR | fema.gov | Ed Garner edward.garner@coloradosprings.gov
2025-08-25 | G386 Mass Fatalities Incident Response | In-Person Class | two-day training program that prepares local and state response personnel to manage incidents with large numbers of fatalities, such as plane crashes and terrorism events | Hospitals, HCCs, EMS, Law Enforcement, Fire, Emergency Management | Department of Homeland Security SCR | fema.gov | Ed Garner edward.garner@coloradosprings.gov
2026-06-26 | BP2 Medical Response and Surge Exercise (MRSE) | TBD | TBD | TBD | TBD | TBD | Kara Prisock kara.prisock@coloradosprings.gov
BP3 (July 2026 - June 2027)
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
Self-paced online course | National Incident Management System (NIMS) training ICS 700, 800 | Self-paced online course | NIMS provides stakeholders across the whole community with the shared vocabulary, systems and processes to successfully deliver the capabilities described in the National Preparedness System. | All levels of government, nongovernmental organizations, and private sector stakeholders in emergency management | FEMA Emergency Management Institute | National Incident Management System (NIMS) | Ed Garner edward.garner@coloradosprings.gov
2025-06-27 | Cybersecurity Exercise | TBD | Exercise Cybersecurity Support Plan | Hospitals, HCCs, EMS, Law Enforcement, Fire, Emergency Management | TBD | Cybersecurity Support Plan, CISA | Kara Prisock kara.prisock@coloradosprings.gov
2027-06-27 | BP3 Medical Response and Surge Exercise (MRSE) | TBD | TBD | TBD | TBD | TBD | Kara Prisock kara.prisock@coloradosprings.gov
2027-06-27 | Patient Movement Exercise | TBD | Exercise Patient Movement Plan | Hospitals, Fire, EMS, HCCs, Public Health | NDMS, VA FCC, CDPHE, NCRHCC, Hospitals, EMS, Airports | Patient Movement Plan | David Dykeman david.dykeman@va.gov
TBD | Federal Patient Movement Exercise | TBD | Test the NDMS Pilot Plan | Hospitals, Fire, EMS, HCCs, RETACs, Military, Airports, Emergency Management, Public Health, Government Officials | VA, NCRHCC, RETAC, CSFD, AMR, UCHealth, CommonSpirit, Children's Hospital, LTCF/SNF, PPROEM | NDMS | David Dykeman david.dykeman@va.gov
BP4 (July 2027 - June 2028)
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
Self-paced online course | National Incident Management System (NIMS) training ICS 300, 700, 800 | Self-paced online course | NIMS provides stakeholders across the whole community with the shared vocabulary, systems and processes to successfully deliver the capabilities described in the National Preparedness System. | All levels of government, nongovernmental organizations, and private sector stakeholders in emergency management | FEMA Emergency Management Institute | National Incident Management System (NIMS) | Ed Garner edward.garner@coloradosprings.gov
2028-06-28 | BP4 Medical Response and Surge Exercise (MRSE) | TBD | TBD | TBD | TBD | TBD | Kara Prisock kara.prisock@coloradosprings.gov
TBD | Non-Cyber Extended Downtime Exercise | TBD | Exercise Extended Downtime Support Plan | HCCs, Hospitals, Emergency Management | TBD | Extended Downtime Support Plan | Kara Prisock kara.prisock@coloradosprings.gov
BP5 (July 2028 - June 2029)
Projected Date | Training/Exercise | Type | Priority | Intended Audience | Partner(s) | Resource(s) | Point of Contact
Self-paced online course | National Incident Management System (NIMS) training ICS 300, 700, 800 | Self-paced online course | NIMS provides stakeholders across the whole community with the shared vocabulary, systems and processes to successfully deliver the capabilities described in the National Preparedness System. | All levels of government, nongovernmental organizations, and private sector stakeholders in emergency management | FEMA Emergency Management Institute | National Incident Management System (NIMS) | Ed Garner edward.garner@coloradosprings.gov
2029-06-29 | Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | TBD | Jurisdictional Priorities defined in strategic plan | TBD | TBD | Strategic Plan, Readiness Plan | Kara Prisock kara.prisock@coloradosprings.gov
2029-06-29 | Statewide Exercise | TBD | Collaboration among healthcare readiness partners in planning for statewide medical surge. | Public Health, Emergency Management, HCCs, & addtl. healthcare readiness partners | Public Health, Emergency Management, HCCs, & addtl. healthcare readiness partners | ASPR NOFO | Eileen Brown eileen.brown.state.co.us
2029-06-29 | BP5 Medical Response and Surge Exercise (MRSE) | TBD | TBD | TBD | TBD | TBD | Kara Prisock kara.prisock@coloradosprings.gov
End of Worksheet

## Instructions (hidden)
ASPR HPP FY2019-2023 HCC Budget: Instructions
1) Proceed to the worksheet tab for each category that funding is requested
2) For each line item, fully complete the data fields for the entire row
3) For cells with a dropdown menu, please select the most appropiate response; do not enter custom text
4) For cells requesting a custom text, be clear and concise to ensure text limits are not exceeded
5) When entering detailed justification statements, be clear and concise to ensure text limits are not exceeded.
6) All dollar amounts to be funded by the program must be fully accounted for; this includes allocation breakdowns between capabilities as well as when cost share is being applied between programs (i.e. HPP vs. PHEP)
7) All line items must be associated with an appropiate HPP activity or multiple activities; failure to identify HPP activities may result in budget restrictions
8) All HPP activities identified in the HCC Budget must be accounted for in the HCC Work Plan; failure to account for HPP activities in the HCC Work Plan may result in budget restrictions

## Sheet1 (hidden)
0. Administrative Oversight
0.1 Program Administration
0.2 Financial Administration
0.3 Sub-recipient Monitoring and Management
0.4 Program Reporting
0.5 Performance Evaluation
1. Establish governance
1.1 HCC Governance Document
1.2 Jurisdiction Information
2. Assess readiness
2.1 Risk Assessment (RA)
2.2 Hazard Vulnerability Assessment (HVA)
2.3 Readiness Assessment
2.4 Supply Chain Integrity Assessment
2.5 Workforce Assessment
2.6 Cybersecurity Assessment
2.7 Extended Downtime Health Care Delivery Impact Assessment
3. Plan and implement
3.1 Strategic Plan for FY 2024-2028
3.2 Readiness Plan
3.2.1 Training and Exercise Plan
3.3 Response Plan
3.3.1 Information-Sharing Plan
3.3.2 Resource Management Plan
3.3.3 Workforce Readiness / Resilience Plan
3.3.4 Medical Surge Support Plan
3.3.5 Patient Movement Plan
3.3.6 Allocation of Scarce Resources Plan
3.4 Continuity and Recovery Plan
3.4.1 Continuity of Operations Plan (COOP)
3.4.2 Cybersecurity Support Plan
3.4.3 Extended Downtime Support Plan
3.4.4 Recovery Plan
4. Exercise and Improve
4.1 Medical Response and Surge Exercise (MRSE)
4.2 Patient Movement Exercise
4.3 Federal Patient Movement Exercise
4.4 Cybersecurity Exercise
4.5 Non-Cyber Extended Downtime Exercise
4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement
4.7 Statewide Exercise

## Data Validation (hidden)
Data Validation
Administrative Oversight | 1. Establish Governance |  |  | 2. Assess Readiness |  |  | 3. Plan and Implement |  |  | 4. Exercise and Improve |  |  | Budget - Personnel |  | Budget - Personnel |  | Budget - Travel | Budget - Contractual |  | Budget - Indirect Costs | Budget - Match
Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select one | Select One | Select one | 0% | 0% | Select one | Select one | Select one | (Yes/No) | Select one
Program Administration | HCC Governance Document | Assessment and risk mitigation | Establish and act upon multi-year priorities | Risk Assessment (RA) | Assessment and risk mitigation | Establish and act upon multi-year priorities | Strategic Plan for FY 2024-2028 | Assessment and risk mitigation | Establish and act upon multi-year priorities | Medical Response Surge Exercise (MRSE) | Assessment and risk mitigation | Establish and act upon multi-year priorities | 0. Administrative Oversight | Recipient | 1% | 1% | In state | Commercial | Monthly | Yes | Cash
Financial Administration | Jurisdiction Information | Information sharing | Enhance and sustain HCCs | Hazard Vulnerability Assessment (HVA) | Information sharing | Enhance and sustain HCCs | Readiness Plan | Information sharing | Enhance and sustain HCCs | Patient Movement Exercise | Information sharing | Enhance and sustain HCCs | 0.1 Program Administration | Health care coalition | 2% | 2% | Out of state | Health care coalition | Quarterly | No | In-kind contributions
Sub-recipient Monitoring and Management |  | Specialty care planning and coordination | Coordination | Readiness Assessment | Specialty care planning and coordination | Coordination | Training and Exercise Plan | Specialty care planning and coordination | Coordination | Federal Patient Movement Exercise | Specialty care planning and coordination | Coordination | 0.2 Financial Administration | Multiple | 3% | 3% |  | Other public entity | Semi-Annual
Program Reporting |  | Respond | Continuity of health care service delivery | Supply Chain Integrity Assessment | Respond | Continuity of health care service delivery | Response Plan: Information-Sharing Plan | Respond | Continuity of health care service delivery | Cybersecurity Exercise | Respond | Continuity of health care service delivery | 0.3 Sub-recipient Monitoring and Management | Other | 4% | 4% |  | State or local hospital association | Annual
Performance Evaluation |  | Health care workforce support |  | Workforce Assessment | Health care workforce support |  | Response Plan: Resource Management Plan | Health care workforce support |  | Non-Cyber Extended Downtime Exercise | Health care workforce support |  | 0.4 Program Reporting |  | 5% | 5% |  | Business support services
|  | Resource management |  | Cybersecurity Assessment | Resource management |  | Response Plan: Workforce Readiness / Resilience Plan | Resource management |  | Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement | Resource management |  | 0.5 Performance Evaluation |  | 6% | 6% |  | Information Technology (IT) consulting services
|  | Training, exercise, and evaluation |  | Extended Downtime Health Care Delivery Impact Assessment | Training, exercise, and evaluation |  | Response Plan: Medical Surge Support Plan | Training, exercise, and evaluation |  | Statewide Exercise | Training, exercise, and evaluation |  | 1. Establish governance |  | 7% | 7% |  | Private laboratory (non-university affiliated)
|  | Continuity and recovery |  |  | Continuity and recovery |  | Response Plan: Patient Movement Plan | Continuity and recovery |  |  | Continuity and recovery |  | 1.1 HCC Governance Document |  | 8% | 8% |  | Security services
|  | Organizational development |  |  | Organizational development |  | Response Plan: Allocation of Scarce Resources Plan | Organizational development |  |  | Organizational development |  | 1.2 Jurisdiction Information |  | 9% | 9% |  | Temporary staff agency
[7 empty] | Continuity and Recovery Plan: Continuity of Operations Plan (COOP) | [5 empty] | 2. Assess readiness |  | 10% | 10% |  | Inter-agency department/division
[7 empty] | Continuity and Recovery Plan: Cybersecurity Support Plan | [5 empty] | 2.1 Risk Assessment (RA) |  | 11% | 11% |  | Local public health department / agency
[7 empty] | Continuity and Recovery Plan: Extended Downtime Support Plan | [5 empty] | 2.2 Hazard Vulnerability Assessment (HVA) |  | 12% | 12% |  | National or federal government agency
[7 empty] | Continuity and Recovery Plan: Recovery Plan | [5 empty] | 2.3 Readiness Assessment |  | 13% | 13% |  | Public health laboratory
[13 empty] | 2.4 Supply Chain Integrity Assessment |  | 14% | 14% |  | Tribal entities / government
[13 empty] | 2.5 Workforce Assessment |  | 15% | 15% |  | Other local government agencies
[13 empty] | 2.6 Cybersecurity Assessment |  | 16% | 16% |  | Other state government agencies
[13 empty] | 2.7 Extended Downtime Health Care Delivery Impact Assessment |  | 17% | 17% |  | Police, fire, HAZMAT, or emergency medical services
[13 empty] | 3. Plan and implement |  | 18% | 18% |  | Local schools, educational institutions, and school boards
[13 empty] | 3.1 Strategic Plan for FY 2024-2028 |  | 19% | 19% |  | Health care facilities and networks - Inpatient
[13 empty] | 3.2 Readiness Plan |  | 20% | 20% |  | Poison Control Center
[13 empty] | 3.2.1 Training and Exercise Plan |  | 21% | 21% |  | Health care facilities and networks – Outpatient
[13 empty] | 3.3 Response Plan |  | 22% | 22% |  | University (both public and private institutions)
[13 empty] | 3.3.1 Information-Sharing Plan |  | 23% | 23% |  | Faith-based organization
[13 empty] | 3.3.2 Resource Management Plan |  | 24% | 24% |  | Private non-profit organization
[13 empty] | 3.3.3 Workforce Readiness / Resilience Plan |  | 25% | 25% |  | Contracts – Other
[13 empty] | 3.3.4 Medical Surge Support Plan |  | 26% | 26%
[13 empty] | 3.3.5 Patient Movement Plan |  | 27% | 27%
[13 empty] | 3.3.6 Allocation of Scarce Resources Plan |  | 28% | 28%
[13 empty] | 3.4 Continuity and Recovery Plan |  | 29% | 29%
[13 empty] | 3.4.1 Continuity of Operations Plan (COOP) |  | 30% | 30%
[13 empty] | 3.4.2 Cybersecurity Support Plan |  | 31% | 31%
[13 empty] | 3.4.3 Extended Downtime Support Plan |  | 32% | 32%
[13 empty] | 3.4.4 Recovery Plan |  | 33% | 33%
[13 empty] | 4. Exercise and Improve |  | 34% | 34%
[13 empty] | 4.1 Medical Response and Surge Exercise (MRSE) |  | 35% | 35%
[13 empty] | 4.2 Patient Movement Exercise |  | 36% | 36%
[13 empty] | 4.3 Federal Patient Movement Exercise |  | 37% | 37%
[13 empty] | 4.4 Cybersecurity Exercise |  | 38% | 38%
[13 empty] | 4.5 Non-Cyber Extended Downtime Exercise |  | 39% | 39%
[13 empty] | 4.6 Exercise to Address Additional Jurisdictional Priorities or Areas of Improvement |  | 40% | 40%
[13 empty] | 4.7 Statewide Exercise |  | 41% | 41%
[15 empty] | 42% | 42%
[15 empty] | 43% | 43%
[15 empty] | 44% | 44%
[15 empty] | 45% | 45%
[15 empty] | 46% | 46%
[15 empty] | 47% | 47%
[15 empty] | 48% | 48%
[15 empty] | 49% | 49%
[15 empty] | 50% | 50%
[15 empty] | 51% | 51%
[15 empty] | 52% | 52%
[15 empty] | 53% | 53%
[15 empty] | 54% | 54%
[15 empty] | 55% | 55%
[15 empty] | 56% | 56%
[15 empty] | 57% | 57%
[15 empty] | 58% | 58%
[15 empty] | 59% | 59%
[15 empty] | 60% | 60%
[15 empty] | 61% | 61%
[15 empty] | 62% | 62%
[15 empty] | 63% | 63%
[15 empty] | 64% | 64%
[15 empty] | 65% | 65%
[15 empty] | 66% | 66%
[15 empty] | 67% | 67%
[15 empty] | 68% | 68%
[15 empty] | 69% | 69%
[15 empty] | 70% | 70%
[15 empty] | 71% | 71%
[15 empty] | 72% | 72%
[15 empty] | 73% | 73%
[15 empty] | 74% | 74%
[15 empty] | 75% | 75%
[15 empty] | 76% | 76%
[15 empty] | 77% | 77%
[15 empty] | 78% | 78%
[15 empty] | 79% | 79%
[15 empty] | 80% | 80%
[15 empty] | 81% | 81%
[15 empty] | 82% | 82%
[15 empty] | 83% | 83%
[15 empty] | 84% | 84%
[15 empty] | 85% | 85%
[15 empty] | 86% | 86%
[15 empty] | 87% | 87%
[15 empty] | 88% | 88%
[15 empty] | 89% | 89%
[15 empty] | 90% | 90%
[15 empty] | 91% | 91%
[15 empty] | 92% | 92%
[15 empty] | 93% | 93%
[15 empty] | 94% | 94%
[15 empty] | 95% | 95%
[15 empty] | 96% | 96%
[15 empty] | 97% | 97%
[15 empty] | 98% | 98%
[15 empty] | 99% | 99%
[15 empty] | 100% | 100%
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Tran-Kiem, Jenn @Hitchcock, Katherine @Drobac, Camila All the Data Validation options on respective tabs I relocated here to reduce user error. I suggest hiding this sheet in final version.