## Sheet1
Project Plan for Spring 2023 Chordsmen Show
All red cells prior to current month should be complete or at least in progress
|  |  | 2021 |  | 2022 | [11 empty] | 2023
TASK | ASSIGNED TO | # Months Prior to Show | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | Notes
Dates
· Set Show Date | Mark | 18 months
· Set Dress Rehearsal Date | Mark | 12 months
· Communicate Date to District | Steve P. | 12 months
· Request ASCAP/BMI Clearance | Steve P. | 12 months
Role Assignments | Mark assigns each role to a volunteer
· Location Lead |  | 18 months
· A/V Lead |  | 18 months
· Ad/Sponsor Chair |  | 12 months
· Guest Quartet - Ensemble Host |  | 12 months
· Script Writer |  | 9 months
· Ticket Lead |  | 6 months
· Publicity Lead |  | 6 months
· Program Lead |  | 6 months
· Stage Manager |  | 6 months
· Props/Set-up lead |  | 6 months
· Emcee |  | 3 months
Venue
· Identify Venue Options (appropriate with show style) | Mark | 18 months
· Key personnel review Venue Options | Mark et. al. | 18 months
· Finalize selection and contract with Venue | Mark | 18 months
Show Theme | Mark | 16 months
Show Song Selection
· Determine length of chorus portion and number of songs | Mark & Music Team | 16 months
· Determine style of show (risers, skit, etc.) | Mark & Music Team | 16 months
· Identify songs | Music Team | 14 months
· Determine which songs are already owned (charts & tracks) | Librarian | 14 months
· Purchase charts & tracks | Treasurer | 14 months
Guest Quartet
· Determine if guest groups will be included and how much time they will be allocated | Mark | 18 months
· Determine the budget for guest groups (including expenses) | Mark | 18 months
· Identify and prioritize potential guest group(s) and designate contact person | Mark, Music Team, Contact person | 17 months
· Contact potential guests and request bids with 2 wk deadline | Contact person | 17 months
· Select guest group(s) | Mark | 16 months
· Contracting | Mark | 16 months
o Written Contract Completed
§ Special Considerations (hotel rooms, table to sell CDs, etc.)
§ Date/Time of Show
§ Venue Address
§ Contact Info/Both Parties
§ Performance Fee
§ Travel Expenses
o Contact hotel and arrange rooms as needed
o Be sure to negotiate the best rate - can try to do a trade for ad in the Ad Book
· Assign Quartet Host | Mark | 12 months
· Contact guests well in advance to share show song lists to avoid duplication of music. | Quartet Host | 12 months
· Payment - a check for the performance fee to be given to the group after the show. Expenses for meals can be paid at the same time. However, airfare can be reimbursed as the expense is incurred. | Treasurer | At show
Guest School Ensemble
· Determine if guest groups will be included and how much time they will be allocated | Mark | 12 months
· Determine the budget for guest groups (including expenses) | Mark | 12 months
· Identify and prioritize potential guest group(s) and designate contact person | Mark, Music Team, Contact person | 9 months
· Contact potential guests | Contact person | 9 months
· Select guest group(s) | Mark | 6 months
· Contracting | Mark | 6 months
o Written Agreement
§ Date/Time of Show
§ Venue Address
§ Contact Info/Both Parties
§ Performance Fee
§ Travel Expenses
· Assign Ensemble Host | Mark | 6 months
· Contact ensemble well in advance to share show song lists to avoid duplication of music. | Ensemble Host | 5 months
· Payment - a check for the performance fee and expenses to be given to the group after the show. | Treasurer | At Show
Show Script | Script Team
· Draft Script and Characters | Script Writer | 6 months
· Identify people to be characters | Music Team | 4 months
· Finalize Script | Script Writer | 3 months
Publicity | Publicity Lead
· Identify various media options for show promotion |  | 6 months
· Develop messaging, logos, etc. |  | 5 months
· Design flyers, website page, Facebook content, etc. |  | 5 months
· Identify partner community groups that will help promote the show |  | 5 months
· Communicate with community group
· Implement publicity plan |  | 3 months
Sponsors/Advertisers | Ad/Sponsor Chair
· Develop/update the “sales pitch template”: Value proposition, free tickets, etc. |  | 6 months
· Provide list of past participants and encourage renewal |  | 3 months
· Provide prior year programs to members to share with potential advertisers/sponsors |  | 3 months
· Initiate sales |  | 3 months
· Monitor progress and report to membership and Mark |  | On-going
· Coordinate financials with Treasurer |  | On-going
Tickets
· Determine Ticket Pricing | Mark | 9 months
· Design Print Tickets | Ticket Lead | 6 months
· Design On-line Ticket Site | Ticket Lead | 6 months
· Print Tickets | Ticket Lead | 3 months
· Distribute Tickets to Members | Ticket Lead | 3 months
· Launch On-line Ticket Site and Coordinate with Publicity Lead | Ticket Lead | 3 months
· Monitor sales progress – report status | Ticket Lead | On-going
Show Program (To Include:) | Program Lead | 1 month
· Show Title
· Order of Performance
· Cast of Characters
· List of songs
· President Message
· Director Message
· Quartets in the show in order of appearance and their members
· Featured Guest Quartet or school group and director
· Show Committee members
· Special thanks to major donors
· Sponsors Listing
· Advertisements
· Promotion to join the chapter
· Promotion of future shows
Show Production
· Rehearsal schedules | Music Team | 14 months
· Props
o Identify all needed properties |  | 6 months
o Acquire all properties | Props/Set-up Lead | 3 months
o Deliver and remove all properties |  | Day of
· A/V Coordination
o Identify all A/V requirements | A/V Lead | 6 months
o Identify availability of equipment and operator(s) |  | 6 months
o Ensure system functions properly for show |  | Week of
· Show run throughs | Music Team | 1 month
· Stage Management (people in the right places at the right time) | Stage Manager | 1 month
· Dress rehearsal | Mark | Week of
Financial Management
· All show receipts and payments will be accounted for on a separate spreadsheet (in addition to normal Chapter financial statements) | Mark & Treasurer
· A final report will be made available to the Board and Chapter members after conclusion of show. | Mark