|  |  |  |
| --- | --- | --- |
| **East Regional Waterline Improvement Project**  **Revised Tentative Schedule**  October 22, 2019 | | |
|  | ***Revised Schedule*** | ***Previous Schedule*** |
| Informational Meeting With Villages | June 2019 |  |
| Begin Project Preliminary Design | August 2019 |  |
| 2nd Public Meeting At Allen East | Spring 2020 | Fall 2019 |
| Finalize Design | Late Spring 2020 | November 2019 |
| Obtain Pti From Oepa | Late Spring/Early Summer 2020 | December 2019 |
| Make Application To CDBG | July 1, 2020 | January 2020 |
| Bid And Award Project | November/December 2020 | February 2020 |
| Begin Construction | Early Spring 2021 | Spring 2020 |
| Complete Construction | Spring 2022 | Spring 2021 |
| Project Wrap-Up Meeting | Summer 2022 | Summer 2021 |