Princeton Community Works 2026

Post with Purpose: A Nonprofit’s Guide to Media Strategy

## Worksheet: Campaign Promotion Playbook

Objective: This checklist turns the chaos of promoting a major initiative—be it an event, a fundraising campaign, or an awareness drive—into a calm, step-by-step process. Planning your communications across a timeline helps you maximize impact and reduce last-minute stress.

Instructions: Fill in your initiative's name below. Then, use this timeline as your guide, checking off items as you complete them.

Campaign or Event Name: ____________________________________________________

### Phase 1: The Foundation (4-6 Weeks Before Launch)

This is where you build the essential assets for a successful promotion.

- [ ] Finalize Campaign/Event Details: Lock in your goal (e.g., dollars raised, volunteers recruited), key message, timeline, and call to action.

- [ ] Create Core Branding & Assets: Use Canva to create a consistent look, including graphics, social media templates, and a unique hashtag.

- [ ] Leverage Free Channels:

  - For Events: Submit to free community calendars (like Patch.com, local news sites).

  - For Campaigns: Share your goal in relevant community Facebook groups or online forums.

- [ ] Announce "It's Coming!": Post a "Save the Date" for an event or a "Get Ready" teaser for a campaign to your social media and email list.

### Phase 2: Building Momentum (2-3 Weeks Before Launch)

This is where you start telling the story behind your initiative and drive early action.

- [ ] Send Targeted Pitches: Use your Media Relationship Tracker (Worksheet 4) to email 3-5 key contacts with a personal pitch about why this initiative is newsworthy.

- [ ] Begin Regular Social Promotion: Share engaging content beyond just "donate now" or "buy tickets."

  - Fundraising Campaign: Share stories of impact showing where the money goes. Post progress-to-goal updates.

  - Awareness Campaign: Post myth-busting facts, surprising statistics, and "how-to" guides.

  - Volunteer Drive: Spotlight current volunteers and share what makes the experience so rewarding.

- [ ] Publish a Blog Post: Write an article with more details about the "why" behind your initiative.

  - Example: An interview with a client, a deeper look at the problem you're solving, or a "Top 5 Reasons to Get Involved" list.

- [ ] Create a Short Promo Video: Video is highly engaging and shareable.

  - Example: A heartfelt message from your leadership, a quick tour of your facility, or a high-energy recap video from last year's campaign.

### Phase 3: The Final Push (The Week of Launch/Deadline)

This is where you create urgency and capture last-minute attention.

- [ ] Send "Last Chance!" Communications: Email your list and post on social media with a clear call to action.

  - Example: "Only 48 hours left to reach our goal!" or "Tickets are almost sold out!"

- [ ] Send Media Update/Reminder:

  - For Events: Remind press of the details.

  - For Campaigns: Provide a mid-campaign update on your progress to reporters who showed interest.

- [ ] Plan Your "Key Day" Content: Decide who will be posting during the most critical moments.

  - For an Event: This is the day itself (live-tweeting, Instagram stories).

  - For a Campaign: This could be the launch day or the final 24 hours (live progress updates, real-time thank yous).

### Phase 4: The Follow-Up & Gratitude (1-3 Days After)

The initiative isn't over when the deadline passes. This is your chance to solidify relationships and report on your success.

- [ ] Post a Public "Thank You": Create a social media post and email blast thanking everyone who participated, volunteered, donated, and especially your sponsors (tag them!).

- [ ] Send Follow-Up Email to Participants: Thank attendees/donors for their involvement. For events, include a survey link. For fundraisers, confirm their donation was received.

- [ ] Share the Success! Report back on the results. Don't make your community guess what happened.

  - Example: Post a graphic announcing "$[Amount] raised!", "XX new volunteers signed up!", or "Our petition got XXXX signatures!" Share a photo album on Facebook or a video recap Reel on Instagram.

- [ ] Send Personal Thank You Notes: Send individual, personal emails or handwritten notes to key sponsors, major donors, key partners, and any press who covered your story.

Result: Your major initiative makes a bigger impact and feels less stressful because you followed a clear, strategic plan from start to finish.