## Single
Single Release | Title: | Release Date | 2024-04-01 | Target Date | Timing Notes
Week 1: Pre-release Preparation
Not yet started | Day 1: Finalize the single artwork and promotional materials. |  |  | 2024-03-18 | -14
Not yet started | Day 2-3: Compile a list of influencers, bloggers, and media outlets to reach out to for promotion. |  |  | 2024-03-21 | -11
Not yet started | Day 4-5: Draft press releases and promotional emails. |  |  | 2024-03-23 | -9
Not yet started | Day 6-7: Create teaser content for social media platforms. |  |  | 2024-03-25 | -7
Week 2: Pre-release Teasers
Not yet started | Day 8: Begin teaser campaign on social media platforms (e.g., snippets of the song, behind-the-scenes footage). |  |  | 2024-03-27 | -5
Not yet started | Day 9-10: Send out press releases and promotional emails to influencers and media outlets. |  |  | 2024-03-26 | -6
Not yet started | Day 11-12: Engage with followers on social media, build anticipation. |  |  | 2024-03-28 | -4
Not yet started | Day 13-14: Continue teaser campaign, encourage pre-saves or pre-orders. |  |  | 2024-03-30 | -2
Week 3: Release Week
Not yet started | Day 15: Release the single on all major music platforms. |  |  | 2024-04-01 | 0
Not yet started | Day 16-17: Share release announcements across all social media channels. |  |  | 2024-04-01 | 1
Not yet started | Day 18-19: Monitor feedback and engagement, interact with fans. |  |  | 2024-04-04 | 3
Not yet started | Day 20: Submit the single to playlists and radio stations. |  |  | 2024-04-06 | 5
Not yet started | Day 21: Thank fans for their support, continue promoting on all platforms. |  |  | 2024-04-07 | 6
Week 4: Post-release Promotion
Not yet started | Day 22: Share any positive reviews or press coverage. |  |  | 2024-04-08 | 7
Not yet started | Day 23-24: Release music video or lyric video if applicable. |  |  | 2024-04-09 | 8
Not yet started | Day 25-26: Engage in collaborations or cross-promotions with other artists or brands. |  |  | 2024-04-11 | 10
Not yet started | Day 27-28: Plan for follow-up promotions, such as acoustic versions, remixes, or live sessions. |  |  | 2024-04-13 | 12
Not yet started | Day 29-30: Evaluate the campaign's success, gather insights for future releases. |  |  | 2024-04-15 | 14
Ongoing:
Engage with fans: Respond to comments, messages, and fan-generated content.
Analyze data: Monitor streaming numbers, social media engagement, and other metrics to assess the campaign's effectiveness.
Iterate and improve: Identify areas for improvement and incorporate lessons learned into future promotional efforts.
Formulas:
Target Date = G1+[Timing Notes]
Target Date = G1+[Timing Notes, row above]

## Album
Album Release | Title: | Release Date | 2024-04-01 | Target Date | Timing Notes
1-2 Months Before Release: Pre-Release Preparation
Not yet started | Week 1-2: Finalize the record including mastering, artwork, and packaging. |  |  | 2024-01-29 | -63
Not yet started | Week 3-4: Plan promotional strategy, including press releases, interviews, and marketing materials. |  |  | 2024-02-12 | -49
Not yet started | Week 5-6: Schedule release date, distribution, and promotional events. |  |  | 2024-02-26 | -35
3-4 Weeks Before Release: Pre-Release Teasers
Not yet started | Week 7: Start teasing snippets of tracks, behind-the-scenes footage, or artwork on social media. |  |  | 2024-03-11 | -21
Not yet started | Week 8: Send out press releases and promotional materials to media outlets and influencers. |  |  | 2024-03-18 | -14
Not yet started | Week 9: Arrange exclusive premieres with music blogs or magazines for singles or tracks from the record. |  |  | 2024-03-25 | -7
Release Week: Record Launch
Not yet started | Day 1: Release the record on all major music platforms and announce it on social media. |  |  | 2024-04-01 | 0
Not yet started | Day 2-3: Engage with fans, share excitement, and encourage feedback and reviews. |  |  | 2024-04-01 | 1
Not yet started | Day 4-5: Host virtual listening parties or live stream performances showcasing the record. |  |  | 2024-04-05 | 4
Not yet started | Day 6-7: Submit the record to curated playlists and radio stations for potential airplay. |  |  | 2024-04-07 | 6
Not yet started
1-2 Weeks After Release: Post-Release Promotion
Not yet started | Week 2-3: Share any positive reviews, press coverage, or notable milestones reached. |  |  | 2024-04-15 | 14
Not yet started | Week 3-4: Release music videos, lyric videos, or visualizers for tracks from the record. |  |  | 2024-04-22 | 21
Not yet started | Week 4-5: Plan for follow-up promotions such as remixes, acoustic versions, or live sessions. |  |  | 2024-04-29 | 28
Not yet started | Week 5-6: Consider merchandise bundles or limited edition releases to sustain interest. |  |  | 2024-05-06 | 35
Ongoing:
Engage with fans: Respond to comments, messages, and fan-generated content on social media.
Analyze data: Monitor streaming numbers, social media engagement, and sales to assess the campaign's effectiveness.
Plan future releases: Use insights gathered to inform future promotional efforts and releases.
Stay active: Continue promoting the record through live performances, interviews, and collaborations to maintain momentum.
Formulas:
Target Date = G1+[Timing Notes]
Target Date = G1+[Timing Notes, row above]