## Slide 1: Gymnastics Newfoundland & Labrador Strategic Plan 2022 - 2025
Presented by: Lindsay Winters & Sarah Byrne

## Slide 2: AGENDA
Background
Key Goals
​Draft “In Progress” Work Plan
​Summary​

## Slide 3: BACKGROUND
Engaged Darlene Scott of Community Sector Counsel (CSC) to assist in the identification of key strategic priorities to form the basis of a new GNL Strategic Plan
CSC interviews with stakeholders held earlier in 2022: GNL Board of Directors and staff; and volunteers and staff of 11 GNL member clubs
CSC shared preliminary findings with GNL Board and member clubs at April 7/22 meeting
Three key goals identified along with various supporting objectives
GNL Strategic Plan focused on effectively supporting clubs, enhancing member service and ensuring effective, sustainable GNL operations into the future
Draft work plan “in-progress”; actions and responsible stakeholders being identified; future detail and timelines to be developed
Three key goals identified
1. Review of GNL Governance
2. Develop new communications strategies
3. Realign members services

## Slide 4: KEY GOALS
GOVERNANCE STRUCTURE
Governance structure dispersed more regionally at the board level and supported with committee structures based on club inputs
COMMUNICATIONS PLAN
Communication strategies and tools that allow for and promote and improve collaboration opportunities between and among clubs
Realign member services
Realign member services to reflect the differing nature and size of clubs that belong to GNL

## Slide 5: DRAFT “IN PROGRESS” WORK PLAN

## Slide 6: GOVERNANCE STRUCTURE
Goal | Supports | Draft Action Plan | Engagement | Target Completion
 | By-Law Review | Strike committee to evaluate: Procure other PSO by-laws to determine best practices Develop Terms of Reference Invite member club participation | Board Committee/Clubs | 
 | Succession Planning-Staff | Phase 1 Detailed Job Descriptions Roles and responsibilities Annual Program Calendar for all positions Organizational Structure reconfiguration and graphics to be disseminated and posted Establish pay brackets for positions Phase 2 Forecast HR needs Apply information gained from forecast to current situation – who do we have? What can they do? Where do we need to develop or hire? Outsourcing – are there business functions that are best done via contract? | Board Committee/GNL Staff | 
 | Succession planning GNL board | Recruitment & nominations Standardize timelines for call for nominations and nomination forms Strike ad hoc committee to engage potential new board members Determine if nominations document is current Review of director’s manual Annual report card for board members | Board Committee/GNL Staff | 
Governance Structure
DRAFT FOR DISCUSSION PURPOSES ONLY

## Slide 7: COMMUNICATIONS STRATEGY
Goal | Supports | Draft Action Plan | Engagement | Target Completion
 | Redevelop Website | Reconstruct the GNL website so it is easily navigated: Identify key areas to highlight on main page Compile resources necessary to functionality in each key area and post Send out memo on changes and where to find information now | GNL Staff | 
 | Communication Plan | Improve internal communications: Implement weekly staff meetings Align workflow and information dissemination with newly adapted organizational structure and roles and responsibilities Establish communication lines electronically, via phone, and plan annual in person staff meeting. Collaborate with PSO’s, NSO’’s and Sport Law to determine best practices Draft a Communication’s Policy Improve External Communications Increase Operations council meeting to quarterly Update and disseminate terms of reference for technical committees Update technical committee membership and create document to be disseminated to membership Implement quarterly newsletter Reinforce effective communication lines with newly established organizational structure/roles & responsibilities Establish key contacts for all areas of business at clubs Create database of media contacts for entire province (geographic areas pertaining to newsworthiness) Create and send out press releases for results | GNL Staff | 
 | Social Media Plan | Utilize existing social media platforms: Create/maintain accounts with Facebook, Instagram, Twitter and Tik Tok Assign Human Resources to update platforms Create social media calendars for posts: Weekly established posts (ex/motivation Monday, Athlete highlight, Coach highlight, Volunteer highlight) Ensure results and accomplishments are highlighted across all platforms Branding: Standardize GNL logo and get proper files for profile pictures and pages | GNL Staff | 
Communications Strategy
DRAFT FOR DISCUSSION PURPOSES ONLY
7

## Slide 8: MEMBER SERVICES
Goal | Supports | Draft Action Plan | Engagement | Target Completion
 | Committee Structures | Technical Committees Edit and approve terms of reference for all technical committees Ensure committees are educated and knowledgeable about the scope of their work Communicate committee members roster to membership and post on website inclusive of dates of terms Standardize timelines and nomination forms for technical committees Review composition of technical committees | GNL Staff/Clubs | 
 | Policy Review | Determine key policies for review & prioritize Structure Terms of reference for review and committee structure Strike committee | Board/GNL Staff/Clubs | 
 | Club Development | Construct a committee structure to develop a plan for club recruitment and development | GNL Staff/Clubs | 
 | Evaluation | Evaluate the impact of realigned members services with annual member surveys | Board/GNL Staff | 
Member Services
DRAFT FOR DISCUSSION PURPOSES ONLY

## Slide 9
Work plan to be further developed in 2022
Strategic Plan to be executed over the next 3 years
Engagement with member clubs important especially on review of governance structure and committee structures
Update membership on Strategic Plan activities/progress during the year
SUMMARY