## TEMPLATE
Complexity (New / Change) | Hrs | PD
Simple_N | 16 | 2
Medium_N | 32 | 4
Complex_N | 48 | 6
Simple_C | 8 | 1
Medium_C | 16 | 2 | Contingency | 12%
Complex_C | 32 | 4 | Screen/Components ( Including Binding )
TEAM / EPIC | Use Case | Comments | Desktop / PWA | Mobile (iOS) | Mobile (Android) | API | Desktop / PWA | Mobile (iOS) | Mobile (Android) | API | Total Efforts (PD) With Contingency 12% | Desktop/ PWA (PD) | iOS (PD) | Android (PD) | API PD | Dev Total PDs | QA @30% (PD's) | Dev + QA (PDs) | Mgmt Effort (15%) | Arch Design (10%) | Total Efforts (PD)
Sample Homepage | Vault page for FS products |  | 2 | 1 | 1 | 1 | Medium_C | Medium_C | Medium_C | Medium_C | 18.2 | 4 | 2 | 2 | 2 | 10 | 3 | 13 | 1.95 | 1.3 | 16.25
Sample Channels Integration | Channels Integration |  |  |  |  | 0.5 |  |  |  | Complex_N | 5.46 | 0 | 0 | 0 | 3 | 3 | 0.9 | 3.9 | 0.585 | 0.39 | 4.875
Marketing/CS/Analytics/Content | Content mgmt |  | 0.5 | 0.5 | 0.5 | 0.5 | Medium_N | Medium_N | Medium_N | Medium_N | 14.56 | 2 | 2 | 2 | 2 | 8 | 2.4 | 10.4 | 1.56 | 1.04 | 13
Data encryption | Data |  | 1 | 1 | 1 | 1 | Medium_C | Medium_C | Medium_C | Medium_C | 14.56 | 2 | 2 | 2 | 2 | 8 | 2.4 | 10.4 | 1.56 | 1.04 | 13
[10 empty] | Total | 52.78 | 8 | 6 | 6 | 9 | 29 | 8.7 | 37.7 | 5.655 | 3.77 | 47.125