## Instructions
PROJECT RESOURCE PLANNING TOOL
Purpose
Use the tol to plan for resource capacity by sprint/iteration.
Instructions
1. Tailor the Resource Planning worksheet to your organization by entering the resource type, core team resource names and % allocation. Then for each sprint/iteration log the # days off, available hours, and planned hours.

## Resource Planning
PROJECT RESOURCE PLANNING TOOL
Resource Capacity by Sprint/Iteration
Agile teams typically create this for each sprint/iteration. |  |  |  |  | From | To | Working Days |  | From | To | Working Days
Illustrative |  |  |  |  | 2012-12-12 | 2013-01-01 | 15 |  | 2012-01-02 | 2013-01-30 | 15
|  |  |  | Sprint/Iteration One |  |  |  | Sprint/Iteration Two
Resource Type | Core Team Resouces Names | Resources Names | % Alloaction | # Days Off | Available Hours | Planned Hours | % Utilization | # Days Off | Available Hours | Planned Hours | % Utilization
Contractor | Java Dev. | John Smith | 100% | 1 | 112 | 100 | 89.29% | 0 | 120 | 100 | 83.33%
Employee | Sr. Java Dev. | Mary Smith | 100% | 0 | 120 | 135 | 112.5% | 0 | 120 | 135 | 112.5%
Employee | QA Tester | Alan Smith | 75% | 2 | 74 | 40 | 54.05% | 0 | 90 | 40 | 44.44%
Contractor | Scrum Mst. | Beth Smith | 80% | 1 | 88 | 0 | 0% | 0 | 96 | 0 | 0%
Employee | Bus. Analyst | Larry Smith | 65% | 0 | 78 | 55 | 70.51% | 0 | 70 | 55 | 78.57%
Employee | Product Owner | JoAnne Smith | 40% | 0 | 48 | 40 | 83.33% | 0 | 40 | 40 | 100%
Employee | Business User | Amy Adams | 50% | 0 | 60 | 65 | 108.3% | 1 | 60 | 65 | 108.3%
Shared Resources
Employee | Architect (30%) | Ronnie Smith | 25% | 2 | 14 | 20 | 142.9% | 1 | 30 | 20 | 66.67%
Employee | Report Designer (10%) | Jackie Smith | 10% | 0 | 12 | 15 | 125% | 0 | 4 | 15 | 375%
Employee | ETL Resource (10%) | Doug Smith | 10% | 0 | 12 | 10 | 83.33% | 1 | 12 | 10 | 83.33%
Contractor | Portal Resource | Greg Smith | 30% | 2 | 20 | 15 | 75% | 0 | 36 | 15 | 41.67%
Employee | Business SME for X | Tomy Smith | 25% | 1 | 30 | 15 | 50% | 0 | 22 | 30 | 136.4%
Employee | IT SME for X | Jonny Smith | 25% | 0 | 22 | 30 | 136.4% | 1 | 30 | 20 | 66.67%
Employee | DBA | Karen Smith | 40% | 1 | 48 | 20 | 41.67% | 2 | 48 | 15 | 31.25%