## Instructions
BACKLOG AND PROGRESS TRACKING TOOLKIT
Purpose
Use this tools to track story backlogs and progress of project costs and story points delivered across sprints/iterations.
Instructions
1. Tailor the Story Backlogs worksheet to your organization by entering the features, stories, story points, and any change management notes.
2. Tailor the Progress Tracker worksheet to your organization by entering target and actual points, target and actual costs, and total funding for each sprint/iteration.
3. Adjust the number of stories, releases, and iterations as needed.

## Story Backlogs
STORY BACKLOG TRACKING TOOL
Agile teams create the backlog during the initial release scope planning meeting and continue to update it throughout the project.
Illustrative
Story |  | Story Points | Release # | Change Management Notes
1 - Security
1.1 Customer Login |  | 2 | 1
1.2 Customer registers for now online account |  | 3 | 1
1.3 Customer retrieves forgotten password |  | 3 | 1
1.4 Customer adds password hint |  | 2 | 2 | Canceled this story on 12/22 due to request. Will send email to customer service to get password reset.
2 - Profile Management
2.1 Customer creates new profile |  | 5 | 1
2.2 Customer updates existing profile |  | 2 | 1 | This was a 5 and was re-estimated during the retrospective to a 2 because the team found that most work was already done in 2.1.
3 - Place Order
3.1 Customer searches product list |  | 3 | 1
3.2 Customer browses all products |  | 2 | 1
3.3 Customer adds product to cart |  | 5 | 1
3.4 Customer completes order |  | 8 | 1
3.5 Customer views product reviews |  | 5 | 1 | Added this story during iteration 2. Product owner approved on dd/mm/yyyy.
4 - Fill in Stories as needed.
4.1 As needed
4.2 As needed
4.3 As needed
….
….
Original Story Points for Release 1 |  | 35
New Points for Release 1 |  | 5
Total Points for Release 1 |  | 40 | 12.5% | Change in Scope

## Progress Tracker
PROGRESS TRACKER TOOL
Agile teams can create this during their first sprint/iteration planning meeting and update throughout all sprints/iterations.
Story Points | Illustrative
Sprint/Iteration | Targeted Points | Actual Points | Total Funding
0 | 5 | 1 | 5
1 | 10 | 2 | 5
2 | 15 | 3 | 6
3 | 20 | 4 | 5
4 | 25 | 5 | 9
5 | 30 | 6 | 5
…
…
Cost | Illustrative
Sprint/Iteration | Targeted Cost | Actual Cost | Total Funding
0 | 100000 | 150000 | 100000
1 | 150000 | 150000 | 150000
2 | 200000 | 150000 | 225000
3 | 225000 | 225000 | 225000
4 | 235000 | 225000 | 225000
5 | 400000 | 225000 | 400000
6 | 500000 | 225000 | 400000
…
…