## Instructions
Agile Readiness Scorecard
I. Purpose: Many organizations choose between Agile and Waterfall on an ad-hoc basis. However, leading IT groups recognize that the selection of the right methodology plays a key role in the realization of project benefits. Use this tool to identify if the inititiave, team, and organizational environment factors are ideal for Agile delivery and create an action plan to mitigate risks of readiness gaps.
II. Audience: Project managers, development leads, and project oversight boards that make the decision on development methodology (often in consultation with their teams, the head of Applications and/or the PMO).
III. Tab - Agile Readiness Assessment : This tab details 16 factors of Agile Readiness Assessment organized in three sections: Readiness of Project/Work Characteristics (Section I), Readiness of Sponsors and Stakeholders (Section II), and Readiness of Team and Project Resources (Section III). Input the rating of individual factors specific to the initiative in this tab. Each factor has been assigned default weights based on members’ qualitative input and a survey of member institutions, users have the option to update the weights as required.
IV. Tab- Dashboard and Action Plan: Based on your selections in the tab "Agile Readiness Assessment," the overall assessment will appear in the tab, "Dashboard and Action Plan" as "Not Recommended for Agile", "Consider for Agile", or "Recommended for Agile." This tab also enables you to articulate action plans to mitigate risks in case of gaps in readiness criteria.
V. Feedback: We welcome feedback on the use of this Scorecard. You may direct questions and ideas to Applications.Support@cebglobal.com or Pmo.Support@cebglobal.com.
APPLICATIONS LEADERSHIP COUNCIL
PMO LEADERSHIP COUNCIL

## Agile Readiness Assessment
Agile Readiness Assessment
Project Name: |  | Project Lead:
| Factors | Rating |  |  | Relative Weight of Factor | Numerical value of weights |  |  |  |  | Action Plan
No. | I. Project/Work Characteristics | Not at All | Somewhat | Totally |  |  | Linked Cell (Option buttons) | Weights (Sum=1) | Score | Weighted Score
1 | Business value of the initiative depends on rapid delivery. |  |  |  | High | 3 | 1 | 8.824% | 0 | 0 | Not Applicable
2 | User interfaces, web development, or data analytics are key components of project. |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Not Applicable
3 | The project does not interface with legacy systems (e.g. mainframe). |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Not Applicable
4 | Scope or high-level requirements are unclear or may change. |  |  |  | Medium | 2 | 1 | 5.882% | 0 | 0 | Not Applicable
| [Additional Factor] |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Not Applicable
| [Additional Factor] |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Not Applicable
| Readiness of Project/Work Characteristics | Low
| II. Sponsors and Stakeholders | Not at All | Somewhat | Totally
5 | There is a single senior stakeholder, rather than multiple stakeholders. |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
6 | Product owner or sponsor is available and empowered to make decisions quickly. |  |  |  | High | 3 | 1 | 8.824% | 0 | 0 | Need Action Plan
7 | Product owner or sponsor has past experience or is trained on Agile methods. |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
8 | Product owner or sponsor is knowledgeable of customer/end user segments. |  |  |  | High | 3 | 1 | 8.824% | 0 | 0 | Need Action Plan
9 | Key functional partners (Legal, Finance etc.) understand and can support Agile ways of working. |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
| [Additional Factor] |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
| [Additional Factor] |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
| Readiness of Sponsor and Stakeholders | Low
| III. Team and Project Resources | Not at All | Somewhat | Totally
10 | Team can be dedicated full time for this initiative. |  |  |  | Medium | 2 | 1 | 5.882% | 0 | 0 | Need Action Plan
11 | Team is co-located. |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
12 | Team has past experience or is trained on Agile methods. |  |  |  | High | 3 | 1 | 8.824% | 0 | 0 | Need Action Plan
13 | Team is experienced in the project's technology and business domains. |  |  |  | Medium | 2 | 1 | 5.882% | 0 | 0 | Need Action Plan
14 | Team has past experience of working together. |  |  |  | Medium | 2 | 1 | 5.882% | 0 | 0 | Need Action Plan
15 | Vendors, if involved, have Agile experience. |  |  |  | Medium | 2 | 1 | 5.882% | 0 | 0 | Need Action Plan
16 | Agile training and coaching support is available throughout the project lifecycle. |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
| [Additional Factor] |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
| [Additional Factor] |  |  |  | Low | 1 | 1 | 2.941% | 0 | 0 | Need Action Plan
| Readiness of Team and Project Resources: | Low
| Overall Agile Readiness: | Not Recommended for Agile
Note on B9: 2 blank rows have been left in each section in case you would like to add additional factors.
Note on H3: We have included default weights for each criterion. Please change the weights here as necessary, with Low being the least important and High being the most important.

## Dashboard and Action Plan
Dashboard and Action Plan
Agile Readiness Dashboard
| Readiness of Project/Work Characteristics | Low
| Readiness of Sponsor and Stakeholders | Low
| Readiness of Team and Project Resources | Low
| Overall Agile Readiness | Not Recommended for Agile
| Criteria | Relevance to Agile Delivery | Need Action Plan | Action Plan : Key Steps to Ensure Agile Success | Examples of Key Steps
I. Readiness of Project/Work Characteristics
1 | Business value of the initiative depends on rapid delivery | When the rapid and incremental delivery of outcomes is critical for business impact, the use of Agile delivery methods is highly recommended. Incremental delivery also helps reduce and manage risks through finding issues faster. | Not Applicable
2 | User interfaces, web development, or data analytics are key components of project | Projects that involve highly intuitive interfaces and data-driven decisions are typically more suitable for Agile because they require business partners' iterative feedback to deliver customer-centric output. | Not Applicable
3 | The project does not interface with legacy systems (e.g. mainframe) | Legacy and mainframe projects involve more complexity and interdependencies that typically make Agile delivery challenging. | Not Applicable
4 | Scope or high-level requirements are unclear or may change. | Agile works best for projects where requirements are unclear as Agile approaches help clarify and refine evolving requirements. | Not Applicable
Number | II. Readiness of Sponsor and Stakeholders
5 | There is a single senior stakeholder, rather than multiple stakeholders. | Differing perspectives and guidances from multiple senior business partners on customer or business requiremente can create coordination and decision delays. | Need Action Plan |  | E.g., Rightsize the number of business stakeholders who will make critical business decisions on the initiative. Build escalation and/or delegation mechanisms to ensure faster business decisions.
6 | Product owner or sponsor is available and empowered to make decisions quickly. | Agile initiatives require consistent feedback and decision support from product owners and sponsors to succeed. | Need Action Plan |  | E.g.,Communicate product owner/sponsor role expectations in Agile contexts.
7 | Product owner or sponsor has past experience or is trained on Agile methods. | Training or prior experience with an Agile project improves the likelihood of the sponsor or product owner embracing his/her role in an Agile project. | Need Action Plan |  | E.g., Create opportunities for business partners to participate in Agile coaching sessions and Agile project simulations.
8 | Product owner or sponsor is knowledgeable of customer/end user segments. | The product owner must understand if customer needs are being met throughout the project. | Need Action Plan |  | E.g., Identify SMEs who have the requisite customer segment knowledge to partner with the product owner on the initiative.
9 | Key functional partners (Legal, Finance etc.) understand and can support Agile ways of working. | Coordination processes between delivery teams and functional partners are often aligned to Waterfall methods, which can create bottlenecks and delays with Agile. | Need Action Plan |  | E.g., Work with partner functions to redesign processes and identify automation opportunities to better align to Agile methods.
| [Additional Factor] |  | Need Action Plan
| [Additional Factor] |  | Need Action Plan
III. Readiness of Team and Project Resources
10 | Team can be dedicated full time for this initiative. | A dedicated team fully committed to a critical initiative has higher productivity and throughput. They are also more likely to deliver effective outcomes aligned to the project priorities. | Need Action Plan |  | E.g., Communicate expectations of individual team member deliverables and timelines upfront.
11 | Team is co-located. | Colocation of Agile team members facilitate better formal and informal interactions required for faster delivery of initiatives. | Need Action Plan |  | E.g., Utilize collaboration tools to enable virtual collaboration.
12 | Team has past experience or is trained on Agile methods. | Training on Agile techniques and methodology or past Agile experience enhances team members' abilities to leverage Agile techniques. | Need Action Plan |  | E.g., Create opportunities for project teams to participate in Agile coaching sessions and Agile project simulations.
13 | Team is experienced in the project's technology and business domains | Because Agile requires rapid work, a lack of domain knowledge could hinder an Agile team from succeeding in iterative sprints. Familiarity with the business domain (e.g., supply chain or finance) supports an Agile team's ability to work iteratively and closely with the sponsor or product owner. | Need Action Plan |  | E.g., Invite business or technology domain experts to team meetings to help the team improve their domain knowledge.
14 | Team has past experience of working together. | When team members have experience working together in the past, it has a significant impact on business outcomes. | Need Action Plan |  | E.g., Define communication and collaboration expectations during early team dicussions. Hold informal coffee meetings or team outings to establish team familiarity early on.
15 | Vendors, if involved, have Agile experience | Third-party vendors without background in Agile methodology can increase complexity and delivery time. | Need Action Plan |  | E.g., Establish expectations of vendor team participation in Agile initiatives. Clarify the Agile processes in your organization during vendor onboarding.
16 | Agile training and coaching support is available throughout the project lifecycle | Agile coaches are good to have to provide sustained guidance to help teams gain confidence in Agile delivery. | Need Action Plan |  | E.g., Identify experienced Scrum Masters who can coach other Agile teams when required.
| [Additional Factor] |  | Need Action Plan
| [Additional Factor] |  | Need Action Plan

## Sheet2 (hidden)
High | 3
Medium | 2
Low | 1

## Sheet1 (hidden)
Low
Medium
High