## Cover Page
< Project / Application Name>
Functional Test Estimation
| Project / Application ID: | <Specify a unique project / application identifier >
| Version | <x.y>
| Purpose Statement: | The purpose of this document is to derive the estimated effort for a functional testing project using the concept of Test Case Points
| Author: | <Specify current author of this document>

## Instructions
TEST EFFORT ESTIMATION TOOL
1.0 Purpose of this Tool
Test Case Point (TCP) analysis is an approach for doing an accurate estimation for Manual testing. This approach emphasizes on key testing factors that determine the complexity of the entire testing cycle and gives us a way of translating test creation efforts to test execution efforts, which is very useful for estimating the testing activities. In other words, TCP is a way of representing the efforts involved in manual testing projects. TCP tool can be used for different levels of test estimation. Each level of estimation should be an update to the previous level estimation. The estimation should be versioned and maintained in a centralized place to track changes.
2.0 Instructions
1. Identify Requirements /Test Cases and its complexity 2. Determine Test Case Point for Test Case generation 3. Determine Test Case Point for manual execution 4. Determine total TCP
3.0 Test Case Points Estimation Process (Manual Testing)
Step 1: To determine the TCP for Test Case generation, first determine the complexity of the Test Cases. Some Test Cases may be more complex due to the inherent functionality being tested. The complexity will be an indicator of the number of TCPs for the Test Case. The Test Case generation complexity can be determined based on the below factors
Test Case Generation Complexity Factors |  | Description
Transactions |  | Any request or response to and from database or any storage location.
Interface with Other Test Cases |  | Dependency of a test case on another test case(s). There might be cases where a series of steps/test cases needs to be performed before starting to execute the actual test case. These steps/test cases would have a direct impact on the test case.
The Number of Verification Points/Steps in the Case |  | Any logical step in a test case that has an expected output to be verified.
Establishing Baseline Data |  | If the outcome of a test case has a critical dependency on the input test data, then the input test data is considered as a baseline test data.
The complexity of a Test Case is determined based on the number of transactions, number of interface with other cases, number of verification points and Baseline test data as indicated in Table below:
Complexity Type | Complexity of Test Case | Interface with Other Test Case | Number of Verification Points
Simple | < 3 transactions | 0 | < 3
Average | 3-6 transactions | <3 | 3-8
Complex | > 6 transactions | >3 | >8
Note : Complexity type of any test case is determined by taking the highest order of any of the parameters identified for that scenario. eg. If a Test Case has >8 verification points but only 1 transaction, the Test Case is considered as complex.
Step 2: Identify the total number of simple, average and complex Test cases for each of the Requirement Classification as below
Requirement Classification | Simple | Average | Complex | Total
Requirement1
Requirement2
Requirement3
……
Total | =sum of all the simple cases | =sum of all the average cases | =sum of all the complex cases
Step 3: Simple, Average and Complex Test Cases have an associated adjustment weight as:
Test Case Type | Adjustment Weight
Simple | 2
Average | 4
Complex | 8
Based on the adjustment weight, total TCP is calculated by using the formulae give below: Total Test case Points= (# of Simple Test Cases X 2) + (# of Average Test Cases X 4) + (# of Complex Test Cases X 8) Where 2, 4, 8 are the adjustment factors for simple, average, and complex Test Case types
Step 4: Independent adjustment factors
Factor Number |  | Description |  | Total No
F11 - If more than 1 OS combination to test, specify number |  | Operating System Combinations |  | 1
F12 - If more than 1 Browser to test, specify number |  | Browser Combinations |  | 1
Some of the other factors that could influence the effort estimation are Number of Operating Systems and number of Browsers in which the application needs to be tested.
Step 5: Adjustment factors for Manual Testing
Factor Number | Description |  | Factor Weight | Complexity Weight | Result | Adjustment Factor
F1 | Domain Knowledge & Complexity |  |  |  | 0 | 0
F2 | Software/Hardware Set Up |  |  |  | 0 | 0
F3 | Environment Set Up |  |  |  | 0 | 0
F4 | Build Management |  |  |  | 0 | 0
F5 | Configuration Management |  |  |  | 0 | 0
F6 | Preparation of Test Bed |  |  |  | 0 | 0
F7 | Stable Requirements |  |  |  | 0 | 0
F8 | Offshore/Onsite Coordination |  |  |  | 0 | 0
F9 | Test Data Preparation |  |  |  | 0 | 0
Factors
Factor Number | Description |  | Details
F1 | Domain Knowledge & Complexity |  | This factor is applicable if domain knowledge is a pre-requisite for testing effort. For e.g. testing of ADS applications requires annuities specific knowledge
F2 | Software/Hardware Set Up |  | Software and/or hardware set up such as simulators, plug-ins etc that would be required for testing
F3 | Environment Set Up |  | Complexity of environment setup process for the application under test. For e.g. environment setup for testing third party applications are deemed complex as there are lot of dependencies involved.
F4 | Build Management |  | Build management is to keep track and control the code migrated to the environment under test
F5 | Configuration Management |  | Configuration management is detailed recording and updating of information that describes an application systems and networks, including all hardware and software components. For e.g., Information of versions and updates that have been applied to installed software packages, network addresses of hardware devices.
F6 | Preparation of Test Bed |  | Identify and prepare test bed (from production or feeds) before test case generation or test execution as required
F7 | Stable Requirements |  | Impact of frequent changes in the requirement
F8 | Offshore/Onsite Coordination |  | This factor is applicable if the project is executed from 2 geographic locations
F9 | Test Data Preparation |  | Effort required for preparation of test data for testing. For e.g. production-like data supplied may need to be masked before it is made available
a) Factor Weight Factor Weight denotes the relevance of the factor in a particular project and is applicable only if it’s in scope for testing in that project. This value will vary from 0 to 10 with 0 being no relevance to 10 being the highest relevance. b) Complexity weight Complexity Weight should be considered based on the expertise required to manage a particular factor. This value will vary from 0 to 3 with 1 indicating less complexity in managing the factor while 3 indicating a requirement for high expertise to manage that factor. Complexity Weight takes into count the expertise that a project organization has and the amount of complexity that is foreseen in the project due to this factor. c) Adjustment factor Adjustment factor= Application Level Parameter’s Assigned (Factor weight * complexity weight)/ (Maximum Factor Weight*Maximum Complexity Weight) Example - Assume a factor weight of 10 and complexity weight of 1 for the parameter ‘Understanding the Insurance Domain’, the adjusted weight is calculated as 10 *1 /30 = .33. Where the denominator 30 denotes the product of maximum complexity weight by maximum factor weight, here the maximum complexity weight is 3 and the maximum factor weight is 10, hence 30.
Step 6: Estimate for Manual Test Case Generation The adjustment factors which influence manual Test Case generation are taken into consideration and the total adjustment factor for manual test generation is arrived. Some of the factors are mentioned below:
Factors - F1 | Adjustment factor
Factors - F9 | Adjustment factor
Factors - F7 | Adjustment factor
Factor - F8 | Adjustment factor
Total of Adjustment factor
Total factor =sum of adjusted weight / no of factors E.g. 1.63 / 4 =0.36 Adjustment Factor = 1 + Total Factor = 1 + .36 = 1.36 Person Hours per TCP indicates the effort in hours required to complete One Test Case Point NOTE: Person Hours per TCP (testing productivity) is arrived at based on the actual values from past projects in the organization. Total Hrs for manual test case generation = TCP * Adjustment Factor * Person Hours per TCP
Step 7: Estimate for Manual Test Case Execution The adjustment factors which influence manual Test Case execution are taken into consideration and the total adjustment factor for manual test execution is arrived. Some of the factors are mentioned below:
Factor - F1 | Adjustment factor
Factor - F2 | Adjustment factor
Factor - F3 | Adjustment factor
Factor - F4 | Adjustment factor
Factor - F5 | Adjustment factor
Factor - F6 | Adjustment factor
Factor - F7 | Adjustment factor
Factor - F8 | Adjustment factor
Total of Adjustment factor
Total factor =sum of adjusted weight / no of factors Adjustment Factor = 1 + Total Factor Person Hours per TCP indicates the effort in hours required to complete One Test Case Point Total Person Hours for manual test case execution = TCP * Adjustment Factor * Person Hours per TCP The Overall Total Effort is computed by summing up the individual efforts calculated for Test Case generation, test automation, and manual and automated test execution. Total Person days = Total Effort / Number of working hrs per day, The total TCP is indicative of the size of the testing project.
Step 8: a) In the 'Effort Summary Sheet', the effort required for Manual test case Preparation, Manual test execution are automatically populated from the TCP estimate sheet. b) The effort required for performing project's other activities such as Strategy and Plan Preparation, requirements ambiguity discussion, Defect tracking, Metrics Collection, Management Activities, etc needs to be added. The total effort in Person Days and Person Months are arrived by adding all the individual effort.
7.0 General - Color coding
Existing / Computed / derived field - Must not enter values
| 0 | To be filled by the user - Editable field
Section divider / heading
Indicates the sequence for entering data
5
1
5
Note on A48: Add or replace as many factors that is applicable for Testing
Note on A60: Add or replace as many factors that is applicable for Testing

## Test Case Points Scorecard
TEST EFFORT ESTIMATION SCORECARD
Complexity of Test Cases
Complexity Type | Complexity of Test Case | Interface with Other Test Case | Number of Verification Points
Simple | < 3 transactions | 0 | < 3
Average | 3-6 transactions | <3 | 3-8
Complex | > 6 transactions | >3 | >8
Test Case Classification : Identify the total number of simple, average and complex Test cases for each of the Requirement Classification in the below table. Refer the Complexity of Test cases table to determine the complexity
Test Case Classification (based on complexity)
Requirement Classification | Simple | Average | Complex | Total
<Functionality/Module 1> | 5 | 5 | 5 | 15
<Functionality/Module 1> | 4 | 4 | 4 | 12
<Functionality/Module 1> | 6 | 6 | 6 | 18
<Functionality/Module 1> | 7 | 7 | 7 | 21
<Functionality/Module 1> | 8 | 8 | 8 | 24
<Functionality/Module 1> | 2 | 2 | 2 | 6
<Functionality/Module 1> | 4 | 4 | 4 | 12
0
0
0
0
0
0
0
Total | 36 | 36 | 36 | 108
Estimate for Total Test Case Points ( Note: The Adjustment Factor in the table below is pre-determined and must not be changed for every project.)
Test Case Type | Complexity Weight | Adjustment Weight | Number | Result
Simple | 1 | 2 | 36 | 72
Average | 2 | 4 | 36 | 144
Complex | 3 | 8 | 36 | 288
Total Test Case Points |  |  |  | 504
Independent Adjustment Factors - OS and Browser Combinations
Factor Number | Description | Total No.
F11 - If more than 1 OS combination to test, specify number | Operating System Combinations | 1
F12 - If more than 1 Browser to test, specify number | Browser Combinations | 2
Multiplication Factor for Manual Execution |  | 2
Factors Affecting Test Case Generation
Factor Number | Description | Factor Weight | Complexity Weight | Result | Adjustment Factor
F1 | Domain Knowledge & Complexity | 1 | 1 | 1 | 0.033333
F2 | Software/Hardware Set Up | 0 | 0 | 0 | 0
F3 | Environment Set Up | 0 | 0 | 0 | 0
F4 | Build Management | 0 | 0 | 0 | 0
F5 | Configuration Management | 0 | 0 | 0 | 0
F6 | Preparation of Test Bed | 0 | 0 | 0 | 0
F7 | Stable Requirements | 3 | 3 | 9 | 0.3
F8 | Offshore/Onsite Coordination | 2 | 2 | 4 | 0.13333
F9 | Test Data Preparation | 2 | 2 | 4 | 0.13333
Factors Affecting Test Case Execution
Factor Number | Description | Factor Weight | Complexity Weight | Result | Adjustment Factor
F1 | Domain Knowledge & Complexity | 1 | 1 | 1 | 0.033333
F2 | Software/Hardware Set Up | 1 | 1 | 1 | 0.033333
F3 | Environment Set Up | 2 | 2 | 4 | 0.13333
F4 | Build Management | 2 | 2 | 4 | 0.13333
F5 | Configuration Management | 2 | 2 | 4 | 0.13333
F6 | Preparation of Test Bed | 2 | 2 | 4 | 0.13333
F7 | Stable Requirements | 3 | 3 | 9 | 0.3
F8 | Offshore/Onsite Coordination | 2 | 2 | 4 | 0.13333
F9 | Test Data Preparation | 0 | 0 | 0 | 0
ESTIMATE FOR MANUAL TEST CASE GENERATION
Factor - F1 | Adjustment factor |  | 0.033333
Factor - F2 | Adjustment factor |  | 0
Factor - F3 | Adjustment factor |  | 0
Factor - F4 | Adjustment factor |  | 0
Factor - F5 | Adjustment factor |  | 0
Factor - F6 | Adjustment factor |  | 0
Factor - F7 | Adjustment factor |  | 0.3
Factor - F8 | Adjustment factor |  | 0.13333
Factor - F9 | Adjustment factor |  | 0.13333
Total of Adjustment factor |  |  | 0.15
Total Test Case Points (TCP ) |  |  | 504
Adjustment Factor |  |  | 1.15
Person Hours Per TCP |  |  | 2
Total Person Hours: |  |  | 1159.2
ESTIMATE FOR MANUAL TEST CASE EXECUTION
Factor - F1 | Adjustment factor |  | 0.033333
Factor - F2 | Adjustment factor |  | 0.033333
Factor - F3 | Adjustment factor |  | 0.13333
Factor - F4 | Adjustment factor |  | 0.13333
Factor - F5 | Adjustment factor |  | 0.13333
Factor - F6 | Adjustment factor |  | 0.13333
Factor - F7 | Adjustment factor |  | 0.3
Factor - F8 | Adjustment factor |  | 0.13333
Factor - F9 | Adjustment factor |  | 0
Total of Adjustment factor |  |  | 0.12917
Total Test Case Points (TCP ) |  |  | 504
Adjustment Factor |  |  | 1.1292
Person Hours Per TCP |  |  | 2
Total Person Hours for one OS/ Browser Combination |  |  | 1138.2
Total Person Hours for all required OS/ Browser Combination: |  |  | 2276.4
| Productivity (Work hours/Day) | 8
| Person Hours | Person Days
Overall Effort for Manual Test Generation & Execution | 3435.6 | 429.45
2
4
5
7
8
8
3
6
1
Note on B12: Enter the requirements from the work sheet provided for rough calculation.
Note on B46: Add or replace as many factors that is applicable for Testing
Note on B58: Add or replace as many factors that is applicable for Testing