Planning Poker
An Essential Part of Agile Estimating and Planning Material for this presentation comes from Michael Cohn’s book Agile Estimating and Planning
By Kevin Best

---
Effort Over Accuracy Chart

---
Who participates in Planning Poker?
Product Owner
Developers
  - DBA
  - UX Design
  - Developer
  - Business Analyst
  - Tester
  - Middle Tier Developer
  - DB Developer

---
When to play Planning Poker?
Two times
  - Once before the beginning of a Project estimation of the first two iterations of user stories takes place.
    - Two or three meetings one to three hours each
  - Second, the team will have to estimate ongoingly as new user stories are identified during the iteration.
    - A meeting near the end of the iteration can be called to estimate the new user stories so they are ready for a future iteration.

---
How does Planning Poker work?
Planning Poker Cards with the numbers 0, ½, ?, 1, 2, 3, 5, 8, 13, 20, 40, and, 100.
Each participant gets a set of the cards
    - The set consists of cards 0, 1, 2, 3, 5, 8, 13, 20, 40 and 100
A moderator reads the description to the participating estimators.
The product owner answers any questions the estimators have about the User Story.
After questions are answered each estimator privately selects a card representing his or her estimate. Cards are turned over simultaneously showing so all participants can see each estimate.
[Speaker Notes: Moderator typically is the Product Owner or an Analyst, but it can be anyone on the Development Team for there is no specialized role associated with being the moderator. Everyone is asked to remain aware of the effort/accuracy curve. The goal in planning poker is not to derive the an estimate that will withstand all future scrutiny.]

---
Agile Planning Poker Flow
High Level Flow
Info
“Estimate”
Info
User Story
Read First User Story
Ask Questions
Ask High and Low
“Estimate”
Info
“Agree on estimate”
User Story Estimated
Ask Low

---
How does Planning Poker Work continued
If estimates differ, the high and low estimators explain their estimates. (goal here is to learn what each estimator is thinking about)
The Group can discuss the story and estimates for a few more minutes
The estimators re-estimates by selecting a card.
If the estimates don’t converge by the second round, continue the process. The process doesn’t usually take more than three rounds.
[Speaker Notes: It is important that the questioning doesn’t come across as an attack on the estimates. Cards are kept private until everyone has estimated, at which point all cards are turned over at the same time. If on the third round there is not a single estimate, but there are 5, 5, 5, 5, and 3 the moderator will ask the person with the 3 estimate if he/she is okay with a 5. The point is not absolute precision but reasonableness.]

---
Why Planning Poker Works
Brings together experts on the technology from a cross-functional team, best suited for estimating the stories making up the product.
Lively dialogue accompanies planning poker sessions, estimators are called upon by their peers to justify their estimates.
Averaging individuals estimates leads to better overall estimates.
Planning poker works because it is fun.
[Speaker Notes: After completing a thorough review of the literature on software estimation, Jorgensen (2004) concluded that “the people most competent in solving the task should estimate it.” Having peers justify their estimates improves accuracy of the estimate, especially on items with large amounts of uncertainty (Hagafors and Brehmer 1983). Being asked to justify has also shown to result in estimates that better compensate for missing information (Brenner et al. 1996). This is important on an agile project because the user stories being estimated are often intentionally vague. Third, studies have shown that averaging individual estimates leads to better results (Hoest and Wohlin 1998) as do group discussions of estimates (Jorgensen and Molokken 2002). Group discussion is the basis of planning poker, and those discussions lead to an averaging of sorts of the individual estimates.]