## Sheet1
SEPTEMBER 2025 Action Plan | Council's plan of Action | Councillor/Clerk | Meeting date
CEMETERY | Council decided to find another person to value the land | Jane/Dale | 2.9.25
in Langhorn's Lane. Clerk to find one
SAFER CROSSINGS | CC Chris Dawson informed the Council that all boxes are ticked, BUT | Jane | 5.8.25
Funding for the crossings are not avilable from the 25/26 budget.
TRAMWAY/Back Lane | Back lane is very much overgrown- Clerk to contact Highways |  | 5.8.25
MAGAZINE | The next magazine to be published end of September. another advertiser. | Clerk/Donna | 2.9.25
CIL Monies | 2022- £558.00, 2023- £288.14, 2024-£3687.95, 2025-£562.77 | 5956.86 | 5.8.25
| Expenditure in July Anglian Water= £495.60, Grass Cutting £85.69 | 581.29
| Total Amount of CIL left to spend. | 5375.57
PENN SLUICE | No more updates till after September | Jane | 3.6.25
COMMUNITY GDN | Donna is bidding £20,000.00 for funding for a Pergoda and a pathway | Donna, Sarah,Jane | 5.8.25
| the gate. Dead trees are to be replaced by the donor who gave trees | Andrea/Clerk/Dale
Anglian Water want to charge £5,000.00 to connect water to the
field from the main line- this to include Traffic Management. Other
grants are being applied for.
BUS SHELTERS | There is grant funding available for Bus Shelters. Cllr Jane Sutton | C C Chris /Jane | 5.8.25
proposed that a shelter outside Laxtons, Isle Road and the Methodist
Church, Isle road . The cost to Council would be approximately £1,800
each. On a proposal by Cllr Tara rust that Council go ahead with these
two and in September look to see how many school children are
requiring shelters, it was seconded by Cllr Donna Semmens. Motion
was passed with 7 voting yes and 2 abstaining. Cllr Jane Sutton to deal
with the paper work.