## Sheet1
December 3rd 2024 Action Plan | Council's plan of Action | Councillor/Clerk | Meeting date
CEMETERY | Chairman researchedloans from PWLB- too expensive to pay back | Jane/Dale | 5.11.24
Look at selling land?
RAILINGS | The owner of Pro -edge outlined the work they will carry out | Jane/David | 3.12.24
and answered questions. Unfortunately Mundo Mac didn't
attend. Council has a CIL bid of £106,000 for this project
Council felt a meeting with Mundo Mac should occur
before decision made. Jane and David to meet owner.
SAFER CROSSINGS | Apply for CIL money when the next bids can be made. | Jane | 3.12.24
Council agreed that selling allotment land could help towards
costs. Clerk and Chairman to research this.
TRAMWAY/Back Lane | No new issues at this time | David | 3.12.24
MAGAZINE | Increasing in advertisers, being distributed as well as left in | Clerk/Donna | 3.12.24
local shops. Feedback is good.
TRAVELLER SITES | Donna highlighted the issues that most sites are located | Donna | 3.12.24
in this area, for the whole of Norfolk's allocation.
Response awaited from the planning
VERGES/RIVERBANK | Jonathon Fenn MLC has said he would meet representatives | Dale/Jill/Tara | 5.11.24
from both parishes to discuss the issue of cutting the river
banks in both parishes.
CIL Monies | 2020- £861.86, 2021-£1243.09, 2022- £558.00, 2023- £288.14, 2024-£3687.95 | 6639.04 | 12.4.24
2020's CIL money has now been spent- £865.81
DEFIBRILATOR | Submitted application for the Defib. Coopers HGV company | Andrea/Clerk | 4.12.24
will do training.
PENN SLUICE | NCC are requesting that B.C get the area cleared to | Jane | 4.12.24
start preserving the sluice
COMMUNITY GDN | 20 fruit trees have been donated.More trees will be sought | Donna, Sarah,Jane | 5.11.24
| to be interdispersed. Cameras and Sims have been purchased | Andrea/Clerk
Developers have now withdrawn from helping with the
Roadway. Andrea to sort scaffold pole
The area is totally cleared now ready for the planting to begin
YOUTH CLUB