## Model
Implementation Readiness Assessment
Assigned
Category | Standard Weighting | Customer Weighting
Project Definition | 15% | 0%
Project Management Structure | 15% | 0%
Project Size | 10% | 0%
Project Technology | 10% | 0%
Sponsorship & Commitment | 20% | 0%
Staffing | 10% | 0%
System Complexity | 5% | 0%
Effect of Implementation on Users | 15% | 0%
| 100% | 0%
Points Assigned
Low Risk = 1
Medium Risk = 5
High Risk = 10
Project Definition |  | Weighting | 0%
|  | Check | Points | Net Score
Benefits of New System | The benefits of the new system are:
| -Well defined or quantified or of strategic importance | Low |  | 0
| -Defined in general, not quantified | Medium |  | 0
| -Not defined or unclear | High |  | 0
Business Knowledge of Project Team | Project team members who are highly knowledgeable about or experienced in the business areas:
| -All | Low |  | 0
| -Half | Medium |  | 0
| -None | High |  | 0
Complexity of Requirements | The requirements of the system are:
| -Straight forward and understandable | Low |  | 0
| -Somewhat known, but complex | Medium |  | 0
| -Very vague and complex | High |  | 0
Dependence on Other Projects | The number of other development efforts on which this system is dependent:
| -Zero | Low |  | 0
| -One | Medium |  | 0
| -Two or More | High |  | 0
Project Deliverables/Scope | The project deliverables are:
| -Well defined | Low |  | 0
| -Defined, but at a high level | Medium |  | 0
| -Vague | High |  | 0
User Knowledge | Personnel responsible for providing application knowledge on the project are:
| -Knowledgeable in both user and IS areas | Low |  | 0
| -Knowledgeable in user area only | Medium |  | 0
| -Lacking adequate knowledge in the user area | High |  | 0
Manageable Project Scope | The manageable scope of the project encompasses:
| -A single business area only | Low |  | 0
| -Between one and two business areas | Medium |  | 0
| -More than two business areas | High |  | 0
Project Management Structure |  | Weighting | 0%
|  | Check | Points | Net Score
Scope change management procedures | The change management procedures for this project are:
| -Well defined and accepted | Low |  | 0
| -Established but unclear | Medium |  | 0
| -Nonexistent | High |  | 0
Methodology Use | The methodology and other standards to be used on the project:
| -Use of a common, formal methodology | Low |  | 0
| -Use of informal practices and standards | Medium |  | 0
| -No methodology | High |  | 0
Methodology Experience | The experience of the organization with the methodology:
| -Full life cycle experience with methodology | Low |  | 0
| -Single phase or partial life cycle experience with methodology | Medium |  | 0
| -This is the first project to use the methodology | High |  | 0
Quality Management Procedures | The quality management procedures for the project are:
| -Well defined and accepted | Low |  | 0
| -Established but unclear | Medium |  | 0
| -Nonexistent | High |  | 0
Decision Making Authority | Authority of participants to make critical decisions in a timely manner:
| -Users have complete decision making authority | Low |  | 0
| -User participants have limited decision making authority | Medium |  | 0
| -User participants have no real decision making authority | High |  | 0
Project Steering Committee | There is a:
| -Cross functional steering committee that meets regularly | Low |  | 0
| -Sponsor & other mgmt team meet occassionally about project | Medium |  | 0
| -No steering committee exists, nor do regulary meetings take place | High |  | 0
Project Size |  | Weighting | 0%
|  | Check | Points | Net Score
Calendar Time | The estimated calendar time for project completion:
| -Four months or less | Low |  | 0
| -Five to 12 months | Medium |  | 0
| -Over 12 months | High |  | 0
Organizations to Coordinate | The number of user organizations involved with this project:
| -One | Low |  | 0
| -Two to four | Medium |  | 0
| -Over four | High |  | 0
Hours of Effort | The total estimated hours of effort for the project:
| -Five thousand or less | Low |  | 0
| -Five thousand to 20,000 | Medium |  | 0
| -Over 20,000 | High |  | 0
Project Team Size | The estimated project team size, at its peak:
| -Four our fewer members | Low |  | 0
| -Five to 7 members | Medium |  | 0
| -Over 7 members | High |  | 0
Number of Sites | The number of sites included in the implementation:
| -One | Low |  | 0
| -Two to three | Medium |  | 0
| -Over three | High |  | 0
Project Technology |  | Weighting | 0%
|  | Check | Points | Net Score
Availability of Development Technology | The development technology must be sufficient for each team member's needs:
| -Software & hardware is already available for team members | Low |  | 0
| -The software & hardware is not yet available | Medium |  | 0
| -Providing sufficient software & hardware is not planned for in | High |  | 0
detail
Skills with Development Technology | All team members have formal knowledge of the technology they will use, and there is sufficient practical experience:
| -All team members have practical experience of the technology | Low |  | 0
they will be using
| -There is experience in each technology, but some team | Medium |  | 0
member have no training
| -There are some technologies in which no team member has | High |  | 0
practical experience
New DBMS | The project will use a DMBS that is:
| -Well established in the organization | Low |  | 0
| -Established, but new for this application | Medium |  | 0
| -New DBMS for the IS organization | High |  | 0
New Language | The project requires:
| -No new language | Low |  | 0
| -Somewhat new language(s) | Medium |  | 0
| -New language(s), used for the first time | High |  | 0
New Tools and Techniques | The development tools & techniques used by project team will be:
| -Very familiar | Low |  | 0
| -Somewhat familiar | Medium |  | 0
| -Used for the first time | High |  | 0
Availability of hardware for | Availability of hardware for development and testing:
development and testing | -Guaranteed availability | Low |  | 0
| -Reasonable assurance of availability | Medium |  | 0
| -No assurance of availability | High |  | 0
New or Nonstandard hardware | The project requirements for new hardware or system software:
or system software | -None | Low |  | 0
| -Existing plus additional | Medium |  | 0
| -All new | High |  | 0
Sponsorship and Commitment |  | Weighting | 0%
|  | Check | Points | Net Score
Commitment of User Mgmt | The general attitude of management:
| -Understands value of and supports the project | Low |  | 0
| -Are somewhat reluctant | Medium |  | 0
| -Are very skeptical or resistant | High |  | 0
Project Ownership | The projected ROI benefits of the project:
| -Have been factored into the sponsors/executives job plans | Low |  | 0
| -Are generally understood and management is expected to deliver | Medium |  | 0
| -Are unclear and ownership of the results has not been assigned | High |  | 0
Commitment of User | The general attitude of management:
Organizations | -Understands value of and supports the project | Low |  | 0
| -Are somewhat reluctant | Medium |  | 0
| -Are very skeptical or resistant | High |  | 0
Project Sponsorship | The champion is:
| -Identified, enthusiastic, and has strong user influence | Low |  | 0
| -Identified, but passive | Medium |  | 0
| -Unknown | High |  | 0
Number of Sponsors | The project has:
| -One sponsor | Low |  | 0
| -Two sponsors | Medium |  | 0
| -More than two sponsors | High |  | 0
Project Scope is within | The project scope is:
Sponsor's Span of Control | -Completely within the sponsor's direct span of control | Low |  | 0
| -Partially outside the sponsor's direct span of control | Medium |  | 0
| -Outside the sponsor's direct span of control | High |  | 0
Staffing |  | Weighting | 0%
|  | Check | Points | Net Score
Experience as a Team | The experience of team members as a team:
| -All have worked together before | Low |  | 0
| -Some have worked together before | Medium |  | 0
| -Team members are strangers | High |  | 0
Full time Project Manager | The project manager manages this project:
| -On a full time basis | Low |  | 0
| -Full time, plus minor responsibilities elsewhere | Medium |  | 0
| -Plus one or more projects | High |  | 0
Full time Project Team | The project team:
| -Assigned to project full time | Low |  | 0
| -At least half the team is assigned full time | Medium |  | 0
| -Less than half the team is assigned full time | High |  | 0
Project Manager Experience | The project manager experience level:
| -Three or more prior projects of similar scope | Low |  | 0
| -One or two prior projects of similar scope | Medium |  | 0
| -No prior projects of similar scope | High |  | 0
Team Members | The people assigned to the project were selected primarily because:
| -They are considered top performers | Low |  | 0
| -They had an interest and some prior experience | Medium |  | 0
| -They were readily available to work on the project | High |  | 0
Time Allocation | Allocation of key project participants to the project:
| -All key participants are sufficiently allocated to the project | Low |  | 0
| -Key participants are partially allocated to the project | Medium |  | 0
| -Key participants are insufficiently allocated to the project | High |  | 0
Team Location | The physical location of the project team:
| -Team is located together | Low |  | 0
| -Most of the team is located together | Medium |  | 0
| -Team is located at several sites | High |  | 0
Team's Experience with Application | The number of times that team members have implemented this application system:
| -More than once | Low |  | 0
| -Only once | Medium |  | 0
| -No knowledge or experience with the system | High |  | 0
System Complexity |  | Weighting | 0%
|  | Check | Points | Net Score
Interfaces to existing systems | The number of existing systems to which interfaces are needed:
| -None | Low |  | 0
| -One to three | Medium |  | 0
| -More than three | High |  | 0
Data Complexity | The level of complexity of the data used by the new system (by the number of entities and the relationships between them):
| -Not complex | Low |  | 0
| -Moderately complex | Medium |  | 0
| -Very complex | High |  | 0
Data Quality | The quality of data for the conversion process:
| -Simple to convert or of good quality | Low |  | 0
| -Average complexity or of fair quality | Medium |  | 0
| -Very complex or of poor quality | High |  | 0
Requirements for System | The system availability (unplanned downtime) must be:
Availability | -Ninety Five % | Low |  | 0
| -Ninety Eight % | Medium |  | 0
| -Greater than 99% | High |  | 0
Technology Mix | Types of technologies the system requires (e.g. DBMS, networking, minis,):
| -Existing or simple architecture | Low |  | 0
| -Adding one new technology | Medium |  | 0
| -New or complex architecture | High |  | 0
Effect of Implementation on the User Organization |  | Weighting | 0%
|  | Check | Points | Net Score
Changes to Org. Structure | The changes to the organization structure are:
| -None or completed | Low |  | 0
| -Planned | Medium |  | 0
| -Not considered | High |  | 0
Effect on Computer Operations | The effect of the new system on computer ops of the org:
| -Little change | Low |  | 0
| -Moderate change | Medium |  | 0
| -Severe change | High |  | 0
Policy Changes | Policy changes required to support the new system:
| -None | Low |  | 0
| -Moderate changes | Medium |  | 0
| -Extensive changes | High |  | 0
Training | The key managers and users of the new system:
| -Have already been trained | Low |  | 0
| -Haven't been trained, but a formal training plan exists | Medium |  | 0
| -Haven't been trained, nor will they be trained formally | High |  | 0
Procedural Changes imposed by | Procedural changes required to support the new system:
the New System | -Little change | Low |  | 0
| -Moderate change | Medium |  | 0
| -Severe change | High |  | 0
Weighted Score |  |  |  | 0
Low Risk = 4.5 to 15
Medium Risk = 16 to 30
High Risk = 31 to 49