## Sheet1
TRI-HURST CONSTRUCTION, INC.
SUBCONTRACTOR'S APPLICATION FOR PAYMENT
377 West 300 South • Blanding, Utah 84511
e-mail: wendy@tri-hurstconstruction.com • phone: 435-485-0058
SUBCONTRACTOR | [5 empty] | PHONE |  | PROJECT
ADDRESS | [5 empty] | FAX |  | DATE
CITY | [7 empty] | FOR PERIOD FROM |  |  |  | TO
CORPORATION |  |  | □ | PARTNERSHIP | □ | PROPRIETORSHIP | □
ID #
1. | ORIGINAL CONTRACT AMOUNT………………………….. | [8 empty] | $
2. | APPROVED CHANGE ORDERS……………………………………………….. | [8 empty] | $
3. | REVISED CONTRACT AMOUNT (lines 1 + 2) | [8 empty] | $
4. | PREVIOUS WORK COMPLETE (INCLUDING STORED MATERIAL)……….. | [8 empty] | $
| 4A. | STORED MATERIAL (IF ANY) ……………………………….. | [6 empty] | $
| 4B. | PREVIOUS RETENTION WITHHELD (4 x 0.05)…………… | [6 empty] | $
5. | WORK COMPLETED THIS PERIOD (INCLUDING STORED MATERIAL)…… | [8 empty] | $
| 5A. | STORED MATERIAL (IF ANY) ……………………………….. | [6 empty] | $
| 5B. | CURRENT RETENTION WITHHELD (5 x 0.05)……………… | [6 empty] | $
6. | CURRENT PAYMENT DUE (5-5B)…………………………. | [8 empty] | $
PENDING CHANGE ORDERS
#____________ | [9 empty] | $
#____________ | [9 empty] | $
#____________ | [9 empty] | $
#____________ | [9 empty] | $
#____________ | [9 empty] | $
#____________ | [9 empty] | $
CERTIFICATE BY CONTRACTOR OR SUPPLIER:
I hereby certify that the work performed and the materials supplied to date as shown above represent the actual value of accomplishment under the terms of the Subcontract Agreement and all authorized changes thereto between the undersigned subcontractor and TRI-HURST CONSTRUCTION, INC., relating the above project.
I further certify that all payments, less any applicable retention, through the period covered by previous payments received from TRI-HURST CONSTRUCTION, INC., have been made in full to (1) all my subcontractors (& sub-subcontractors) and (2) for all materials and labor used in or in connection with the performance of this contract.
I further certify that I have complied with Federal, State and Local tax laws, including Social Security, Unemployment Compensation, Workman's Compensation and Withholding Tax Laws, insofar as applicable to this contract and the at payroll fringe benefits where applicable have been applied.
________________________________ ________________________________ | [10 empty] | ____________________
BY | [5 empty] | TITLE |  |  |  |  | DATE