## Dashboard
Portfolio Dashboard
Counts by category
Scale candidate | 0
Pilot (gated) | 0
Defer/Redesign | 0
Top 20% flagged | 0
Average final score | #DIV/0!
How to use
1) Score initiatives in Backlog_Scoring (blue cells).
2) Adjust weights/thresholds in Settings if needed.
3) Use Pilot_Decisions for Day14 / Week6 / Monthly evidence and decisions.

## Settings
Pilot-to-Profit Scoring Settings
Weights (must sum to 1.0) |  |  | Stage options | Decision options | Reason codes
Value weight (V) | 0.4 |  | Day 14 | Scale | Impact
Feasibility weight (F) | 0.3 |  | Week 6 | Fix | Adoption
Adoption weight (A) | 0.3 |  | Monthly | Kill | Complexity
Risk penalty factor | 5 |  |  |  | Risk
Scale candidate threshold | 80 |  |  |  | Owner
Pilot (gated) threshold | 65 |  |  |  | Data readiness
Top-20% cutoff (%) | 0.2 |  |  |  | Integration
Change load
Suggested gating defaults (edit as needed) |  |  |  |  | Unit economics
Day 14 – Required checklist items (count) | 4
Week 6 – Minimum adoption (%) | 30
Week 6 – Minimum KPI delta (%) | 5
Week 6 – Max incidents/week (if relevant) | 2
Enable risk gate (1=on, 0=off) | 1 | Set to 0 to remove gate; see Settings B18
Risk gate: min R_avg for Scale | 3 | If R_avg < this, cannot be 'Scale candidate'
Pilot decision board settings
Auto next review date (1=on, 0=off) | 1 | Set to 0 to disable auto next review
Day 14 offset (days) | 14
Week 6 offset (days) | 42
Monthly offset (months) | 1

## Criteria
Scoring Rubric (1–5) and Definitions
Use 1 (weak) to 5 (strong). For risk criteria, higher score = lower risk.
Dimension | Criterion | Definition | Score (1–5) guidance
Value (V) | V1 – P&L Impact | Size of expected revenue uplift / cost reduction / risk reduction | 1=small/local; 3=meaningful; 5=material enterprise impact
Value (V) | V2 – Time-to-Value | Likelihood of measurable value within 90 days | 1=unlikely; 3=possible; 5=high confidence within 90 days
Value (V) | V3 – Strategic Fit | Alignment with CEO priorities and initiatives | 1=nice-to-have; 3=aligned; 5=directly tied to top priorities
Feasibility (F) | F1 – Data Readiness | Access + quality + freshness + governance | 1=unknown/poor; 3=usable; 5=ready with governance
Feasibility (F) | F2 – Integration Complexity | Simplicity of required integrations (simpler = higher) | 1=heavy/core systems; 3=some; 5=low/no integration
Feasibility (F) | F3 – Delivery Capability | Team/partner capacity and execution readiness | 1=no bandwidth; 3=some capacity; 5=ready team + plan
Adoption (A) | A1 – Workflow Embed | Embedded in core workflow (not optional)? | 1=optional tool; 3=partially embedded; 5=default path
Adoption (A) | A2 – Change Load | Behavior change cost (lower = higher) | 1=major shift; 3=moderate; 5=minimal change
Adoption (A) | A3 – Incentives & Ownership | Clear Value Owner + aligned incentives | 1=unclear; 3=owner named; 5=owner + incentives aligned
Risk (R) | R1 – Data Sensitivity | Lower sensitivity/exposure = higher score | 1=highly sensitive; 3=moderate; 5=low sensitivity
Risk (R) | R2 – Regulatory/Compliance | Lower exposure = higher score | 1=high exposure; 3=some; 5=low exposure
Risk (R) | R3 – Brand/Harm Risk | Lower harm risk = higher score | 1=high harm; 3=manageable; 5=low harm

## Backlog_Scoring
Portfolio Intake & Scoring (Pick the 20% that can scale)
Last updated: 2026-02-01
Idea ID | Initiative | Business Area | Workflow (where it lives) | Business Value Owner | V1 | V2 | V3 | V_avg | F1 | F2 | F3 | F_avg | A1 | A2 | A3 | A_avg | R1 | R2 | R3 | R_avg | Score_base (0–100) | Risk_penalty | Final Score (0–100) | Category | Rank | Top 20%? | Primary KPI | Baseline | Baseline Source

## Pilot_Decisions
Scale / Fix / Kill Decision Board (Evidence-based)
Log one row per pilot per review date. Pick an Idea ID in column A; auto fields populate. Fill evidence + decision columns manually. | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20
Pilot ID | Pilot Name (auto) | Review Date | Stage (Day14/Week6/Monthly) | Primary KPI (auto) | Baseline (auto) | Current |  | Adoption % (active/target) | Incidents/week | Repeatability (1–5) | Benefit ($/period) | Cost ($/period) |  | Business Value Owner (auto) | Category (auto) | Final Score (auto) | R_avg (auto) | Owner | Deadline | Next review (auto) | Decision (Scale/Fix/Kill) | Reason code 1 | Reason code 2 | Fix actions (if Fix) | Decision notes