| Project Information |  |
| --- | --- |
| Project Title | Redirecting with Purpose: APAT Model |
| Project Purpose | To train residential staff in the use of the APAT redirection model to reduce incidence of confrontation between RAs and resident trainees due to forceful redirection methods. |

| Roles & Responsibilities |  |
| --- | --- |
| Role | Marek Sidykh Instructional Designer |
| Role |  |
| Role |  |

| Audience, Goals & Objectives |  |
| --- | --- |
| Target Audience | All residential staff working directly with trainees in the dormitories. |
| Project Goal | Terminal Objective for the Curriculum: Reduce amount of trainee resignations due to dorm-based conflict and negative staff experiences. Reduce amount of RA resignations due to dorm-based conflict with trainees and related negative experiences. |
| Learning Objectives | After completing this training, learners will be able to… Residential staff will be able to approach, address, and redirect trainees when necessary, in non-confrontational and respectful manner by using clear communication and de-escalation strategies using the APAT redirection model. |

| Project Deliverables |  |
| --- | --- |
| Deliverable | APAT Training module action map |
| Deliverable | APAT Training module storyboard/draft document |
| Deliverable | Final APAT Training module |

| Project Milestones |  |
| --- | --- |
| Date | APAT Training module action map Week 1 |
| Date | APAT Training module storyboard/draft document Week 2 |
| Date | APAT Training module first draft Week 3 |
| Date | APAT Training module revision meeting Week 3 |
| Date | APAT Training module final draft Week 4 |
| Date | Module implementation Week 5 |

| Implementation & Measurement |  |
| --- | --- |
| Implementation Plan | Residential staff will receive training via company LMS & ILT, notifications disseminated via email and department meetings |
| Evaluation Plan | Level One: Learner Reaction - Pre- and post-training reaction surveys Level Two: Learner Knowledge - Post-training assessment (part of training module) Level Three: Learner Behavior - 30, 60, 90 day dorm culture observation and audit of case notes, resignations Level Four: Business Results - Audit of 30, 60, 90 day resignations of RAs and trainees |
| Constraints & Risks | - Trainee access to LMS may be limited – trainees may not have devices to access the LMS or may not know how to navigate the LMS to find the training - Scheduling recurring ILT for RAs and trainees may pose a logistical challenge |