| Project Information |  |
| --- | --- |
| Project Title | Understanding and Using Nutrition Labels |
| Project Purpose | The purpose of the project is to design a short training module for PlateSmart Initiative customers on how to read a nutrition label and use the nutritional information on the label to make healthier food choices based on specific dietary guidelines. |

| Roles & Responsibilities |  |
| --- | --- |
| Role | Marek Sidykh, instructional designer |

| Audience, Goals & Objectives |  |
| --- | --- |
| Target Audience | New customers of the PlateSmart Initiative health app will receive the training as part of onboarding with the app in order to prepare them to use the app’s more advanced features. |
| Project Goal | To empower PlateSmart Initiative customers to make meaningful and informed food choices by accurately reading and understanding nutrition labels for different foods. |
| Learning Objectives | PlateSmart Initiative customers will be able to: - Identify the parts of a nutrition label - Compare foods using nutrition label information to see which ones better fit dietary requirements Combine information from different foods’ nutrition labels to plan a healthy meal option. |

| Project Deliverables |  |
| --- | --- |
| Deliverable | Action Map for eLearning module |
| Deliverable | Storyboard for eLearning module |
| Deliverable | Draft 1 of eLearning module |
| Deliverable | Final draft of eLearning module |

| Project Milestones |  |
| --- | --- |
| Monday, March 30 | Module action map & Review |
| Wednesday, April 1 | Storyboard for module & review of storyboard |
| Friday, April 3 | Draft 1 of learning module & review |
| Tuesday, April 7 | Final draft of eLearning module |

| Implementation & Measurement |  |
| --- | --- |
| Implementation Plan | Training will be delivered via mobile app for new users/clients of PlateSmart Initiative’s health guidance application. |
| Evaluation Plan | Level One: Learner Reaction A post-task user survey will evaluate users’ reaction to the learning module and collect feedback about its relevance, accessibility, and perceived effectiveness. Level Two: Learner Knowledge An assessment at the end of the module will test learners’ uptake of the basic concepts introduced in the learning module. Level Three: Learner Behavior Intermittent surveys of clients’ use habits with the PlateSmart Initiative app will be used to gauge uptake and efficacy of the nutrition label training. Level Four: Business Results Progress and retention of customers through the app will be evaluated, and intermittent surveys will assess users’ satisfaction with app features, including whether they feel prepared to use nutrition labels as part of their PlateSmart application experience. |
| Constraints & Risks | What constraints or risks may prevent the completion of the project? Stakeholders may terminate project prior to completion to prioritize other customer training goals. |