## Backlog (Product Owner)
Epic | User Story Title | User Story | Estimate | User Story State | Priority | (Calculated Value) Sprint Date
ScienceJournalShopping System Login | Login Page | As an internal user, I would like to log in to the ScienceJournalShopping System So that I can access my records |  | Ready | 1 | 2018-01-01
ScienceJournalShopping System Login | Log out Page | As an internal user who is logged in I would like to be able to log out of the ScienceJournalShopping System and end my session So that I can ensure that my data is no longer accessible after the log out. |  | Ready | 1.5 | 2018-01-01
ScienceJournalShopping System Shared tools | Invoice generation | As an ScienceJournalShopping System, I would like to have the ability to dynamically generate an invoice based on the customer, Title, description, quanitity, Quantity per price, tax, and total, So that I can have any invoice be created for any existing or future products |  | Analysis | 2 | 2018-01-01
ScienceJournalShopping System Customer data | Create/edit customer | As in internal user who is logged in and is admin I would like to create a customer record which contains first name, last name, address, city, country, postal code, phone number, and email, and status So that I holds my customer data and associat it to my records |  | Pending | 3 | 2018-01-01
ScienceJournalShopping System Record | Create/edit record | As in internal user who is logged in, I would like to create a record which contains my customer, product number, and quantity So that I can create an order |  | Pending | 4 | 2018-01-05
ScienceJournalShopping System Record | Generate record invoice | As an internal user who is logged in on a record, I would like to create an order on a record So that it can generate my invoice to send to the client |  | Pending | 5 | 2018-01-05
ScienceJournalShopping System Record | Item 1 | Item 1 user story |  | Pending | 6 | 2018-01-09
ScienceJournalShopping System Record | Item 2 | item 2 user story |  | Pending | 7 | 2018-01-09
ScienceJournalShopping System Record | Item 3 | item 3 user story |  | Pending | 8 | 2018-01-09
This area is designated for the Product Owner and respective analyst. The aim by the product owner is to enter the user stories, epics, and priority.
After every sprint, the product owner and scrum master will go through a grooming exercise to organize the backlog list. This list represents the entire system and is always changing based on status

## Lookup Data (Scrum Master)
Sprints | 2018-01-01 | State | Pending | User Story State | Pending | Team Sprint Capacity | 43 | Days in Sprint | 14
| 2018-01-15 |  | Design |  | Analysis
| 2018-01-29 |  | Development |  | Ready
| 2018-02-12 |  | Testing
| 2018-02-26 |  | Ready for live
| 2018-03-12 |  | Blocked
2018-03-26
2018-04-09
2018-04-23
2018-05-07
2018-05-21
2018-06-04
2018-06-18
2018-07-02
2018-07-16
2018-07-30
2018-08-13
2018-08-27
This area is designated for Scrum Master. The capacity, status, and sprint dates are stored here.
Data here is always being adjusted based on actual events.
These must be concrete items agreed on by owners and dev team.