## Sprint (Scrum Team)
Estimation
User Story Title2 | Sprint | Task | Priority | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Summation (To be Hiddn) | Total Point | Estimation OK?
Login Page | 2018-01-01 | Testing | 1 | 16 | 14 | 10 | 8 | 7 | 8 | 10 | 6 | 5 | 3 | 1 | 1 | x | x | 16
Log out Page | 2018-01-01 | Ready for live | 2.5 | 5 | 5 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | x | x | 21
Create/edit customer | 2018-01-01 | Testing | 4 | 13 | 10 | 8 | 7 | 8 | 5 | 5 | 3 | 2 | 2 | 2 | 1 | x | x | 34
Invoice generation | 2018-01-01 | Development | 1.5 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 5 | 4.5 | 3 | x | x | 43 | 43 | At Capacity
Create/edit record | 2018-01-15 | Testing | 2 | 10 | x | x | x | x | x | x | x | x | x | x | x | x | x | 10
Generate record invoice | 2018-01-15 | Pending | 2.1 | 4 | x | x | x | x | x | x | x | x | x | x | x | x | x | 14
Item 1 | 2018-01-15 | Pending | 5 | 11 | x | x | x | x | x | x | x | x | x | x | x | x | x | 25
Item 2 | 2018-01-15 | Pending | 5.5 | 9 | x | x | x | x | x | x | x | x | x | x | x | x | x | 34
Item 3 | 2018-01-15 | Pending | 5.55 | 14 | x | x | x | x | x | x | x | x | x | x | x | x | x | 48 | 48 | Over Capacity
This area is designated for the development team. At the start of every sprint, the team with the product owner define what can be taken on or otherwise.
For each item in a sprint, the user story must be defined
For each item in a sprint, the estimate will be reviewed and set

## Lookup Data (Scrum Master)
Sprints | 2018-01-01 | State | Pending | User Story State | Pending | Team Sprint Capacity | 43 | Days in Sprint | 14
| 2018-01-15 |  | Design |  | Analysis
| 2018-01-29 |  | Development |  | Ready
| 2018-02-12 |  | Testing
| 2018-02-26 |  | Ready for live
| 2018-03-12 |  | Blocked
2018-03-26
2018-04-09
2018-04-23
2018-05-07
2018-05-21
2018-06-04
2018-06-18
2018-07-02
2018-07-16
2018-07-30
2018-08-13
2018-08-27
This area is designated for Scrum Master. The capacity, status, and sprint dates are stored here.
Data here is always being adjusted based on actual events.
These must be concrete items agreed on by owners and dev team.