## Lab Scale Tests
Lab Scale Tests
Task |  | Results | Explanation | Soruce | Links
Grow on Rice Substrate (to prove if cellulase can be grown and the entire assay (without extracting cellulase) added to biomass to produce suger)
EP1 | Purchase Trichoderma (R,V,H) | Bought $20.00 bag from https://www.kelp4less.com/shop/trichoderma-inoculant-powder/ | Order the initial Trichoderma fungi/powder to start from | Rootshield Plus Trichoderma Inoculant | https://www.bioworksinc.com/rootshield-plus-wp/ https://www.kelp4less.com/shop/trichoderma-inoculant-powder/
EP2 | Cook Rice | 1/28/20 - cooked 1 cup rice, 2 cups water for 25 minutes. Brought to boil then turn flame down • When done, rice was wet and sticky | Put your water and rice in the rice cooker. Turn it on. If using a pot and lid, bring the rice and water to a boil then lower to a simmer and put the lid on it. Cook until the moisture is gone (about 25 minutes).
EP3 | Bag and cool rice | 1/28/20 • Put 2 - 2.5 teaspoons of cooked rice in 5 smann sqaure snack bags, packed rick on bottom, rolled bag to get air out and zipped bag shut • Put 3 - 3.5 teaspoons of cooked rice in 3 quart bags, packed rick on bottom, rolled bag to get air out and zipped bag shut | Put a couple spoonfuls of the cooked rice into a new and clean ziploc baggie. Squeeze all the air out, packing down the rice and then seal the bag and wrap it to keep any spores or air from getting in. Let the rice cool until you can handle it comfortably.
EP4 | Add Trichoderma Fungi | 1/28/20 - Once bags cooled to touch and were warm: • added 1/2 to 3/4 teaspoon of trichoderma to the 5 small snack bag, bunched top of bag and held closed with rubber band (not super tight, but no gap into bag was visible), shook each bag (30 secods or less), and packed rice at bottom. • added 3/4 teaspoon of trichoderma to the 3 quart bags, bunched top of bag and held closed with rubber band (not super tight, but no gap into bag was visible), shook each bag (30 secods or less), and packed rice at bottom. | Once the rice is cool, open the bag and add a 1/2 teaspoon of Trichoderma powder to the rice. close the bag again. Don’t squeeze the air out this time. Seal it with a rubber band at the top, not the ziploc part. Let the bag naturally fill with air. Shake the bag and spread around the fungi on all the rice. Create two sections to the bag. Pack the rice tightly again at the bottom, leaving the air at the top of the bag.
EP5 | Poke holes in the bag | 1/28/20 - Poked 10 - 15 holes in each bag with insulin needle | Take your needle and poke about 10 holes in the air-filled part of the bag.
EP6 | Use up all rice |  | Do this repeatedly with as many bags until all the rice is gone
EP7 | Store the bags | 1/28/20 - Set bags on stand in front of a western facing window | Place the bags in a clean area that is room temperature that is not too dark
EP8 | Mix the substrate | 1/31/20 - never shook bags again. White fuzz/material seen growing | Shake the bags again in two days, pack the rice down again and let sit for another 7 days.
EP9 | Confirm trichoderma growth and cellulase production | 2/17/20 - majority of visible material in each bag is dark green/black, has some brown and more recently white dry material 2/2/20 - fungi growth observed - 25-50% of surface is green in most bags and some brown (less than 5%) brown in some bags. Significant green on bottoms of bags. Bags closer to window have slightly higher percentage of green growth | The fungi is ready to use. It will remain usable for 3-4 weeks. The Trichoderma could be anywhere from dark green to light yellow to white. If it is healthy, it should smell vaguely like coconut sunscreen.
Test converting grass to sugar with some samples of trichoderma/rice mixes
Dry Run (to prove if grown cellulase can convert bimass to sugar in a silo)
a | Cut switchgrass with tin snips | Grass prepared on 2/22/2020
b | Ran thru food processor, 30 seconds each
c | Ran thru Hanshu meat grinder 1 time each
d | Added 1.5 cups dustified SG to blender
e | Initial sugars from Wet run were 21 to 27
f | Added 2 bags of rice/trico to blender
g | Blend | Dry matter would not swirl at all. Rice/tricho mix was moist and stuck together
h | Chop SG/rice/Trichderm mix in food processor | Ran in groups thru food process to get mixed
i | Add water | Inteneed to add some warm water, however rice/trich mix had enough moisture to make the resulting mix look like silage
j | Ensiled in cleand out grated cheese container | Added mixes from food processor and packed in. This was done on 2/23/2020
2/24/20 3:25pm | Filled red solo cup 1/4 full of grass, rest with warm tap water, stirred manually for 30 seconds | Sugar read LO and LO | Was there any enzyme in the top portion of the biomass??
3:40pm |  | Sugar read LO | Was there any enzyme in the top portion of the biomass??
7:35pm |  | Stirred manually for 30 seconds. Sugar read 24 and 24 | Was there any enzyme in the top portion of the biomass??
5:45am 2/25/20 |  | Stirred manually for 30 seconds. Sugar read LO
2/26/20 - 4/21/20 | Let mixture sit in red solo cup | Molded up early on (white color)
2020-04-21 | Liquid all gone | Not sure if evaporated or cup got a hole in it. No signs of liquid on rug under where it's been sitting. Solid grass in bottom is dry and there's white cheese like chunks in the cup. These are white. Not sure if mold or enzyme or something else. Top of cup was never sealed - just covered with a metal pulley - air could always get to it
Wet Run #1 (to prove if grown cellulase can convert bimass to sugar in a hydrolysis environment)
a | Cut switchgrass with tin snips | Grass prepared on 2/22/2020
b | Ran thru food processor, 30 seconds each
c | Ran thru Hanshu meat grinder 1 time each
d | Chop rice/Trichderm mix in food processor | cut top off bag and dumped 2 bags in | In dry run, rice/tricho mix was moist and stuck together
e | Bring 2 cups tap water to 120 Farenheit | Tap water was 119.8
f | Add water to blender
g | Add 1.5 cups dustified SG to blender
h | Agitate and measure sugar | Mix was too thick for meter - had to pour liquid into cup Sugars read 27 and 25
i | Add more water to blender | Added 1 red solo up (holds 2 cups) of tap water | Tried to make more of a liquid mix so as to test for sugar easier
j | Agitate and measure sugar | Sugars read 21 and 21
k | Measure PH (target is 5.0) | Measured at 6.6. Left as is and moved on
l | Add bag of rice/tricho/cellulase
m | Added rice/tricho mix to blender and mixed at 7:45am ET on 2/24/20 | Had to scoop rice/tricho mix out of food processor. Scooped into blender and then mixed for 30 seconds
10:10am | blend quick and measure sugar | Sugars read 285 and 293. Poured liquied in cup, measured, returned liquid and mixed for 5 seconds
11:10am | blend quick and measure sugar | Sugars read 382 and 425. Poured liquied in cup, measured, returned liquid and mixed for 5 seconds
1:10pm | blend quick and measure sugar | Sugars read 405 and 416. Poured liquied in cup, measured, returned liquid and mixed for 5 seconds Sugars read 454 and 424. Poured liquied in cup, measured, returned liquid and mixed for 5 seconds
3:18pm | blend quick and measure sugar | Mixed for 5 seconds, poured liquid into cup. Sugars read 477 and 505
5:24pm | blend quick and measure sugar | Mixed for 5 seconds, poured liquid into cup. Sugars read 502 and 493
7:30pm | blend quick and measure sugar | Mixed for 5 seconds, poured liquid into cup. Sugars read 514 and 510
5:45am 2/25/20 | blend quick and measure sugar | Mixed for 5 seconds, poured liquid into cup. Sugars read 535 and 535
7:25pm | blend quick and measure sugar | Mixed for 5 seconds, poured liquid into cup. Sugars read 282 and 284
7:16pm 2/26/20 | blend quick and measure sugar | Mixed for 5 seconds, poured liquid into cup. Sugars read 74 and 70 Left in blender pitcher
2/26/20 - 4/21/20 | Let mixture sit in blender pitcher | Molded up early on (white color) Solids settled to bottom Molded dissappeared after time
2020-04-21 | blend quick and measure sugar | Mixed for 5 seconds, poured liquid into cup. Sugars read Lo twice
2020-04-21 | Strained to keep solids with round kitched metal strainer
Wet Run #2 (to prove if grown cellulase can convert bimass to sugar in a hydrolysis environment and the resulting sugar converted to alcohol) • This would prove the entire process, start to finish, can be done at home/on the farm. • Efficiency is not a goal here - just need to proved it can be done. If we need to grow excess cellulase to make up for lack of efficiency, and can grow it cheaper than commercial producere make it, we would be ahead.
A | Cut switchgrass with tin snips | Grass prepared on 2/22/2020
B | Run thru food processor, 30 seconds each
C | Run thru Hanshu meat grinder 1 time each
D | Bring 4 cups tap water to 120 Farenheit
E | Add water to blender
F | Add 1.5 cups dustified SG to blender
G | Agitate and measure sugar
H | Measure PH (target is 5.0)
I | Add 2 bags of rice/tricho/cellulase |  | Hopefully, it hasn't become inactive
hour 1 | blend quick (5 seconds) and measure sugar
hour 2 | blend quick (5 seconds) and measure sugar
hour 4 | blend quick (5 seconds) and measure sugar
hour 6 | blend quick (5 seconds) and measure sugar
hour 8 | blend quick (5 seconds) and measure sugar
hour 10 | blend quick (5 seconds) and measure sugar
hour 12 | blend quick (5 seconds) and measure sugar
hour 24 | blend quick (5 seconds) and measure sugar
hour 25 | Heat up or strain liquid off to stop enzyme activity | Heat up on turkey fryer or laboratory heat pad
J | Ferment | • Pour liquid into a bucket w/a fermentation trap (use trap from home brew kits) • Wash remaining solids and pour those liquids into fermentation bucket • Squeeze solids out using Electric meat gringer and/or Hanschau meat grinder • Add packet of yeast
K | Dry solids | Bakes solids in the sun Use dehydrator if necessary
L | Distill
Grow on Switchgrass Substrate
EP10 | Chop | Cut down by hand and freeze?
EP11 | Hammer | Use Small Hammer Mill
EP12 | Process 1 | Food Processor
EP13 | Process 2 | Meat grinder with tri blade on end
EP14 | Spread Trichoderma on substrate | Fish Tank Incubator?
EP15 | Control Temperature | • Electric element is easiest to control - will it dry things out though? • Hot water circulation to add heat • Air conditioner to remove heat | Although all the species of Trichoderma produced sufficient biomass at different temperatures viz. 20°C, 25°C, 30°C and 35°C but they were found to be best grown at a temperature range of 25°C to 30°C (77F to 86F)Aeration by agitation was also checked at different speeds such as 100, 150, 200 and 250 rpm but greatest biomass was recorded at 150 rpm.
EP16 | Control PH | Spray of a PH plus or minus? | • The most favorable pH ranges between 5.5 and 7.5 in which total dry weight of mycelium varies between 1.41 and 1.35 g. • Check once/day and spray as needed?
EP17 | Control Moisture | • Pump humidifier output into incubator as needed? • Duct the tank to the front of a dehumidifier if too humid? • Need a moisture level meter either way | • They make a house more humid. • They remove humitidy from a house.
EP18 | Extract Enzyme | • Vaccum celluase off top? • Mix everything with biomass in silo? • Filter/sift/scrape off cellulase? | • If enzmes grow on top, could we control a vaccum enough to just suck off the enzymes • Even if less efficient, would it be simpler & cheaper to mix it all in with the biomass in the blower and keep some to start the next batch? To make up for the lack of efficiency, grow more trichoderma to increase the enzyme loading ratio.
EP19 | Measure Amount Produced
EP20 | Freeze enzyme?
Start next growth cycles
EP21 | Save 10% of fungi from initial rice substrate
EP22 | Repeat steps E10 thru E20
Grow on Tobacco Substrate
EP23 | Chop | Cut down by hand
EP24 | Split | Cut stalks in half
EP25 | Spread Trichoderma on substrate | Fish Tank Incubator?
EP26 | Control Temperature | • Electric element is easiest to control - will it dry things out though? • Hot water circulation to add heat • Air conditioner to remove heat | Although all the species of Trichoderma produced sufficient biomass at different temperatures viz. 20°C, 25°C, 30°C and 35°C but they were found to be best grown at a temperature range of 25°C to 30°C (77F to 86F)Aeration by agitation was also checked at different speeds such as 100, 150, 200 and 250 rpm but greatest biomass was recorded at 150 rpm.
EP27 | Control PH | Spray of a PH plus or minus? | • The most favorable pH ranges between 5.5 and 7.5 in which total dry weight of mycelium varies between 1.41 and 1.35 g. • Check once/day and spray as needed?
EP28 | Control Moisture | • Pump humidifier output into incubator as needed? • Duct the tank to the front of a dehumidifier if too humid? • Need a moisture level meter either way | • They make a house more humid. • They remove humitidy from a house.
EP29 | Extract Enzyme | • Vaccum celluase off top? • Mix everything with biomass in silo? • Filter/sift/scrape off cellulase? | • If enzmes grow on top, could we control a vaccum enough to just suck off the enzymes • Even if less efficient, would it be simpler & cheaper to mix it all in with the biomass in the blower and keep some to start the next batch? To make up for the lack of efficiency, grow more trichoderma to increase the enzyme loading ratio.
EP30 | Measure Amount Produced
EP31 | Freeze enzyme?
Start next growth cycles
EP32 | Save 10% of fungi from initial rice substrate
EP33 | Repeat steps E28 thru E36
Taget endocellulase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces endocellulase well
Taget exocellulase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces exocellulase well
Taget B-Glucosidase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces B-Glucosidase well
Taget Xylanase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma harzianum has been used to produce enzymes to target Xylanase
Taget Glucoamalyse (for starch hydrolization) |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Viride can produce good enzymes for this
Enzymes that attack Cellulose are endocellulases, exocellulases, and B-Glucosidases Enzymes that attack hemicellulose come are glucoronide, acetylesterases, xylanase, B-xylosidase, galactomannase, and glucomannase
Pretreat Biomass
P1 | Chop | Cut down by hand and freeze? | Tin Snips
P2 | Hammer | Use Small Hammer Mill | On the farm
P3 | Process 1 | Food Processor - run for 30 seconds per loading in the food processor | In the shop
P4 | Process 2 | Meat grinder with tri blade on end - may want to try a few times through | Runnings?
Ensile Biomass with Enzymes
EN1 | Measure sugar of Switchgrass | Mix in blender with distilled water • 2 cups switchgrass • 2 cups water?
EN2 | Mix Switchgrass and fungi/enzyme mix from step EP9 in a coffee can | • Try a 4:1 ration of Switchgrass to enzyme/fungi mix • Mix with kitchen blender
Wash Sugar off of Silage
EN3 | Measure sugar of Switchgrass | 20 Days in - Mix in blender with distilled water • 2 cups switchgrass • 2 cups water? | Blender
Ferment
Distill
Dry leftovers and Densify

## Small Silo On-Farm Test
Small Silo On-Farm Tests
Task |  | How to execute | Source / tool | Explanations
Grow Enzymes on Substrates identified in Lab tests
EP1 | Purchase Trichoderma (R,V,H) | Order the initial Trichoderma fungi/powder to start from
EP2 | Chop | Cut down by hand
EP3 | Hammer | User Small Hammer Mill
EP4 | Process 1 | Food Processor
EP5 | Process 2 | Meat grinder with tri blade on end
EP6 | Spread Trichoderma on substrate | Fish tank for an incubator (SSF)
EP7 | Control Temperature | • Electric element is easiest to control - will it dry things out though? • Hot water circulation to add heat • Air conditioner to remove heat |  | Although all the species of Trichoderma produced sufficient biomass at different temperatures viz. 20°C, 25°C, 30°C and 35°C but they were found to be best grown at a temperature range of 25°C to 30°C (77F to 86F)Aeration by agitation was also checked at different speeds such as 100, 150, 200 and 250 rpm but greatest biomass was recorded at 150 rpm.
EP8 | Control PH | Spray of a PH plus or minus? |  | • The most favorable pH ranges between 5.5 and 7.5 in which total dry weight of mycelium varies between 1.41 and 1.35 g. • Check once/day and spray as needed?
EP9 | Control Moisture | • Pump humidifier output into incubator as needed? • Duct the tank to the front of a dehumidifier if too humid? • Need a moisture level meter either way |  | • They make a house more humid. • They remove humitidy from a house.
EP10 | Extract Enzyme | • Vaccum celluase off top? • Mix everything with biomass in silo? • Filter/sift/scrape off cellulase? • Centrifuge to extract cellulase? |  | • If enzmes grow on top, could we control a vaccum enough to just suck off the enzymes • Even if less efficient, would it be simpler & cheaper to mix it all in with the biomass in the blower and keep some to start the next batch? To make up for the lack of efficiency, grow more trichoderma to increase the enzyme loading ratio.
EP11 | Measure Amount Produced
EP12 | Freeze enzyme?
Start next growth cycles
EP13 | Save 10% of fungi from initial substrate
EP14 | Repeat steps E2 thru E12
Taget endocellulase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces endocellulase well
Taget exocellulase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces exocellulase well
Taget B-Glucosidase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces B-Glucosidase well
Taget Xylanase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma harzianum has been used to produce enzymes to target Xylanase
Taget Glucoamalyse (for starch hydrolization) |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Viride can produce good enzymes for this
Enzymes that attack Cellulose are endocellulases, exocellulases, and B-Glucosidases Enzymes that attack hemicellulose come are glucoronide, acetylesterases, xylanase, B-xylosidase, galactomannase, and glucomannase
Pretreat Biomass
P1 | Chop | Cut down by hand | Tin Snips
P2 | Hammer | User Small Hammer Mill - buy the smallest screen possible. Speed up hammer mill? Gather dust and use only that? | On the farm
P3 | Process 1 | a) Custom built meat grinder like machine? b) Auger feed down slightly tapered tunner, with chain saw disks at end? c) Hot water treatment? | Custom built machine | Meat grinder - push chopped biomass thru an opening, where outside of it is a rotating fan knife or disk or drum with cutting edges. Theory is if knives are spinning fast enough and feed is proceeding slow enough, we can cut the feedstock at very short lengths. Auger feed - use the BM (no heat on) to force the biomass into a log like item. As the log exits, have several chain saw disk spinning very fast to produce a saw dust like and sized material.
Ensile Biomass with Enzymes
EN1 | Measure sugar of Switchgrass | Mix in blender with distilled water • 2 cups switchgrass • 2 cups water?
EN2 | Mix Switchgrass and fungi/enzyme mix from step EP10 | Pre-mix in cement mixer then blow in with blower *** ensiling serves as dilute acid hydrolysis too
Wash Sugar off of Silage
EN3 | Measure sugar of Switchgrass | 20 Days in - Mix in 55 gallon hydrolyder • SG and water ratios TBD • Length of mixing time TBD (all afternoon perhaps. Check sugar ever 1/2 hour)
Ferment
F1 | Extract liquid | Siphon liquid into another 55 gallon drum | 55 gallon hydrolyzer
F2 | Add yeast | xx Pounds of yeast | TBD
F3 | Add lid and CO2 trap | Seal lid on and put water in CO2 trap
F4 | Ferment | 1 week
Distill
D1 |  |  | Pot distiller
| Cooling water |  | New Swimming Pool
Dry leftovers and Densify

## On-farm Production
On-Farm Production
Task |  | How to execute | Source / tool | Explanations | Power Source
Grow Enzymes on Substrates identified in Lab and Small Silo Tests tests
EP1 | Purchase Trichoderma (R,V,H) | Order the initial Trichoderma fungi/powder to start from |  | Reuse some of prevoius runs fungi, for the amount of times it remains viable. Purchase new to start from incrementally as dictated by viability & reusability of prevoius trichoderma
EP2 | Chop | Cut as short as possible - slow feedrolls and groundspeed | Allis Chalmers 50 |  | ethanol powered
EP3 | Hammer | Use small screen | PTO hammer mill |  | solar or wind powered / ethanol powered
EP4 | Process 1 | a) Custom built meat grinder like machine b) Auger feed down slightly tapered tunner, with chain saw disks at end c) Hot water treatment d) Scaled up Wiley Mill e) Flash freeze and then mill? | Custom built machine | Meat grinder - push chopped biomass thru an opening, where outside of it is a rotating fan knife or disk or drum with cutting edges. Theory is if knives are spinning fast enough and feed is proceeding slow enough, we can cut the feedstock at very short lengths. Auger feed - use a BM (no heat on) like die, but bigger, to force the biomass into a log like item. As the log exits, have several chain saw disk spinning very fast to produce a saw dust like and sized material. | solar or wind powered / ethanol powered
EP5 | Spread Trichoderma on substrate | Scaled up SSF incubator from small silo tests SSF: Slow moving belt - add substrate at beginning and pick off enzyme, or everything at the end |  | Theory with slow moving belt is that fill it at one end of the barn, and over the course of days the trichoderma replicates and produces cellulase. At the end of the belt, we'd collect the cellulase. The belt would be encased so that temperature, moisture, and light can be controlled. Many rows of these belts coudl be alinged side by side so that cellulase can constatly be produced throughout the year. We could freeze the enzmyes until needed and collect the heat from the freezers to heat the building or incubator belts. | solar or wind powered
EP6 | Control Temperature | • Electric element is easiest to control - will it dry things out though? • Hot water circulation to add heat • Air conditioner to remove heat |  | Although all the species of Trichoderma produced sufficient biomass at different temperatures viz. 20°C, 25°C, 30°C and 35°C but they were found to be best grown at a temperature range of 25°C to 30°C (77F to 86F)Aeration by agitation was also checked at different speeds such as 100, 150, 200 and 250 rpm but greatest biomass was recorded at 150 rpm. | solar or wind powered
EP7 | Control PH | Spray of a PH plus or minus in sprayer lines inside the SSF incubator |  | • The most favorable pH ranges between 5.5 and 7.5 in which total dry weight of mycelium varies between 1.41 and 1.35 g. • Check once/day and spray as needed?
EP8 | Control Moisture | • Pump humidifier output into SSF incubator as needed? • Duct the tank to the front of a dehumidifier if too humid? • Need a moisture level meter either way |  | • They make a house more humid. • They remove humitidy from a house. | solar or wind powered
EP9 | Extract Enzyme | • Vaccum celluase off top? • Mix everything with biomass in silo? • Filter/sift/scrape off cellulase? • Centrifuge to extract cellulase? |  | • If enzmes grow on top, could we control a vaccum enough to just suck off the enzymes • Even if less efficient, would it be simpler & cheaper to mix it all in with the biomass in the blower and keep some to start the next batch? To make up for the lack of efficiency, grow more trichoderma to increase the enzyme loading ratio. | solar or wind powered
EP10 | Measure Amount Produced
EP11 | Freeze enzyme?
Start next growth cycles
EP12 | Save 10% of fungi from initial rice substrate
EP13 | Repeat steps E2 thru E11
Taget endocellulase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces endocellulase well
Taget exocellulase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces exocellulase well
Taget B-Glucosidase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Reesei produces B-Glucosidase well
Taget Xylanase |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma harzianum has been used to produce enzymes to target Xylanase
Taget Glucoamalyse (for starch hydrolization) |  | Once we know how to grow fungi in general, find initial fungi to produce specific Cellulases • Trichoderma Viride can produce good enzymes for this
Enzymes that attack Cellulose are endocellulases, exocellulases, and B-Glucosidases Enzymes that attack hemicellulose come are glucoronide, acetylesterases, xylanase, B-xylosidase, galactomannase, and glucomannase
Pretreat Biomass
P1 | Chop | Cut as short as possible - slow feedrolls and groundspeed | Allis Chalmers 50 |  | ethanol powered
P2 | Hammer | Use small screen | PTO hammer mill |  | solar or wind powered / ethanol powered
P3 | Process 1 | a) Custom built meat grinder like machine b) Auger feed down slightly tapered tunner, with chain saw disks at end c) Hot water treatment d) Scaled up Wiley Mill e) Flash freeze and then mill? | Custom built machine | Meat grinder - push chopped biomass thru an opening, where outside of it is a rotating fan knife or disk or drum with cutting edges. Theory is if knives are spinning fast enough and feed is proceeding slow enough, we can cut the feedstock at very short lengths. Auger feed - use a BM (no heat on) like die, but bigger, to force the biomass into a log like item. As the log exits, have several chain saw disk spinning very fast to produce a saw dust like and sized material. | solar or wind powered / ethanol powered
Ensile Biomass with Enzymes
EN1 | Measure sugar of Switchgrass | Mix in blender with distilled water • 2 cups switchgrass • 2 cups water?
EN2 | Mix Switchgrass and fungi/enzyme mix from step EP11 | Mix in blower *** ensiling serves as dilute acid hydrolysis too |  |  | ethanol powered
Wash Sugar off of Silage
EN3 | Measure sugar of Switchgrass | 20 Days in - Mix in 500 gallon hydrolyder • SG and water ratios TBD • Length of mixing time TBD |  |  | solar or wind powered
Ferment
F1 | Extract liquid | Siphon liquid into another 5000 gallon drum | 5000 gallon hydrolyzer |  | solar or wind powered
F2 | Add yeast | xx Pounds of yeast | TBD
F3 | Add lid and CO2 trap | Seal lid on and put water in CO2 trap
F4 | Ferment | 1 week
Distill
D1 |  |  | Pot distiller |  | solar or wind powered
| Cooling water |  | New Swimming Pool
Dry leftovers and Densify

## Options for Process Steps
Cellulase Production on Farm
• Will need to make more cellulase than comparted to comercial producers, as we'll need more cellulase per gallon to make up for lack of efficiency of each unit of Cellulase
• Producing locally would eliminate transport costs
• Mix biomass with a plant that produces cellulase naturally. Univeristies are working to genetically modify plants (tobacco) to produce cellulase naturally. Both the biomass for fuel and cellulase producing plant could be grown on the same farm
• If growing on carbon based medium, find way to draw off Cellulase or cenrifuge it out, or just add the who mixture to the Hydrolysis process. Need to figure out how to grow Trichoderma fungus or reuse it and find way to draw off just the Cellulase and let the Trichoderma keep working, with the addition of more carbon based biomass as the growth medium.
• Could produce the Cellulase year round in a controlled environment, and during the winter and spring, store it for use when ensiling in summer or fall. Could use heat from controlled environment to heat other buildings, or to preheat the 'beer' prior to distillation.
Mechanical Breakdown of Biomass for fuel production and Cellulase growth medium
• Build a scaled up Wiley Mill
• Build a screw press with a 10,000 RPM chopping disk at the end
• Speed up chopper knives and slow feed rolls down
• Build a big meat grinder
• No chemicals means less cost and less complexity
Ensiling/Hydrolysis
• Mix with water and cellulase assay at time of ensiling. After 21 days, unload and wash sugars off of solids.
• Centrifuge enzymes off of solids first for enzyme recycling
• Use same screw press to extrude remaing liquid from hydrolized solids
• To stop enzyme activity, could also heat the slurry using densified left overs for heat. Either directly under a vessel or, via gassification where we burn the syngas for heat - this might allow for better control of the heating temperature.
• Use countercurrent extraction to remove sugars. Move material upward in extractors by means of augers. Water is added at the higher end of the extractor, moving in a countercurrent manner, downward with the force of gravity. Extracts contain a high solute concentration, depending on the liquid:solid ratio used during the extraction. Temperature also affects product recovery. Over 90% of the sugars and organic acid in sweet sorghum silage were extracted using a 2:1liquid:solid ratio at 70°C.
Ferementation
• Could be done in old milk tanks
• Could be done in other vessels. Vessels need to be clean first.
Distillation
• Use densified left overs for heat. Either directly under fermenter or, via gassification where we burn the syngas for heat - this might allow for better control of the heating temperature.
Densify Left Overs
• Use same screw press to produce briquettes (add heat for these runs)
• Build a screw press tunnel with a stainless steel sleeve or teflon on the inside
• Build solar oven to dry solids, or burn syngas in a generator to run a dehydrator
Heat and Power
• Install solar panels and wind turbine(s) to support the process. Grants and rebates would help make this feasible.
• Densify the left overs and burn to heat parts of the process, or gassify to produce syngas to run generators, or set up a CHP unit to provide heat and power.
• If cold storing enzymes from winter production for summer use, recycle heat give off for building heat or process heat
• Instal geothermal to help support the condensing process of the output from distillation