## Slide 1: Product Development Essentials
Assumptions
Prerequisites
The Team
The Plan
Meetings, reporting and tracking progress
Problems
Completion

## Slide 2: Assumptions
Competent marketing managers have verified commercial desire for the product
Competent sales managers have verified optimal sales volumes projecting for up to five years
Project has a budget provided by Management
Protection has been established or other mitigations in place
Active substance manufacturer(s) have been identified with an adequate data package (CEP, ASMF or otherwise).
Satisfactory Technical and Commercial agreements in place with ASM

## Slide 3: Prerequisites
Individuals suitable trained in their specific disciplined
  Experience and competence is also always desirable
  Training alone does not = competence
A costed and sponsor approved Project Plan
Individuals who are totally committed to the project
People who can communicate clearly and who can think and express ideas
Team players – loose cannons, prima donnas and dead wood tend not to help

## Slide 4: The Project Team
Project Lead selects team, project lead selected by sponsor
Note: It may be considered desirable to have a dedicated Project Manager + Project Leader for complex projects
Multidiscipline, typically qualified individuals from:
    Formulation
    Analytics
    Regulatory
    Manufacturing
    Quality Assurance
    Procurement
    Marketing
Team meets regularly in accordance with plan & milestones. Sub-groups normal

## Slide 5: The Project Plan
A fundamental and critical document which lays out:
  Specific tasks, task responsibilities, timelines (work time and duration) and milestones
Common to use commercial software e.g. MS Project but not essential
The plan should identify dependencies; e.g. stability studies cannot commence before necessary registration batches have been made
Similarly plan should clearly identify work (tasks) that can occur concurrently
It should also recognise task of fixed duration (e.g. batch analysis) and undefined duration (e.g. formulation development)
Review of milestones are a major and critical part of the plan
Similarly deviations or slippage needs to be documented, studied and reported

## Slide 6: Meetings, Reporting and Tracking Progress
Culture is critical – open, honest & candid opinions are desired and encouraged
A comprehensive initiation meeting is required, where project leader outlines in detail the project. Like all meetings this is minuted promptly
At the stage the draft project plan is discussed and agreed by all team members Note: It is normal for this to take several sittings to finalise
Team meetings are scheduled according to plan tasks and milestones. Apologies accepted when appropriate. All discussions subject to detailed and accurate minutes
Progress/delays/problems are reported ahead of the meeting so that they can be specifically addressed
The plan should be updated after each meeting and disseminated (inc. sponsor)

## Slide 7: Problems
Generally inevitable across all disciplines – you have to manage them
  Materials procurement, validation issues, process failures; a huge list and they happen
They are managed according to their nature & most commonly mean delay which should be built into the plan
Rarely, problems seem irresolvable and project leader may take expert external advice which may impact budget
It is relatively rare to encounter an issue that cannot be resolved but it does happen
Can you modify/adapt?
If the plug has to be pulled, avoid prevarication #nodeadhorses

## Slide 8: Completion
Learn from it
  Feedback from project team
  How did the team function?
  Who performed well and who didn’t? Why?
  What were the primary issues that arose and how were they resolved?
  What might be changed for the better next time?
  What mistakes were made?
Congratulate, recognise and thank.