## Executive Ops Data
Department | Project Name | Owner | Start Date | Status | Priority | Team Size | Due Date | Budget Allocated | Actual Spend | % Complete | Risk Level
Facilities | Distribution Center Relocation | L. Nakamura | 2026-03-17 | Not Started | Medium | 9 | 2026-08-29 | 73956 | 122856 | 20% | Low
Facilities | HQ Floor 3 Renovation | J. Ferraro | 2025-12-03 | Delayed | Medium | 8 | 2026-10-03 | 128951 | 170951 | 90% | Medium
Facilities | Parking Structure Repair | M. Lindqvist | 2025-11-26 | Not Started | Low | 9 | 2026-11-01 | 128658 | 107993 | 10% | High
Facilities | HVAC System Upgrade | K. Whitfield | 2025-11-09 | In Progress | Medium | 8 | 2026-09-30 | 95482 | 83772 | 90% | Low
Facilities | Lobby Modernization | A. Mbeki | 2026-01-06 | In Progress | Medium | 6 | 2026-11-04 | 130346 | 103909 | 85% | Medium
Facilities | Warehouse Safety Audit | T. Okonjo | 2026-04-03 | In Progress | High | 6 | 2026-12-12 | 81655 | 63800 | 55% | Low
Facilities | Loading Dock Expansion | J. Ferraro | 2026-01-20 | In Progress | High | 6 | 2026-10-23 | 62856 | 57031 | 85% | High
Facilities | Fire Suppression Inspection | M. Lindqvist | 2026-05-22 | Complete | High | 5 | 2026-07-02 | 123307 | 111752 | 100% | Medium
Facilities | Break Room Remodel | B. Osei | 2026-04-14 | Complete | High | 2 | 2026-07-19 | 125827 | 105734 | 100% | Low
Facilities | Campus Signage Refresh | A. Mbeki | 2025-10-05 | Not Started | High | 6 | 2026-08-11 | 110962 | 100105 | 35% | Medium
IT | Data Warehouse Consolidation | S. Petrov | 2025-11-27 | In Progress | High | 5 | 2026-08-27 | 69904 | 103604 | 90% | High
IT | Network Firewall Upgrade | D. Achebe | 2025-10-19 | Delayed | Medium | 3 | 2026-09-11 | 159160 | 171828 | 0% | High
IT | VPN Migration | D. Achebe | 2026-02-09 | Delayed | High | 5 | 2026-09-25 | 68442 | 63567 | 85% | Medium
IT | Helpdesk Ticketing Rollout | L. Nakamura | 2026-05-28 | Complete | Low | 5 | 2026-06-04 | 66415 | 58819 | 100% | Medium
IT | Cloud Storage Migration | J. Ferraro | 2025-11-18 | Not Started | High | 7 | 2026-11-07 | 86577 | 77504 | 65% | Medium
IT | Endpoint Security Rollout | N. Kowalski | 2026-05-10 | Not Started | Medium | 3 | 2026-11-14 | 159913 | 154703 | 0% | Medium
IT | Server Room Cooling Fix | R. Vasquez | 2026-04-23 | Not Started | Low | 5 | 2026-10-29 | 112374 | 93569 | 85% | High
IT | Employee Laptop Refresh | N. Kowalski | 2026-01-17 | Not Started | High | 3 | 2026-10-03 | 141031 | 121894 | 75% | Medium
IT | Intranet Redesign | G. Thackeray | 2025-10-13 | On Hold | Medium | 2 | 2026-09-28 | 159184 | 141932 | 10% | Medium
Operations | Vendor Onboarding Redesign | P. Andersson | 2026-02-27 | In Progress | Medium | 4 | 2026-09-22 | 154977 | 148890 | 0% | Low
Operations | Inventory Tracking Rollout | B. Osei | 2026-05-06 | On Hold | High | 5 | 2026-09-26 | 140090 | 148750 | 65% | Medium
Operations | Shift Scheduling Overhaul | G. Thackeray | 2025-12-03 | In Progress | Medium | 3 | 2026-11-27 | 125514 | 92745 | 65% | High
Operations | Supply Chain Audit | S. Petrov | 2026-02-11 | On Hold | Medium | 7 | 2026-11-27 | 103963 | 79424 | 35% | Medium
Operations | Warehouse Automation Pilot | K. Whitfield | 2025-11-03 | Not Started | Medium | 7 | 2026-08-17 | 71260 | 57116 | 10% | Medium
Operations | Quality Control Revamp | T. Okonjo | 2026-03-09 | In Progress | Low | 3 | 2026-08-13 | 105563 | 96956 | 85% | Low
Operations | Fleet Maintenance Program | B. Osei | 2025-12-07 | Complete | High | 3 | 2026-07-02 | 156200 | 136025 | 100% | Medium
Operations | Process Documentation Update | R. Vasquez | 2025-12-12 | Complete | High | 6 | 2026-07-19 | 79598 | 63398 | 100% | Low
Operations | Regional Distribution Review | A. Mbeki | 2026-04-28 | In Progress | Medium | 3 | 2026-07-31 | 70835 | 53335 | 20% | Low
Sales | CRM Data Cleanup | J. Ferraro | 2026-02-21 | On Hold | High | 4 | 2026-11-09 | 84662 | 76407 | 85% | High
Sales | Territory Realignment | E. Reyes | 2026-02-27 | In Progress | Medium | 2 | 2026-11-02 | 87763 | 79463 | 45% | Medium
Sales | Sales Enablement Toolkit | L. Nakamura | 2026-05-19 | Delayed | Medium | 3 | 2026-09-21 | 120166 | 116538 | 55% | Medium
Sales | Pipeline Forecasting Tool | T. Okonjo | 2026-03-08 | On Hold | Medium | 5 | 2026-11-07 | 56180 | 47900 | 20% | Low
Sales | Client Onboarding Redesign | P. Andersson | 2025-10-07 | Complete | High | 8 | 2026-07-14 | 67101 | 57093 | 100% | Low
Sales | Renewal Process Automation | T. Okonjo | 2025-11-10 | Delayed | Low | 2 | 2026-08-25 | 68295 | 50628 | 75% | High
Sales | Sales Training Refresh | P. Andersson | 2026-04-28 | Complete | Low | 5 | 2026-08-10 | 102942 | 75205 | 100% | Medium
Sales | Quota Planning Tool | A. Mbeki | 2026-03-18 | Complete | High | 3 | 2026-09-01 | 123395 | 102971 | 100% | Medium
Sales | Channel Partner Program | D. Achebe | 2026-03-14 | Not Started | Medium | 7 | 2026-08-20 | 69496 | 55973 | 0% | Medium
Finance | Q3 Budget Reconciliation | N. Kowalski | 2026-05-24 | In Progress | Medium | 3 | 2026-12-10 | 92067 | 104271 | 45% | Medium
Finance | Expense Policy Overhaul | C. Delgado | 2026-01-13 | Not Started | Medium | 4 | 2026-07-31 | 56178 | 40833 | 35% | Medium
Finance | Vendor Payment Automation | L. Nakamura | 2026-05-29 | Not Started | Medium | 4 | 2026-12-10 | 43190 | 33716 | 90% | Low
Finance | Audit Prep Workstream | T. Okonjo | 2026-02-18 | Not Started | Low | 5 | 2026-08-17 | 90218 | 81077 | 65% | Medium
Finance | Payroll System Migration | R. Vasquez | 2026-03-17 | On Hold | Medium | 5 | 2026-12-02 | 40536 | 38429 | 85% | Medium
Finance | Cost Center Restructuring | C. Delgado | 2026-03-18 | Not Started | High | 7 | 2026-10-07 | 85273 | 74663 | 10% | Medium
Finance | Invoice Approval Redesign | A. Mbeki | 2025-12-19 | Complete | High | 2 | 2026-06-10 | 46071 | 33424 | 100% | High
Finance | Financial Reporting Refresh | E. Reyes | 2026-01-30 | In Progress | Medium | 9 | 2026-08-27 | 64656 | 59655 | 65% | Low
Finance | Tax Filing Coordination | S. Petrov | 2026-04-02 | On Hold | Medium | 5 | 2026-10-10 | 39811 | 52642 | 20% | Medium
Marketing | Brand Refresh Rollout | E. Reyes | 2026-05-09 | Delayed | Medium | 5 | 2026-07-26 | 55506 | 48440 | 45% | Medium
Marketing | Website Redesign | N. Kowalski | 2025-12-01 | On Hold | High | 6 | 2026-08-02 | 54165 | 49952 | 35% | High
Marketing | Event Sponsorship Program | R. Vasquez | 2025-12-21 | Delayed | Low | 4 | 2026-10-28 | 42086 | 32255 | 35% | High
Marketing | Content Calendar Overhaul | M. Lindqvist | 2025-11-09 | Not Started | Medium | 8 | 2026-12-13 | 32680 | 28023 | 55% | High
Marketing | Email Automation Setup | K. Whitfield | 2026-01-15 | On Hold | High | 8 | 2026-11-14 | 23627 | 19780 | 90% | Low
Marketing | Social Media Audit | D. Achebe | 2026-01-06 | In Progress | Medium | 6 | 2026-11-28 | 26778 | 21254 | 65% | Low
Marketing | Lead Scoring Model | K. Whitfield | 2026-04-10 | Not Started | Medium | 5 | 2026-11-23 | 49419 | 48637 | 75% | Low
Marketing | Campaign Analytics Dashboard | C. Delgado | 2026-01-20 | Complete | Medium | 8 | 2026-08-01 | 74660 | 92943 | 100% | Medium
Marketing | Rebranding Rollout | G. Thackeray | 2026-01-28 | Complete | Low | 2 | 2026-05-20 | 31079 | 27604 | 100% | Low
HR | Onboarding Program Redesign | P. Andersson | 2026-06-01 | On Hold | Medium | 2 | 2026-09-22 | 64042 | 54455 | 0% | Medium
HR | Benefits Enrollment Overhaul | S. Petrov | 2026-05-03 | Complete | High | 4 | 2026-08-10 | 63185 | 47020 | 100% | High
HR | Performance Review Revamp | M. Lindqvist | 2025-10-30 | On Hold | Medium | 6 | 2026-07-31 | 51022 | 41440 | 55% | High
HR | Recruiting Pipeline Rebuild | G. Thackeray | 2026-03-05 | Delayed | Low | 4 | 2026-08-04 | 28299 | 22874 | 45% | Low
HR | Employee Survey Rollout | E. Reyes | 2025-10-07 | In Progress | Low | 8 | 2026-11-29 | 48096 | 55523 | 65% | Medium
HR | Compliance Training Refresh | A. Mbeki | 2026-03-01 | Complete | Medium | 3 | 2026-08-26 | 50237 | 47589 | 100% | Medium
HR | HRIS Migration | A. Mbeki | 2026-03-03 | Delayed | Low | 2 | 2026-12-12 | 26601 | 41408 | 55% | Low
HR | Wellness Program Launch | A. Mbeki | 2026-03-19 | On Hold | Medium | 7 | 2026-11-09 | 43518 | 36080 | 0% | Medium
Legal | Contract Repository Cleanup | B. Osei | 2026-03-21 | On Hold | Medium | 7 | 2026-12-03 | 52730 | 44889 | 20% | High
Legal | Compliance Policy Refresh | C. Delgado | 2025-12-30 | Not Started | Low | 6 | 2026-10-13 | 23823 | 21335 | 85% | Medium
Legal | Vendor Agreement Review | C. Delgado | 2026-05-31 | In Progress | High | 8 | 2026-11-21 | 49712 | 41068 | 75% | High
Legal | IP Filing Backlog | J. Ferraro | 2026-03-26 | On Hold | Medium | 9 | 2026-10-16 | 45073 | 41536 | 0% | Low
Legal | NDA Template Update | R. Vasquez | 2025-11-26 | In Progress | Medium | 7 | 2026-10-23 | 55346 | 40387 | 75% | High
Legal | Litigation Hold Process | M. Lindqvist | 2026-04-09 | Not Started | Medium | 9 | 2026-08-15 | 37203 | 27654 | 45% | Medium
Legal | Data Privacy Audit | S. Petrov | 2025-11-29 | Delayed | High | 3 | 2026-10-18 | 26778 | 21071 | 85% | High
Legal | Regulatory Filing Review | A. Mbeki | 2025-11-25 | Complete | Medium | 6 | 2026-08-11 | 40255 | 30220 | 100% | Medium
Legal | Employment Policy Update | C. Delgado | 2025-12-15 | In Progress | High | 2 | 2026-10-10 | 30080 | 27815 | 85% | High