| ACDA FOUNDERS MEETING MINUTES 6/8/2024 11 am Location: Marilyn’s House |  |  |  |
| --- | --- | --- | --- |
| ATTENDING MEMBERS Lori Swetlin Marilyn Buchwald Sam Heider Janice Marciniak (Via phone) |  |  |  |
| Topic | Discussion | Next Action | Responsible Team Members |
| G Drive Projects ACDC | All ACDC Projects are listed and being tracked in G Drive for project management | Please review and update assigned projects on an ongoing basis | All |
| Fitness Center | Ideally, the Fitness Center would contain: Physician’s/healthcare provider office Mental Health provider office Fitness Center Reception area | -Meet with Unified Bank to inquire what type of financing plan would be best to finance the Fitness Center, i.e. membership, donations, etc. -Lori is in contact with a person whose company creates a picture using individual’s pictures to create a large picture acknowledging all donors -Megan will obtain quote for gazebo/pavilion after property is excavated | Lori Melissa Lori Megan |
| Ohio CDCA | Lori and Marilyn attended a regional OCDCA meeting 5/22/2024. Many good contacts established. OCDCA offered ACDC free membership in OCDCA, which will save us $275.00. OCDCA has offered a follow up meeting with ACDC | -Send Julia Robinson a thank you for our free membership -Confirm a meeting time of June 14th, after 12 noon -Develop an agenda for OCDCA meeting that includes: -How to fund a Community Center using community donations -Advice about Blue Zones -Best way to track money and finances -Accounting tools -IRS -Newsletter | Marilyn Marilyn Lori |

| Newsletter | US Post Office may use ACDC for pilot studies in their projects in rural communities. -ACDC should receive a rate of .111 per piece for a flat sheet of paper 11X7 folded in half for the newsletter -Newsletter will contain information on MWCD, local businesses -Estimated cost for newsletter for Dover, Bolivar, New Philadelphia, Leesville and all zip codes that touch the lake (29,000 pieces) is estimated at $10,000.00 | -USPS will assign a Specialist to work with Lori -Apply for USPS non-profit permit -Contact Buckeye Career Center to develop a template for newsletter -Consider using USPS Local Connect for rural businesses -Consider parcel lockers for deliveries -Consider a digital newsletter for now -Explore grant opportunities for the ACDC newsletter, -Consider the Ashton Foundation for a grant request as suggested by Mike Humphries | Lori Marilyn Megan Lori Lori Lori Lori,Marilyn |
| --- | --- | --- | --- |
| Blue Zones | Have not received any feedback from MWCD regarding the Blue Zones proposal | Send a follow-up email to Sheila Hurley and Ethan Zucal | Janice |
| MWCD Foundations | Lori and Marilyn met with Sheila Hurley to update her on our progress. | -It was suggested that ACDC consider taking on the beer and wine concession for the next Bounty on the Bridge this October as a fund raising activity as well as giving ACDC an opportunity to showcase our organization -Forward a thank you email to Sheila for our meeting | All Marilyn |
| Art Show | Sam will lead this project with back up as her Gold Girl Scout Project | Ask for sponsorships for show -Meet with the New Philly Alley Cats owners- consider partnering with them for a possible seasonal site in Dellroy including their vendors -Contact the Second Shop in Carrollton (located behind the Carroll County Arts Center) -Consider Dellroy Murals, post office, bowling alley -Contact Mayor Amy -Post FB notification of the upcoming art show | Lori Sam Lori Lori Sam, Lori |
| Alpaca Fleece Processing | Kathy Thompson, owner of a local alpaca farm, has a contact in Lorraine, Ohio who is interested in applying for grants to establish a fleece processing plant | Consider working with the Lorraine company to establish an off site storefront in the Atwood area that would service local alpaca farms as well as selling yarn, etc. | All |

| Dellroy Barn | Tom and Carol Abel are the owners of the renovated white barn in Dellroy | Connect with the Abel’s to explore possible opportunities for their property, i.e. small winery | Lori |
| --- | --- | --- | --- |
| ACDC Facebook Activity | Reviewed FB contacts from individuals interested in participating in our art show and responded to all messages | -Responses were sent to Susan Spar (newsletter), Nic Kucera, Larissa Beatty, Melissa Allen, Pamela Cadwell, Sasha Poole and Gabriella Stanik | Lori Sam Lori |
| ACDC Contacts | Participants in Community Meetings and FB were added to the ACDC contact list in Gmail | -Future contacts to establish: Dellroy Trustees Sherrodsville Mayor |  |
| Other Professional Contacts | -The Ready Foundation is sponsored by the Ready Appalachia Program that offers grants up to $25,000 for non-profits in the Appalachia region. -SCORE is a non-profit association that assists small businesses | -Lori and Marilyn are registered for The Ready Foundation Pre-App Webinar 6-13-2024 -Check out their website for upcoming classes you may be interested in | Lori Marilyn All |
| Next ACDC Founder’s Meeting |  | Next Commmunity Meeting is scheduled for Thursday, June 26th. | All |