TOWN OF ELBRIDGE – UNOFFICIAL
JOINT MUNICIPAL WATER MEETING
JULY 21, 2026

Minutes for the July 21, 2026 Joint Municipal Water meeting, held at the Town of Elbridge Route 5, Jordan, NY.  The meeting was called to order at 9:06 AM by a Barton & Loguidice Representative.
PRESENT:			Kenneth Bush III, Supervisor
				Todd Platten, Councilman
				Joe Farrugia, Councilman

RECORDING SECRETARY:	Patti Cooper, Town Clerk

OTHERS PRESENT:	Village of Elbridge Mayor Christopher DeCola, Village of Elbridge Clerk, Tammy Kunz, Dawson Dunham, Fred DiRisio, Tom King, Marty Williams, Barton & Loguidice Representatives

Resolution:  82-26
SEQR Amendment resolution determining that the Town of Elbridge concurs with the determination of the Village of Elbridge that the proposed Village of Elbridge, Town of Elbridge and Village of Jordan Joint Water System improvement project is a Type 1 action and will not have a significant adverse impact on the environment.
RESOLVED: 
Motion was made by:  Todd Platten; Seconded by:  Joe Farrugia – the above resolution was ADOPTED with no discussion.  
(3) Ayes (Platten/Farrugia/Bush)
(0) Nays

Contract 1:  Distribution System and Pumping Stations Improvements
a.  Payment Application No. 14
		i. 	$198,330.00
		ii.	Percent Complete 90%
		iii.	Includes:
			1.  Pump Station sites
			2.  Brutus Vault Stored Materials
	Village of Elbridge (27.6%)		$54,739.08
	Town of Elbridge  (42.4%)		$84,091.92
	Village of Jordan  (30.0%)		$59,499.00          
	Amount due to the Contractor	$198,330.00

Motion was made by Todd Platten to pay the $84,091.92, seconded by Joe Farrugia – motion carried with no discussion.
(3) Ayes (Platten/Farrugia/Bush)
(0) Nays

b. Construction Update
i. Kingston: July production / tentative week of Aug 24th delivery
ii. Hamilton: Sept production/ tentative week of Oct 26th delivery
iii. Jordan: Oct production/ tentative week of Dec 1st delivery
iv. Crossett: Nov production/ tentative end of December and/or beginning of
                    January delivery
v. Brutus Tank to be put online once outlet pipe is tested.
c. Next progress meeting is July 29th at 1:00 PM at the Job Site Office, 243 E Main Street,
     Elbridge, NY 13060

2. Contract 1B: Distribution System and Pumping Stations Improvements
a. No Payment Application

3. Contract 2: Distribution System and Pumping Stations Improvements
a. Payment Application No. 13
i. $567,216.68
ii. Percent Complete: 93%
iii. Includes:
1. Water Main Installation
2. Water Services
3. Asphalt Restoration
Village of Elbridge (27.6%) $156,551.80
Town of Elbridge (42.4%) $240,499.88
Village of Jordan (30.0%) $170,165.00
Amount due to the Contractor $567,216.68

Motion was made by Todd Platten, seconded by Ken Bush III; with the following discussion.  All three municipalities to HOLD payment for Application #13 until Highlander can provide a schedule that has end dates for each street.  There will also be an on-going list sent to Ian Douglass at B&L on items that we are not happy with (i.e. Fire Hydrant placement, pipes in certain spots, etc).  Todd Platten will take complaints from Town of Elbridge; as well as Village of Jordan and relay these back to Ian.  Tammy Kunz and Chris DeCola will continue to take complaints from Village of Elbridge and relay those back to Ian with B&L.  These complaints will then be sent to Highlander for correction if possible.  With this discussion, motion was carried to hold above funds for application #13.
(3) Ayes (Platten/Farrugia/Bush)
(0) Nays

b. Construction Update
i. All water main is installed
ii. 2 Water Services left on Jordan Road
iii. Setting the MHP PRV Vaults
iv. Restoration
c. Next progress meeting August 5th at 1 PM at Job Site Office, 243 E Main Street, Elbridge,
     NY 13060
d. The boards agreed to hold payment again until Highlander provides a schedule breaking
     out restoration locations and remaining work to be done by street.
e. Major areas of concern noted during the meeting include:
i. Vent location for the air relief valve by the Garden and on Mechanic Street.
ii. Blacktop in front of the library instead of the brick sidewalk.

4. Contract 3: Water Storage Tank Improvements
a. No Payment Application
i. Percent Complete: 90%

5. Potential Change Orders (PCOs)
a. Contract 1
i. Summary to date:
1. Item 1A.33 MAW: $200,000.00
2. PCOs Submitted Total: $212,829.00
3. PCOs Accepted Total: $107,256.46
4. Balance: $92,743.54
ii. PCO-017, Railroad Services: $26,500.00
1. Balance if Accepted: $66,243.54
2. The group decided to wait until the August meeting to decide.
b. Contract 2
i. Summary to date:
1. Item 2A.28 MAW: $180,000.00
2. PCOs Submitted Total: $523,958.19
3. PCOs Accepted Total: $177,628.90
4. Change Order 3: $50,000.00
5. Balance: $52,371.10
ii. PCO-050 to PCO-052 DeMarco Water Service: $21,442.03
1. Balance if Accepted: $30,929.07
2. The group decided to wait until the August meeting to decide.

6. Budget Tracker 

7. Additional Discussion
a. Jordan Road Main
i. DOH approval
b. Jordan Road Tank
i. Land Acquisition
ii. Soil Borings
iii. Design (B&L Amendment)
c. SEQR Amendment (Town of Elbridge)
i. Town completed at meeting
d. Bond Increase to be put on August Agendas
i. B&L will provide a handout for the August Board meetings.


Motion to adjourn at 10:15 AM was made by Todd Platten, seconded by Ken Bush III.

Submitted by
Patti Cooper, Town Clerk
