TOWN OF ELBRIDGE

JOINT MUNICIPAL WATER MEETING

February 17, 2026

Minutes for the February 17, 2026 Joint Municipal Water meeting held at the Town of Elbridge Route 5, Jordan NY.  The meeting was called to order at 9:05 AM by Town of Elbridge Supervisor, Kenneth Bush III.

PRESENT:			Kenneth Bush III, Supervisor

Todd Platten, Councilor

Joe Farrugia, Councilor

RECORDING SECRETARY:	Patti Cooper, Town Clerk

OTHERS PRESENT:  Village of Jordan Mayor Casey Brimm, Fred Wieskoff, Village of Elbridge Mayor Christopher DeCola

- Contract 1:	Distribution System and Pumping Stations Improvements

- Payment Application No. 11

- $212,424.83

- Percent Complete:  76%

- Includes:

- Kingston Road Site Work

- Hamilton Road Site Work

Village of Elbridge (27.6%)		$58,629.25

Town of Elbridge (42.4%)		$90,068.13

Village of Jordan (30.0%	)		$63,727.45

Amount Due to the Contractor		$212,424.83

Resolution #47/26

Motion made by Councilor Platten for Town of Elbridge to pay the $90,068.13 portion, seconded by Councilor Farrugia.

ADPOPTED:  (3) Ayes, motion carried.

- RFP-004, Fencing Hamilton Drainage Basin

- Discussion was initated by Councilor Platten regarding the fencing pricing.  Robinson quoted approximated $45,000.00 for this.  Councilor Platten asked Arrow Fence do a quote.  There was some discrepancy on the quantities to scale; however, Arrow Fence gave two quotes:

- Galvanized 4’ fencing - $12,105.00

- Red split rail 4’ fencing - $13,185.00

- There is a 30 day valid estimate to guarantee these prices.  All decided that we do not want Robinson to do the fencing even if pricing from Arrow goes up a little bit.

- Next progress meeting is March 4th at 9:00 AM at the Job Site Office, 243 E Main Street, Elbridge NY 13060

- Contract 2:	Distribution System and Pumping Stations Improvements

- No Payment Application

- Percent Complete:  73%

- Next progress meeting March 4th at 1:00 PM at Job Site Office, 243 E Main Street, Elbridge, NY 13060

- Contract 3: 	Water Storage Tank Improvements

  - Payment Application No. 7

    - $4,180.00

    - Percent Complete:  85%

    - Includes:

      - Hamilton Road Tank Testing

Village of Elbridge (27.6%)		$1,153.68

Town of Elbridge (42.4%)		$1,772.32

Village of Jordan (30.0%)		$1,254.00

Amount Due to the Contractor		$4,180.00

Resolution #48-26

Motion made by Councilor Farrugia for Town of Elbridge to pay the $1,772.32 portion, seconded by Councilor Platten.  ADOPTED:  (3) Ayes, motion carried.

- No Cost Change Order No. 4

  - Contract 2:  Highlander Construction

Resolution #49-26

On a motion made by Councilor Platten to approve final completion dates as noted on Change order #4, seconded by Councilor Farrugia.

ADOPTED:  (3) Ayes, motion carried.

- Potential Change Orders (PCOs)

  - Contract 1

    - PCO-013 Revised:  Cold Weather Concrete ($5,510.47)

    - PCO-014: Kingston Road Pump Station Connection ($7,960.00)

    - Summary to Date:

      - Item 1A.33 MAW:	$200,000.00

      - PCOs Submitted Total:	$212,829.00

      - PCOs Accepted Total:	$107,256.47

      - Balance:		$92,743.53

  - Contract 2

    - Summary to date:

      - Item 2A.28 MAW:	$180,000.00

      - PCO’s Submitted Total:	$522,355.84

      - PCOs Accepted Total:	$174,356.61

      - Change Order 3:	$   50,000.00

      - Balance:		$  55,643.39

- Budget Tracker (see attached)

  - Contingency Options

    - Meadow Loops

    - Replacing Jordan Road Water Main

- IMA (Approved Town of Elbridge, Village of Jordan – Village of Elbridge will vote at next meeting)

On a motion by Councilor Platten, meeting was adjourned at 9:46 AM and seconded by Councilor Farrugia.  Motion accepted and carried.  Next Water Project meeting will be on March 17, 2026 at 9:00 AM at the Town of Elbridge, Route 5, Jordan, NY.

Respectfully,

Patti Cooper, Elbridge Town Clerk