## Slide 1: WHO-HOW-WHAT template How to capture the data to develop a Communication and Training Plan
Thorsten Manthey
tmanthey@kpmg.com
www.tmanthey.com/speaker.html

## Slide 2: 1. WHO IS AFFECTED?
Group | Contact | Description | # Members / Information
Remember to stick to the agenda - WHO, don’t start identifying HOW or WHAT.
INITIAL MEETING
  Invite a representative from each group you think is affected
  Capture affected groups in the initial meeting and identify a contact person
SECOND MEETING
  Invite to a second validation meeting with all identified groups to validate the list

## Slide 3: 1. WHO IS AFFECTED?
Group | Contact | Description | # Members / Information
Identify all groups that are being affected in any aspect by the change
  Users of the new system, tool or processes being implemented
  Data consumers e.g. reporting teams or finance teams etc.
  Managers – for approvals, manager of the users that are impacted
  Service Desk / 2nd level support / Technical support
  Developers / Designers
  HR / Finance / Procurement
  External Vendors / Partners
Remember to stick to the agenda - WHO Don’t start identifying HOW or WHAT

## Slide 4: 1. WHO IS AFFECTED?
Group | Contact | Description | # Members / Information
Service Desk | NN | Handles first level phone calls and tickets from customers. USA and India. | +90 customer service rep, multiple locations, 7x24x365
2nd level Support | NN | Handles escalated calls from the Service Desk. Two locations in the US | 15 support staff, two main locations, 7:00-21:00 business days
HR | NN | Supporting with the new roles and organizational changes | 5 HR people supporting the IT organization
Procurement | NN | Internal team plus a number of vendors | 2 people in procurement team. 3 major vendors
Finance | NN | Provides input to the new process via an automated feed from finance system | 2 VPs and their groups, total of 9 people
IT Managers | NN | All IT managers within the Infrastructure organization | All line managers 45 managers + their team, total ~800 people
Customers ordering services | NN | Anyone using the process. | USA: 1,500 people India: 200 people
Reporting team | NN | Extracting data from the system creating monthly reports | 6 individuals
Interfacing process teams | NN | Multiple interfacing processes | 5 process managers and 5 process owners
App. Development | NN | The team leader for the application development team X | 1 team lead and 10 people in the team in total
Example

## Slide 5: 1. WHO IS AFFECTED?
Group | Contact | Description | # Members / Information

## Slide 6
Affected Group | How are the affected? / What information do they need?
Remember to stick to the agenda - HOW, don’t start identifying WHAT.
INITIAL MEETING
  Invite the contact person from each affected group
    What is changing?
    What is not changing?
SECOND MEETING
  Invite to a second validation meeting with all identified groups to validate the information
2. HOW ARE THEY AFFECTED?

## Slide 7
Affected Group | How are the affected? / What information do they need?
Ask the following questions for each of the affected groups identified
  What is changing for this group? What will be different?
  What is not changing for this group? What will be the same?
  What is driving the change, why are we changing?
  What is the Vision for the Enterprise / BU / Group?
  What does success look like for this Enterprise / BU / Group?
  WIIFM? (most likely different for each of the Groups)
  Who is going to lose/gain what?
  What happens if we do NOT change?
2. HOW ARE THEY AFFECTED?

## Slide 8: 2. HOW ARE THEY AFFECTED?
Affected Group | How are the affected? / What information do they need?
Service Desk | Emails, calls and chat to the Service Desk about the new tools/system/processes Knowledge about the new/updated/deleted tools/system/processes e.g. how to access, use, convert etc. How and where to escalate and route calls to 2nd level support Need to know when the tool/system/process has been released – Go Live date (staffing etc.) Implementation plans e.g. will there be a Hyper Care, phased roll-out etc. Information about Notifications, Approvals, Status Views, Escalations etc. in the new tool (Service Catalog) New support scripts to be developed / New FAQ and knowledge articles / Update existing information Etc.
2nd Level Support | Escalations to the 2nd Level Support about the new tools/system/processes How to escalate and route to external vendor Need to know when the tool/system/process has been released – Go Live date (staffing etc.) Implementation plans e.g. will there be a Hyper Care, phased roll-out etc. Information about Notifications, Approvals, Status Views, Escalations etc. in the new tool (Service Catalog) New support scripts to be developed / New FAQ and knowledge articles / Update existing information Etc.
Managers | New roles and organizational changes e.g. new or different skills needed? Execution/ operational procedure changes, sourcing models etc. New / different reports or reporting structures Policy updates e.g. approvals, escalation etc. Etc.
Process Users | New tools and procures executing the process New or different skills required for the new role
Reporting team | New user interface when extracting data from the tool/system New data fields and values Mapping of old data to new data etc.
Etc. | 
Example

## Slide 9
Affected Group | How are the affected? / What information do they need?
2. HOW ARE THEY AFFECTED?

## Slide 10: 3. WHAT ARE THE NEEDED ACTIONS?
# | <Name of Affected Group> | Developer | Timing
1 |  |  | 
2 |  |  | 
3 |  |  | 
SEPARATE MEETINGS
  How much people change management is needed?
  Identify the “actions” needed
    Hands on training (virtual, on site, CBT), exercises, demonstrations, FAQs, role plays, email communications, newsletters, web information, recorded videos, lunch & learn, group meeting, virtual meeting, town hall, one-on-one coaching, detailed examples etc.
  Tasks and Actions are identified to:
    Mitigate anticipated resistance, address unique attributes of each group, address historical or cultural barriers, leverage key influences, build awareness and desire to engage, provide needed knowledge and skills (training)

## Slide 11: 3. WHAT ARE THE NEEDED ACTIONS?
Separate meeting with each affected group with key stakeholders
  Multiple meeting might be required
  One PPT slide for each group
Capture:
  What activity is needed
  The person / role responsible to develop the material / training etc.
  The timing (a specific date or e.g. 1 week before go live)
# | Actions for <Group Name> | Developer | Timing
1 |  |  | 
2 |  |  | 

## Slide 12: 3. WHAT ARE THE NEEDED ACTIONS?
# | Actions for Service Desk | Developer | Timing
1 | Live Demonstration of the End-to-end tool/system/process Train the trainer, live training (NN, NN, NN) Record demonstration and place on web page | Process Expert (NN) | 2 weeks before go live, 1 week before training session
2 | Information - Need to know when the tool/system/process has been released – Go Live date Email sent with release information (2 different emails) | Project Manager (NN) | 4 weeks before go live and also just days before Go Live
3 | Training and some hands on exercise on how to use the tool/system/process and how to escalate any issues the user experiences to 2nd level support. Train the trainer, live training (NN, NN, NN must attend) Record session and place on web page | Process Expert (NN) | 2 week before Go Live and just after Go Live (two sessions)
4 | Information session (Live web meeting and Q&A) about Notifications, Approvals, Status Views, Escalations etc. in the tool/system/process Train the trainer, live training will deliver session | Train the Trainer person (NN) | 1 week before Go Live and just after Go Live (two sessions)
5 | Service Desk Activity – Develop new support scripts / New FAQ and knowledge articles / Update information that exist / review & update what information is on the web | Service Desk Manager | Prepare before go live and release at Go Live
6 |  |  | 
Example

## Slide 13: 3. WHAT ARE THE NEEDED ACTIONS?
# | Help Desk | Developer | Timing
1 |  |  | 
2 |  |  | 
3 |  |  | 
4 |  |  | 
5 |  |  | 
6 |  |  | 
7 |  |  | 
8 |  |  | 
9 |  |  | 
10 |  |  | 
11 |  |  | 
12 |  |  | 

## Slide 14: OVERALL TIMELINE
Usually takes 3-5 week to execute
Start as soon as possible!
The data you collect is a SOLID START to the Communications & Training (C&T) Plan
Remember, the C&T Plan is a living document
As a facilitator you collect and update the information gathered and distribute prior to the second meeting.
Individual meetings scheduled with each of the affected groups to identify the actions (WHAT).
Week 1
Week 2
Week 3
Week 4
Week 5
WHO
HOW
WHAT

## Slide 15: STICK TO YOUR AGENDA
It is a very simple approach: WHO – HOW – WHAT, but very effective!
If you stick to the agenda you will have solid data to populate the Communications & Training Plan.
  It is very easy to get off track by focusing on “WHAT” too early and getting into the weeds – DON’T DO IT