## Project Schedule
Work Stream 01: <NAME> |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01
Start Date of the Week | time axis 2018-05-06 to 2019-03-02
# | Activities | time axis 2018-05-06 to 2019-03-02
1 | Key Activity Group 1 | 2018-05-06: Key Activity Group 1
1.1 | Gap analysis | bar: 2018-05-06 to 2018-05-20
1.2 | Establish detailed project plan and scope work | 2018-06-17: 14-Jun: Establish detailed project plan and scope work
2 | Key Activity Group 2 | 2018-06-24: Key Activity Group 2
2.1 | Sub Activity 2.1 | 2018-07-22: 19-Jul: Sub Activity 2.1
2.2 | Sub Activity 2.2 | 2018-07-01: 28-Jun: Sub Activity 2.2
2.3 | Sub Activity 2.3 | 2018-08-26: 23-Aug: Sub Activity 2.3
2.4 | Sub Activity 2.4 | bar: 2018-08-26 to 2018-09-09
2.5 | Sub Activity 2.5 | 2018-09-30: 23-Sep: Sub Activity 2.5
2.6 | Sub Activity 2.6 | 2018-09-30: 27-Sep: Sub Activity 2.6
3 | Key Activity Group 3 | 2018-06-17: Key Activity Group 3
3.1 | Sub Activity 3.1 | 2018-07-15: 12-Jul: Sub Activity 3.1
3.2 | Sub Activity 3.2 | 2018-08-26: 23-Aug: Sub Activity 3.2
3.3 | Sub Activity 3.3 | 2018-08-05: 02-Aug: Sub Activity 3.3
4 | Key Activity Group 4 | 2018-07-01: Key Activity Group 4
4.1 | Sub Activity 4.1 | 2018-07-22: 19-Jul: Sub Activity 4.1
4.2 | Sub Activity 4.2 | 2018-08-12: Vacation; 2018-09-30: 27-Sep: Sub Activity 4.2
4.3 | Sub Activity 4.3 | 2018-08-12: Vacation; 2018-09-30: 27-Sep: Sub Activity 4.3
4.4 | Sub Activity 4.4 | 2018-10-28: 25-Oct: Sub Activity 4.4
4.5 | Sub Activity 4.5 | 2018-10-28: 25-Oct: Sub Activity 4.5
5 | Key Activity Group 5 | 2018-09-30: Key Activity Group 5
5.1 | Sub Activity 5.1 | bar: 2018-09-30 to 2018-10-21
5.2 | Sub Activity 5.2 | 2018-10-28: 25-Oct: Sub Activity 5.2
5.3 | Sub Activity 5.3 | 2018-11-04: 01-Nov: Sub Activity 5.3
Milestone
Deliverable (Mandatory: Listed in separate tab)
Planned task
Completed task
Delayed task
Vacation
TODAY

## WBS Activities
Work Stream 01: <NAME>
Task ID | Streams; Work ; Task | Predecessor | Task Description | Start Date | End Date | Completed (Yes or No or free text) | Owner (TCS or Saipem name) | Execution / Status Comments | RAG | Completion comment
Key Activity Group 1

## Deliverables
Work Stream 01: <NAME>
# | Description | Target Date | Completion | Status | Sign-Off (Who signed off the deliverable) | Comments
1
2
3
4

## Project Team
Project Team | Org | Role
NN |  | WS Lead
NN |  | Client SPOC
NN |  | OCM Lead
NN |  | HR
NN |  | Stakeholder from ABC
NN |  | Stakeholder from XYZ

## Week #
Weeks