## Risk Register
Risk Item Details | [5 empty] | Risk Analysis |  |  |  |  | Risk Response Plan
# | Stream | Risk Status | Date Identified | Risk Category | Risk Description | Potential Impact | Assigned to | Probability (1-5) | Impact (1-5) | Risk Level (1-25) | Response Strategy | Mitigation Actions (Actions to eliminate Risk) | Contingency Plan (When risk has happened)
1 | 0-PM & General | Active | 2019-09-01 | Resources & People (TCS, Saipem, vendor) | There is only one person within the project with the critical skill of the ABC application which is a critical skill the project rely on. | Delay or failure of the project if the skill is not available. | John Smith | 3 | 5 | 15 | Mitigate | Make sure the person with the critical skill of application ABC conducts knowledge sharing sessions during the project. | Search within the organization or on the market for a person with the needed skills.
2 | [9 empty] | 0
3 | [9 empty] | 0
4 | [9 empty] | 0
5 | [9 empty] | 0
6 | [9 empty] | 0
7 | [9 empty] | 0
8 | [9 empty] | 0
9 | [9 empty] | 0
10 | [9 empty] | 0
11 | [9 empty] | 0
12 | [9 empty] | 0
13 | [9 empty] | 0
14 | [9 empty] | 0
15 | [9 empty] | 0
16 | [9 empty] | 0
17 | [9 empty] | 0
18 | [9 empty] | 0
19 | [9 empty] | 0

## Detailed Instructions
Column
Cell | Name | Description
Risk Register Worksheet
A | Risk # | Enter Risk Number
B | Stream | The name of the Work Stream or if it is a Project Management/General risk
C | Risk Status | Is the risk Active, Completed, Cancelled or did the Risk Happen
D | Date Identified | Enter date when risk is identified
E | Risk category | Example category Project Management (e.g. timeline, planning), Resources & People (TCS, external, vendor), Process / Workflow, Technology / Infrastructure, Governance & Communications, Quality, External
F | Risk Description | Enter risk description (text)
G | Potential Impact | Enter potential impact if risk occurs (text)
H | Assigned to Team Member | Enter assigned team member's name (name)
I | Probability of Occurrence | Probability of risk occurrence: 0: No probability; 1: Improbable (1-20%) , 2: Possible (21-40%), 3: Probable (41-60%), 4: Highly probability (61-80%): 5: Almost certain (81-100%)
J | Impact of Risk | Enter risk impact: 0: None, 1: Minimal impact, 2: Small impact, 3: Average impact, 4: Large impact, 5: Very large impact
K | Risk Level | Automatically calculated by by multiplying the probability of occurrence by the impact of risk. (The threshold for a detaild action plan is 15)
L | Response Strategy | Choose from one of the responses below:
Acceptance: Accept the consequences, will not hurt the overall project success, but may delay a milestone.
Avoidance: Eliminate the cause of the risk - change the project direction to protect the project objectives from this impact.
Mitigation: Take action to reduce probability that the risk will occur to an acceptable threshold.
Transference: Transfer the responsibility of managing the risk, including ownership, and acceptance of consequences. Transference does not eliminate the risk.
M | Mitigation Actions (Before risk happens) | How to respond/mitigate the risk identified.
N | Contingency Plan (When risk has happened) | Actions to kake after risk has happened and is now an issue

## Risk Response
Reduce | The risk is reduced by either reducing the likelihood of the risk or by reducing the impact of the risk. For this, develop a mitigation and a contingency plan. Mitigation plan: Includes actions to be taken before the occurrence of a risk, so as to reduce or eliminate the risk. Contingency plan: Includes actions to be taken when the risk occurs even after mitigation. Also includes a fallback plan, in case the actions are not effective.
Avoid | The risk is avoided when you have removed the source of risk itself. Risk is no longer applicable for the project.
Transfer | The risk is transferred to another party by the project team. In such a case: Develop a contingency plan Transfer to another party with full consent and acknowledgment
Accept | The risk is accepted when options for mitigation, avoidance and transfer are not available. Then: Develop only a contingency plan Seek approval by project sponsor

## Risk Analysis Matrices
Risk Analysis Matrix 1
Impact (If Risk Occurs) | 5 | [5 empty] | Probability Levels
[7 empty] | 1 | Improbable (1 - 20%)
[7 empty] | 2 | Possible (21-40%)
[7 empty] | 3 | Probable (41-60%)
| 4 | [5 empty] | 4 | Highly Probably (61-80%)
[7 empty] | 5 | Almost Certain (81-100%)
Impact Levels
| 3 | [5 empty] | 1 | Minimal
[7 empty] | 2 | Small
[7 empty] | 3 | Average
[7 empty] | 4 | Large
| 2 | [5 empty] | 5 | Very Large
Contingency Planning A Contingency Plan should be developed for risks that fall into the “Red Zone." Development of a Contingency Plan should be considered for risks that fall into the "Orange Zone." The Contingency Plan will be executed when the risk event occurs and is intended to reduce the impact of the risk event on the project.
1
|  | 1 | 2 | 3 | 4 | 5
Probability (That the Risk will occur)

## List
Probability Levels | Impact of Risk | Response Strategy | Risk Status | Category | Stream
0 | 0 | Accept | Active | Project Management (e.g. timeline, planning) | 0-PM & General
1 | 1 | Avoid | Complete/Closed | Resources & People (TCS, Saipem, vendor) | 1-<WS1 Name>
2 | 2 | Mitigate | Cancelled | Process / Workflow | 2-<WS2 Name>
3 | 3 | Transfer | Risk Happened | Technology / Infrastructure | 3-<WS3 Name>
4 | 4 |  |  | Governance & Communications | 4-<WS4 Name>
5 | 5 |  |  | Quality | 5-<WS5 Name>
|  |  |  | External | 6-Other
Other