## Slide 1: A well written Project Charters minimizes confusion!
Having a well written Project Charter minimizes unwanted “noise” confusion and provides a clear scope definition!

## Slide 2: Have you experienced this?
What is the Scope of the project?
Who is the Project Manager?
When does the project start?
Pain Points?
Who are the project members?
Is there a budget?
Project End date?
Are the deliverables defined?
Governance structures
Do you have a steering Committee defined?
Stakeholders
Project Sponsor
Project Members
Leadership
Scrum Masters
Agile Coash
Development Team
Independent of Project Type
SW / HW / Org. Design
Waterfall / Agile

## Slide 3: Yes, I know the feeling…
How do I get out of this situation?
A well written Project Charter!
Read the Project Charter, if you have additional questions I am here to help…
Tell me about your pain points…

## Slide 4: What does a Project Charter Accomplish?
You don’t have to answer the same questions over and over and over and over and over and over and …
  Answer: Please read the Project Charter… (Consistent answer of the same question)
Clarity of the Scope (and what is NOT included)
Understanding of the Goals, Objective and Output (What does success look like?)
Required Resources and Funding
When the project is done (High level timeline)
Who are involved (Product Sponsor, Project Members, Scrum Masters, Steering Committee, Stakeholders, Etc.)
Reporting Structure, Format and Cadence
MINIMIZE THE UNWANTED NOICE

## Slide 5: What is a Project Charter?
In project management, a project charter, project definition, or project statement is a statement of the scope, objectives, and participants in a project. It provides a preliminary delineation of roles and responsibilities, outlines the project objectives, identifies the main stakeholders, and defines the authority of the project manager. It serves as a reference of authority for the future of the project.
A Project Charter, as per the PMBOK 5th Edition guide, can be defined as the document issued by the sponsor/initiator of the project that formally authorizes the existence of the project and provides the Project Manager with the authority to apply organizational resources to Project Activities.
According to the PMBOK Guide, “the project charter is an official document that formally authorizes a project or a phase and records the initial requirements that satisfy the stakeholders’ needs and expectations.”
Project Charter
Scope & Objectives
Goal & Output
Timelines
Sponsor & Participants
Key Stakeholders Needs
Roles & Responsibilities
Resources
Etc.

## Slide 6: What Is The Perfect Project Charter?
No such thing!
I am sharing some of my “ready to use” templates I have used the last few years executing Global Projects with sub-projects (Work Streams)
Use what you think is helpful and modify based on your type of project, environment, culture etc.
Templates: http://www.tmanthey.com/speaker.html

## Slide 7: Templates we will look at
Project Charter – Word Document
  1-Page Work Stream (sub-project) description – PPT
  Project Plan (Excel)
  Resource Plan (Excel)
  Risk Register (Excel)
  Action Points Register (Excel)
  Work Stream / Sub-project - Weekly Report (PPT)
  Project Weekly - Report (PPT)
Templates: http://www.tmanthey.com/speaker.html
Definition
Execution

## Slide 8: Project Charter - Template
Who is the Sponsor (Member of Steering Committee)
Introduction (What is this document about)
Executive Overview (goals, problem statement, background and reason for the project)
Project Scope and Included Work Streams (short description)
Resource Requirements (budget, staff, skills, facilities, locations, infrastructure, other etc.)
Critical Success Factors (what are the must have)
Critical Dependencies (Internal & External for each work stream)
Project Schedule and Timelines
Project Organization & Governance (Roles and Responsibilities, Steering Committee, Key Stakeholders)
Key Risks (Risk Level 15 and higher)
1-Page Work Stream Descriptions
Weekly Report Recipients (Stakeholders)
Reporting Format (templates)
Risk Matrix definition

## Slide 9: 1-Page Work Stream Description
Difficult to write on 1-page
If you (or the work stream lead / Sub-Project Manager) spend time creating this PPT, it will force you to really think of the scope and expected outcome!
The template is a “Staring Point” – update template based on your needs, culture, type of project etc.

## Slide 10: Work Stream: <NAME>
Description:
Text
Start Date:
End Date:
What does success look like:
Text
Text
Risks & Mitigation Actions:
Text
Text
Key Milestones / Deliverables & Stream Objective (SMART):
Text
Text
Resource Requirements (e.g. people/skills, technology, $$ etc.):
Text
Text
WS Lead: NN
Client WS SPOC:
Key Members: NN, NN, NN,
Dependencies and Assumptions:
Text
Text
Updated January 1st ,2019

## Slide 11: Work Stream: ITSM Governance
Description:
Designing and implementing an IT Service Management governance framework for client's ITSM organization. The roles that need to be assigned, responsibilities and accountabilities for each role and the meetings and councils to be established in order to operate and govern IT Processes, and ITSM technology within the IT organization. Align ITSM Governance framework with the new Client’s organization and utilize existing structures.
Start Date: dd-mmm-yyyy
End Date: dd-mmm-yyyy
What does success look like:
A defined ITSM Governance framework where people understand their roles and responsibilities.
Processes and technology is managed and governed both tactical and strategic to enable optimized service delivery.
Escalation path and thresholds are clearly defined and understood.
Strategic Process/Platform Roadmaps are being developed and managed for each IT process and ITSM technology (ITSM Platform).
ITSM Governance framework is implemented and aligned with Client’s new organization.
A central repository of process artifacts is available.
Risks & Mitigation Actions:
Delay in identification and assignment of Process / Technology Owners (Risk rating xx); Engage Client management to help with assignments and priority
Availability of assigned resources to attend required council meetings (Risk rating xx); Client management to communicate this is an important initiative
New organization not yet ready to get onboard the new ITSM governance (Risk Rating xx); Engage with the new General Manager
Key Milestones / Deliverables & Stream Objective (SMART):
Approved ITSM Governance framework (v1.0): dd-mmm-yyyy
Governance roles for processes and technology assigned and trained: dd-mmm-yyyy
Strategies Process Roadmaps developed for in scope processes: dd-mmm-yyyy
Strategic Platform Roadmap developed for ITSM tools: dd-mmm-yyyy
Governance roles for processes and ITSM platform trained: dd-mmm-yyyy
Handover of ITSM Governance Framework to SMO completed: dd-mmm-yyyy
Resource Requirements (e.g. people/skills, technology, $$ etc.):
Process Owners & Process Managers assigned for each process in scope
ITSM Platform and relevant tools have assigned owner(s)
Development of training material and execution of the training
Potential tools for process management (documentations, assessments audits etc.), part of the SMO work stream
WS Lead: NN
Client WS SPOC: NN
Key Members: NN, NN, NN,
Dependencies and Assumptions:
New organization in place with key roles assigned.
Process Owners to be assigned by Client
Technology / Platform Owner will be assigned by Client
Process Managers can be either Regional or Local
Any other required resources and roles are made available and assigned.
Updated January 1st ,2019
Example

## Slide 12: Resource Plan & Project Plan
To simplify I am using Excel to capture the Resources (staffing & rates) and the project plan (timeline and deliverables)
Most people know how to use Excel
It is difficult to share files for updates with other people if they don’t have the application installed e.g. MS Project

## Slide 13: Risk Register

## Slide 14: Action Points
Track Only project relevant Action Points (usually not for each work stream)
Review on a weekly basis
Key Action Points from Steering Committee

## Slide 15
Weekly Project Report creation:
Work Stream status (G-A-R color) copied to the Weekly Project Report
WS Project Status is copied to the Weekly Project Report. Only current information is added, last weeks information is removed.
Activities / Milestones Achieved copied to the Weekly Project Report
1
2
3
Project Reporting

## Slide 16: Questions?
Thorsten Manthey
Director, TCS
Thorsten@tmanthey.com
Templates: http://www.tmanthey.com/speaker.html
Project Charter template (word document)
1-page PPT describing each Work Stream/sub-projects (PowerPoint)
Resource Plan template (excel)
Risk Register temple & Action Points template (Excel)
Project Plan template (excel)
Weekly Work Stream Status report template (PPT)
Weekly Project Status report template (PPT)

## Slide 17: Thank You!
Don’t forget to provide a review of this presentation.