## Slide 1
The Practical WHO-HOW-WHAT Approach to Organizational Change Management
November 11-15, 2023 | Loews Royal Pacific | Orlando, FL

## Slide 2: WHY PEOPLE CHANGE MANAGEMENT?
Increase Probability of Project Success!
Manage employee Resistance to change
Improve speed of Adoption (how quick)
Increase Utilization (how many)
Optimize Proficiency (how well)

## Slide 3: IMPORTANCE OF CHANGE MANAGEMENT
Pace and frequency of change is increasing
Successful companies manage change well
Lead and manage change - most sought-after skills for both leaders and staff
ROI is directly related to the ability to lead and manage change
Leading change is a leadership skill with the highest Return on Investment

## Slide 4: PROCESS & TECHNOLOGY IS NOT ENOUGH
Perfectly Designed Process
+
Perfectly Designed Technology
If PEOPLE are not following the new process or not using the new tool, very little is changing!
=> Project Goal/Benefits/ROI is NOT realized

## Slide 5: USE A STRUCTURED APPROACH
People Change Management Approaches and Frameworks
ADKAR (Prosci)
Kotter’s 8 Steps
TCS’s Delivery Framework
Company-specific
People Change Management is much more than a communications & training plan!

## Slide 6: WHO - HOW - WHAT
WHO is impacted? Identify all groups that are being affected in any aspect by this change.
HOW are they impacted? What is changing?
What is not changing?
WHAT is needed? Identify the “actions” and how much people change management is needed for the impacted groups?

## Slide 7: THE THREE STEPS APPROACH
WHO
HOW
WHAT
After these three steps have been completed you can populate the Communication & Training (C&T) plan
Communication & Training Plan
STEP 1
STEP 2
STEP 3
Initial meeting
2nd validation meeting
Initial meeting
2nd validation meeting
Separate meetings with each group
Stick to the topic in each meeting

## Slide 8: 1. WHO IS AFFECTED?
Group | Contact | Description | # Members / Information
Identify all groups that are being affected in any aspect by the change
  Users of the new system, tool or processes being implemented
  Data consumers (e.g., reporting teams, finance teams, etc.)
  Managers
  Service Desk / 2nd level support / Technical support
  Developers / Designers
  HR / Finance / Procurement
  External Vendors / Partners
Remember to stick to the agenda - WHO Don’t start identifying HOW or WHAT

## Slide 9: 1. WHO IS AFFECTED?
Group | Contact | Description | # Members / Information
Service Desk | NN | Handles first level phone calls and tickets from customers. USA and India. | +90 customer service rep, multiple locations, 7x24x365
2nd level Support | NN | Handles escalated calls from the Service Desk. Two locations in the US | 15 support staff, two main locations, 7:00-21:00 business days
HR | NN | Supporting with the new roles and organizational changes | 5 HR people supporting the IT organization
Procurement | NN | Internal team plus a number of vendors | 2 people in procurement team. 3 major vendors
Finance | NN | Provides input to the new process via an automated feed from finance system | 2 VPs and their groups, total of 9 people
IT Managers | NN | All IT managers within the Infrastructure organization | All line managers 45 managers + their team, total ~800 people
Customers ordering services | NN | Anyone using the process. | USA: 1,500 people India: 200 people
Reporting team | NN | Extracting data from the system creating monthly reports | 6 individuals
Interfacing process teams | NN | Multiple interfacing processes | 5 process managers and 5 process owners
App. Development | NN | The team leader for the application development team X | 1 team lead and 10 people in the team in total
Example

## Slide 10: 2. HOW ARE THEY AFFECTED?
Affected Group | How are the affected? / What information do they need?
Ask the following questions for each of the affected groups identified
  What is changing for this group? What will be different?
  What is not changing for this group? What will be the same?
  What is driving the change, why are we changing?
  What is the Vision for the Enterprise / BU / Group?
  What does success look like for this Enterprise / BU / Group?
  WIIFM? (most likely different for each of the groups)
  Who is going to lose / gain what?
  What happens if we do NOT change?

## Slide 11: 2. HOW ARE THEY AFFECTED?
Affected Group | How are the affected? / What information do they need?
Service Desk | Emails, calls and chat to the Service Desk about the new tools/system/processes Knowledge about the new/updated/deleted tools/system/processes e.g. how to access, use, convert etc. How and where to escalate and route calls to 2nd level support Need to know when the tool/system/process has been released – Go Live date (staffing etc.) Implementation plans e.g. will there be a Hyper Care, phased roll-out etc. Information about Notifications, Approvals, Status Views, Escalations etc. in the new tool (Service Catalog) New support scripts to be developed / New FAQ and knowledge articles / Update existing information
2nd Level Support | Escalations to the 2nd Level Support about the new tools/system/processes How to escalate and route to external vendor Need to know when the tool/system/process has been released – Go Live date (staffing etc.) Implementation plans e.g. will there be a Hyper Care, phased roll-out etc. Information about Notifications, Approvals, Status Views, Escalations etc. in the new tool (Service Catalog) New support scripts to be developed / New FAQ and knowledge articles / Update existing information
Managers | New roles and organizational changes e.g. new and different skills required for staff Operational procedure changes, sourcing model will change (now outsourced) New / different reports or reporting structures Policy updates e.g. approvals, escalation etc.
Process Users | New tools and procures executing the process New or different skills required for the new role
Reporting team | New user interface when extracting data from the tool/system New data fields and values Mapping of old data to new data etc.
Example

## Slide 12: 3. WHAT ARE THE NEEDED ACTIONS?
Separate meeting with each affected group with key stakeholders
  Multiple meeting might be required
  One PPT slide for each group
Capture:
  What activity is needed
  The person / role responsible to develop the material / training, etc.
  The timing (a specific date or, for example, “1 week before go live”)
# | Actions for <Group Name> | Developer | Timing
1 |  |  | 
2 |  |  | 

## Slide 13: 3. WHAT ARE THE NEEDED ACTIONS?
# | Actions for Service Desk | Developer | Timing
1 | Live Demonstration of the End-to-end tool/system/process Train the trainer, live training (NN, NN, NN) Record demonstration and place on web page | Process Expert (NN) | 2 weeks before go live, 1 week before training session
2 | Information - Need to know when the tool/system/process has been released – Go Live date Email sent with release information (2 different emails) | Project Manager (NN) | 4 weeks before go live and also just days before Go Live
3 | Training and some hands-on exercise on how to use the tool/system/process and how to escalate any issues the user experiences to 2nd level support. Train the trainer, live training (NN, NN, NN must attend) Record session and place on web page | Process Expert (NN) | 2 week before Go Live and just after Go Live (two sessions)
4 | Information session (Live web meeting and Q&A) about Notifications, Approvals, Status Views, Escalations etc. in the tool/system/process Train the trainer, live training will deliver session | Train the Trainer person (NN) | 1 week before Go Live and just after Go Live (two sessions)
5 | Service Desk Activity – Develop new support scripts / New FAQ and knowledge articles / Update information that exist / review & update what information is on the web | Service Desk Manager | Prepare before go live and release at Go Live
6 |  |  | 
Example

## Slide 14: OVERALL TIMELINE
Usually takes 3-5 weeks* to complete
Start as soon as possible!
The data you collect is a SOLID START to developing an effective C&T plan
Remember, the C&T plan is a living document
As a facilitator you collect and update the information gathered and distribute prior to the second meeting.
Individual meetings scheduled with each of the affected groups to identify the actions (WHAT).
Week 1
Week 2
Week 3
Week 4
Week 5
WHO
HOW
WHAT
C&T Plan
*Example timeline; may increase per the complexity and size of the change across the organization

## Slide 15: POPULATE THE C&T PLAN
HOW
WHAT
Communication & Training Plan
https://tmanthey.com/speaker
You have captured a lot of solid data
WHO

## Slide 16: COMMUNICATION & TRAINING PLAN
Target Audience
Area / Process / Technology

## Slide 17: STAY WITHIN THE STEPS OF THE APPROACH
It is a very simple approach: WHO – HOW – WHAT, but very effective!
If you stick to the agenda, you will have solid data to populate the C&T plan.
  It is very easy to get off track by focusing on the “WHAT” too early – DON’T DO IT

## Slide 18: TOOLBOX & QUESTIONS?
Please don’t forget to complete an evaluation form!
Add to your tool box:
WHO-HOW-WHAT templates
Communication & Training Plan template
The WHO-HOW-WHAT Approach to Organizational Change Management (OCM)
This presentation
To download templates, go to: http://www.tmanthey.com/speaker.html
Thorsten Manthey
Engagement Director, TCS
(617) 513 0000
Thorsten.manthey@tcs.com
thorsten@tmanthey.com