## Slide 1: WHO - HOW - WHAT Communication & Training Needs
How to capture the data to develop a Communication and Training Plan
01/01/2019 Thorsten Manthey
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 2: Approach
WHO is impacted? Identify all targeted groups that are being impacted in any aspect by this change.
  Users of the new system, process, tools
  Data consumers e.g. reporting teams or finance teams
  Integrated systems, tool and processes (current and future)
  Managers – approvals, financials or managing the users that are impacted
  Service Desk / Helpdesk / Technical support
  Developers / designers of technical solutions
  External or third party vendors
HOW will each impacted group be impacted? For each impacted group above, answer the following questions.
  What is changing for this group? What will be different
  What is not changing for this group? What will be the same?
  What is driving the change, why are we changing? What does success look like?
  Who is going to lose/gain what?
  What happens if we (you) do NOT change?
WHAT communication and training is needed? Identify the “actions” and how much people change management is needed for the impacted group?
  Email communications, newsletters, web information, FAQs, training, lunch & learn, group meeting, virtual meeting, one-on-one coaching, detailed examples, role play etc.
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 3: WHO
Identify all targeted groups that are being impacted in any aspect by this change.
  Users of the new system, process, tools
  Data consumers e.g. reporting teams or finance teams
  Integrated systems, tool and processes (current and future)
  Managers – approvals, financials or managing the users that are impacted
  Service Desk / Helpdesk / Technical support
  Developers / designers of technical solutions
  External or third party vendors
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 4
Group | Contact | Description | # Members / Information
Help Desk | NN | Handles first level phone calls and tickets from customers | +90 customer service rep, multiple locations, 7x24x365
2nd level Support | NN | Handles escalated calls from the Help Desk | 15 support staff, one location, 7:00-21:00 business days
Managers | NN | Any manager | All line managers +800
Process Users | NN | Anyone using the process. | ~6,000, international
Reporting team | NN | Extracting data from the system creating monthly reports | 6 individuals
Interfacing processes | NN | Multiple interfacing processes | 5 process managers
Etc. |  |  | 
1 - IDENTIFY IMPACTED GROUPS - WHO
Example
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 5
Group | Contact | Description | # Members / Information
1 - IDENTIFY IMPACTED GROUPS - WHO
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 6: HOW
For each impacted groups, a number of questions should be answered to identify HOW they are impacted.
  What is changing for this group? What will be different
  What is not changing for this group? What will be the same?
  What is driving the change, why are we changing? What does success look like?
  Who is going to lose/gain what?
  What happens if we (you) do NOT change?
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 7
Impacted Group | How are they Impacted? / Information needed?
Help Desk | Emails and calls to the Help Desk about the new tools/system/processes How to escalate and route calls to 2nd level support Need to know when the tool/system/process has been released – Go Live date Demonstration of the new tool/system/process Information about Notifications, Approvals, Status Views, Escalations etc. in the new tool New support scripts to be developed / New FAQ and knowledge articles / Update existing information Etc.
2nd Level Support | Escalations to the 2nd Level Support about the new tools/system/processes How to escalate and route to external vendor Need to know when the tool/system/process has been released – Go Live date Training of the new tool/system/process Information about Notifications, Approvals, Status Views, Escalations etc. in the new tool New support scripts to be developed / New FAQ and knowledge articles / Update existing information Etc.
Managers | Information/Training: How to approve/reject Escalation, delegation, Approval notifications to managers (Manager page – onboarding information)
Process Users | New tools and procures executing the process
Reporting team | New user interface when extracting data from the tool/system New data fields and values
Interfacing processes | New delivery mechanisms for input/output
2 – Impact to each Group - HOW
Example
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 8
Impacted Group | How are they Impacted? / Information needed?
2 – Impact to each Group - HOW
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 9: WHAT
Identify the “actions” and how much people change management is needed for the impacted group?
  Email communications, newsletters, web information, FAQs, training, lunch & learn, group meeting, virtual meeting, one-on-one coaching, detailed examples, role play etc.
Tasks and Actions are identified to:
  Mitigate anticipated resistance
  Address unique attributes of each group
  Address historical or cultural barriers
  Leverage key influences
  Build awareness and desire to engage
  Provide needed knowledge and skills (training)
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 10: Instructions – Communication & Training needs
Identify tasks and actions for each identified targeted group of people or functional area.
Tasks and Actions are identified to:
Mitigate anticipated resistance
Address unique attributes of each group
Address historical or cultural barriers
Leverage key influences
Build awareness and desire to engage
Provide needed knowledge and skills (training)
Identify WHY this activity is important and WHEN it is needed
Awareness, Desire, Knowledge, Ability, Reinforcement
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com
Communication & Training Plan

## Slide 11
# | Help Desk | Why perform | Timing
1 | Live Demonstration of the End-to-end tool/system/process Train the trainer, live training (NN, NN, NN) Record demonstration and place on web page | Awareness of what is coming | Once – 2 weeks before go live, 1 week before training session
2 | Information - Need to know when the tool/system/process has been released – Go Live date Email sent with release information | Awareness | Just before Go Live
3 | Training and some hands on exercise on how to use the tool/system/process and how to escalate any issues the user experiences to 2nd level support. Train the trainer, live training (NN, NN, NN) Record session and place on web page | Knowledge | Twice – 1 week before Go Live and just after Go Live
4 | Information session (Live web meeting and Q$A) about Notifications, Approvals, Status Views, Escalations etc. in the tool/system/process Train the trainer, live training (Kevin Friel) | Knowledge | Twice – 1 week before Go Live and just after Go Live
5 | Help Desk Activity – Develop new support scripts / New FAQ and knowledge articles / Update information that exist / review & update what information is on the web | Knowledge | Prepare before go live and release at Go Live
6 |  |  | 
Contact: NN
3 - Identify Communication & Training Needs - WHAT
Example
(One slide for each identified target group)
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 12
# | ?? | Why perform | Timing
1 | Information: How will this be different from today To understand the data changes Etc. | Awareness | Before Go Live
2 | Live Demonstration - End to end demonstration… | Awareness | Once – 2 weeks before go live, 1 week before training session
3 | Training - hands on exercise | Knowledge | Twice - Just before Go Live and just after Go Live
4 | Job Aids: Develop job aids and FAQs | Knowledge | Develop before go live Update after go Live with additional information
5 |  |  | 
6 |  |  | 
Contact: NN
3 - Identify Communication & Training Needs - WHAT
Example
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com

## Slide 13
# |  | Why perform | Timing
1 |  |  | 
2 |  |  | 
3 |  |  | 
4 |  |  | 
5 |  |  | 
6 |  |  | 
7 |  |  | 
8 |  |  | 
9 |  |  | 
10 |  |  | 
11 |  |  | 
12 |  |  | 
13 |  |  | 
Contact:
3 - Identify Communication & Training Needs - WHAT
Thorsten Manthey - thorsten@tmanthey.com - www.tmathey.com