## HOP
Hour Of Prayer Manager
Six (6) Months
Task: | Date Started | Still in Progress | Date Completed | Completed | Comments
Selected Event Name/Theme | 2026-03-05 |  |  | ü
Write a description of the event
Select a Base Scripture
Selected Related Scripture
Create Focus Areas
Make a list of potential participants
Draft a program
Three (3) Months
Task: | Date Started | Still in Progress | Date Completed | Completed | Comments
Select Participants
Confirmed Participants Zoom Background (Tablet & Laptop only)
Send YouTube music to RevDee for YouTube approval if included in program
Set up a meeting with the AIF lead and RevDee
Send music to Sheila if a slide with music is needed
Send RevDee the PPT or document for the participants' meeting
Email Sheila the flyer information.
Two (2) Months
Task: | Date Started | Still in Progress | Date Completed | Completed | Comments
Approve the flyer
Meeting with AIF lead, RevDee, and participants
Meeting email to participants
Secure Admins: Spotlight & admitting; send program and meet
One (1) Months
Task: | Date Started | Still in Progress | Date Completed | Completed | Comments
Send participants the flyer and link
Follow up meeting with participants and admins