# Three Hour Tour Marketing Partnership Plan

South Shore LobsterFest 2026
Marshfield, Massachusetts

## Objectives

Increase attendance at South Shore LobsterFest

Promote LobsterFest as a premier South Shore summer event

Drive traffic to the official LobsterFest website

Cross-promote South Shore LobsterFest and Three Hour Tour

Showcase live music while supporting the overall festival experience

## 8 Weeks Before

Website: Add LobsterFest to Upcoming Shows and feature on homepage.

Social: Event announcement, tag LobsterFest, share official graphics.

Event Listings: Facebook Events and multiple platforms

## 6 Weeks Before

Share 'Why We're Excited' band video or content.

Begin countdown posts.

Highlight food, vendors, family activities, sponsors and attractions.

Publish website news post.

## 5 Weeks Before

Email Newsletter #1 – We're Heading to South Shore LobsterFest!

Link to official event website and encourage attendance.

## 4 Weeks Before

Reveal event merchandise (shirt, can cooler, hats).

Share rehearsal and behind-the-scenes content.

## 3 Weeks Before

Promote original music and invite fans to hear it live.

Three-week countdown posts.

## 2 Weeks Before

Email Newsletter #2 with event details, parking, schedule and merchandise.

Increase stories, reels and rehearsal updates.

## 1 Week Before

Daily countdown posts.

Band introductions.

Merchandise previews.

Festival reminders.

## Event Week

Feature LobsterFest on website homepage.

Daily social updates, setup, sponsors, food and festival atmosphere.

Share short Facebook Live / Instagram Stories and Reels.

## Event Day

Morning travel and festival updates.

Load-in and soundcheck photos.

Pre-show reminder.

Performance photos and short videos.

## After the Festival

Thank-you campaign recognizing organizers, volunteers, sponsors and attendees.

Highlight video and photo gallery.

Email recap and promote upcoming Three Hour Tour shows.

## Promotional Assets We'll Provide

Band logos

High-resolution photos

Social graphics

Website graphics

Promotional copy

Merchandise mockups

Press kit

Stage plot/input list

## Collaboration Opportunities

Cross-tagging social posts

Sponsor recognition

Joint giveaways (if desired)

Live social coverage

Photo/video assets for future promotions

## Success Metrics

Website traffic

Social engagement

Email performance

Merchandise sales

Video views

Spotify streaming after the event

## Closing Statement

Three Hour Tour is committed to making South Shore LobsterFest a success. We view this as a partnership and will actively promote the festival across our website, email newsletters and social media channels to help generate excitement, increase attendance and create a memorable experience for everyone involved.