## 2011-2012 Deliverables
IT PERFORMANCE MANAGEMENT DASHBOARD (2011-2012) ANALYTICS |  |  | August 31/2011
IT EXECUTIVE LEADERSHIP (ELS)
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator | Performance Metrics | OK
IT Governance Accountability Framework | 2011-04-01 | 2011-12-31 | In-Progress | 60% | G | % IT staff performing IT Governance; # Improvements completed
HR Performance Contract Alignment | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing HR Alignment; # Improvements completed
Executive Management (EM) Progress Status | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing EM Communications; # Improvements completed
Executive Management Presentation/Approvals | 2011-04-01 | 2012-03-31 | In-Progress | 60% | G | % IT staff performing EM Presentation; # Improvements completed
IT Policies and Procedures | 2011-04-01 | 2012-03-31 | In-Progress | 60% | G | % IT staff performing IT Policies; # Improvements completed
IT Operational Accountability Framework | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing IT Operations; # Improvements completed
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 56.67% | G
OPERATIONAL-SD | StartDate | End Date | Status | % Complete | Indicator
IT Contract Accountability Framework | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | %IT staff delivering Contract Management; # Improvements completed
IT Consultants NDA | 2011-04-01 | 2011-09-30 | In-Progress | 70% | Y | %IT staff delivering Consultants NDA; # Improvements completed
CIO Approvals-RFP | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | %IT staff delivering RFP Approvals; # Improvements completed
CIO Approvals-IT Infrastructure Impact | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | %IT staff delivering IT Infrastructure Impacts; # Improvements completed
IT Equipment Purchases Records | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G | %IT staff delivering IT Equipment Purchases; # Improvements completed
CIO Approvals-Business Projects | 2011-04-01 | 2011-09-30 | In-Progress | 90% | G | %IT staff delivering Business Projects Approvals; # Improvements completed
CIO Approvals-Technology Infrastructure Projects | 2011-04-01 | 2012-03-31 | Not-Started | 40% | G | %IT staff delivering IT Infrastructure Project Approvals; # Improvements completed
CIO Approvals-IT Equipment Expenditures | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | %IT staff delivering IT Equipment Expenses Approvals; # Improvements completed
CIO Approvals-IT Outsourced/Consulting Services | 2011-04-01 | 2011-08-31 | In-Progress | 80% | R | %IT staff delivering IT Contracting Approvals; # Improvements completed
CIO/CEO Approvals-Special Business Projects | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | %IT staff delivering Special Business Projects Approvals; # Improvements completed
CIO/CEO Approvals-Special Technology Projects | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G | %IT staff delivering Special Technology Projects Approvals; # Improvements completed
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 63.18% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
IT Management Policies Framework | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing IT Mgnt Policies; # Improvements completed
IT Management Procedures | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing IT Mgnt Procedures; # Improvements completed
IT Business Council Accountability Framework | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing IT Business Council Accountability; # Improvements completed
IT Compliance - Industry Performance Measures | 2011-04-01 | 2012-03-31 | Not-Started | 30% | Y | % IT staff performing IT Compliance-Industry; # Improvements completed
IT Benchmarking Metrics | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing IT Benchmarking Metrics; # Improvements completed
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 54% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator | % IT staff performing EM Relations/Feedback; # Improvements completed
Executive Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing BA Relations/Feedback; # Improvements completed
Business Areas Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing Vendors Relations/Feedback; # Improvements completed
Vendors Relations/Feedback | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing IT Outsourced Relations/Feedback; # Improvements completed
IT Outsourced Providers Relations/Feedback | 2011-10-01 | 2012-03-31 | Not-Started | 0% |  | % IT staff performing IT Contracted Resources Relations/Feedback; #Improvements completed
IT Contracted Resources Relations/Feedback | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT Capital Costs | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff managing IT Capital Costs; # Improvements completed
IT Operational Costs | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff managing IT Operational Costs Mgnt; # Improvements completed
IT Outsourced/Consulting Costs | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff managing IT Outsourced Costs Mgnt; # Improvements completed
IT Staff Costs | 2011-10-01 | 2012-03-31 | Not-Started | 0% |  | % IT staff managing IT Staff Costs Mgnt; # Improvements completed
Major Business Projects Costs | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff managing IT Business Projects Costs Mgnt; # Improvements completed
Major Technology Infrastructure Project Costs | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff managing IT Technology Costs Mgnt; # Improvements completed
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 56.67% | G
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing Client Satisfaction Surveys; # Improvements completed
IT Business Council Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff attending IT Business Council Meetings; # Improvements completed
Vendor Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing Vendor Satisfaction Surveys; # Improvements completed
IT Outsourced Providers Performance Measures | 2011-10-01 | 2012-03-31 | Not-Started | 0% |  | % IT staff performing IT Vendors Performance Measures; # Improvements completed
IT Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing IT Benchmarking surveys ; # Improvements completed
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
IT Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing Progress Reporting ; # Improvements completed
IT Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT Staff performing Staff Performance Contract ; # Improvements completed
Staff Learning/Growth | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing Learning/Growth sessions; # Improvements completed
Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing staff communications/meetings ; # Improvements completed
Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black | % IT staff performing staff retention/retraining, etc.; # Improvements completed
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT EXECUTIVE LEADERSHIP SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 55.36% | G
IT PLANNING & ADMINISTRATION SERVICES (PAS)
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT Strategic Planning Framework | 2011-04-01 | 2011-09-30 | In-Progress | 100% | Black | % IT staff performing IT Strategic Planning ; # Improvements completed
IT Operating Planning Framework | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing IT Operating Planning ; # Improvements completed
IT Budgeting Planning Framework | 2011-04-01 | 2011-12-31 | In-Progress | 30% | R | % IT staff performing IT Budget Planning ; # Improvements completed
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
OPERATIONAL-SD | Start Date | End Date | Status | % Complete | Indicator
IT Strategic and Operating Plan | 2011-04-01 | 2011-04-30 | In-Progress | 100% | Black | % IT staff delivering IT Strategic/Operating Plans ; # Improvements completed
IT Budget Plan | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G | % IT staff delivering IT Budget Plans ; # Improvements completed
IT Budget Plan status/ progress/forecasts | 2012-01-01 | 2012-03-31 | Not-Started | 0% |  | % IT staff delivering IT Budget Plan status ; # Improvements completed
IT Capital/Operating Expenditures Coding | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering IT Capital/Operating Expenditures ; # Improvements completed
IT Invoice Processing & Financial Admin | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering IT Invoicing ; # Improvements completed
IT Contract Agreement Status | 2011-04-01 | 2011-06-30 | In-Progress | 55% | Past Due | % IT staff delivering IT Contract Agreement Status ; # Improvements completed
Stakeholders Financial Support | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering Stakeholders Financial Support ; # Improvements completed
Finance and HR collaborations | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering Finance and HR Collaborations ; # Improvements completed
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48.12% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
IT Strategic/Operating Plan-Guidelines | 2011-04-01 | 2011-06-30 | In-Progress | 80% | Past Due | % IT staff performing IT Strategic/Operating Guidelines ; # Improvements completed
IT Financial Accountability Framework | 2011-04-01 | 2011-06-30 | In-Progress | 80% | Past Due | % IT staff performing IT Financial Accountability Framework ; # Improvements completed
IT Financial Guidelines | 2011-04-01 | 2011-06-30 | In-Progress | 90% | Past Due | % IT staff performing IT Financial Guidelines ; # Improvements completed
IT Financial Compliance-Financial Measures | 2011-04-01 | 2011-06-30 | In-Progress | 100% | Black | % IT staff performing IT Financial Measures ; # Improvements completed
IT Financial Benchmarking Metrics | 2011-04-01 | 2011-06-30 | In-Progress | 90% | Past Due | % IT staff performing IT Financial Benchmarking Metrics ; # Improvements completed
OPERATIONAL-SE Summary | 2011-04-01 | 2011-06-30 | In-Progress | 88% | Past Due
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
Financial Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff performing Financial Relations ; # Improvements completed
Vendors PAS Relations/Fedback | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff performing Vendors Relations ; # Improvements completed
IT Outsourced Providers PAS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff performing Outsourced Providers Relations ; # Improvements completed
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT Planning Costs | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff managing IT Capital Costs; # Improvements completed
IT Administration Costs | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff managing IT Operational Costs Mgnt; # Improvements completed
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
PAS Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing Client Satisfaction Surveys; # Improvements completed
PAS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff attending IT Business Council Meetings; # Improvements completed
PAS Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing Vendor Satisfaction Surveys; # Improvements completed
PAS IT Outsourced Providers Surveys | 2011-10-01 | 2012-03-31 | Not-Started | 0% |  | % IT staff performing IT Vendors Performance Measures; # Improvements completed
PAS Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing PAS Benchmarking surveys ; # Improvements completed
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
PAS Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing Progress Reporting ; # Improvements completed
PAS Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT Staff performing Staff Performance Contract ; # Improvements completed
PAS Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing Learning/Growth sessions; # Improvements completed
PAS Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing staff communications/meetings ; # Improvements completed
PAS Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 50% | Past Due | % IT staff performing PAS retention/retraining ; # Improvements completed
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 51% | G
IT PLANNING & ADMINISTRATION SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 52.16% | G
IT ENTERPRISE ARCHITECTURE SERVICES (EAS)
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT Enterprise Architecture Framework | 2011-04-01 | 2011-09-30 | In-Progress | 25% | R | % IT staff performing IT Enterprise Architecture ; # Improvements completed
Information Management Framework | 2011-04-01 | 2011-09-30 | In-Progress | 25% | R | % IT staff performing IM Framework ; # Improvements completed
Technology Project Management Governance | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff performing Technology PM Governance ; # Improvements completed
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
OPERATIONAL-SD | Budget | YTD Actual | Status | % Complete | Indicator
Business Systems Planning Support | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff delivering Business Systems Planning; # Improvements completed
Business Case/Architecture Support | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff delivering Architecture Business Case; # Improvements completed
IT Enterprise Architectures | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff delivering IT Enterprise Architecture ; # Improvements completed
IT Enterprise Architecture Standards | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff delivering IT Enterprise Architecture Stds ; # Improvements completed
IT Security Plans | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff delivering IT Security Plans ; # Improvements completed
IT Security Implementation | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff delivering IT Security ; # Improvements completed
Innovative Communications tools | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff delivering Communications Tools ; # Improvements completed
Technology Projects Contract Management | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff delivering Technology Projects CM; # Improvements completed
Technology Program/Project Management | 2011-04-01 | 2011-09-30 | In-Progress | 90% | G | % IT staff delivering Technology Projects PM ; # Improvements completed
IT Productivity Tools and Framework | 2011-04-01 | 2011-09-30 | In-Progress | 40% | R | % IT staff delivering IT Productivity Tools ; # Improvements completed
Technology Infrastructure Delivery/Support | 2011-04-01 | 2011-09-30 | In-Progress | 35% | R | % IT staff delivering Technology Infrastructure ; # Improvements completed
Technology Research/Trends | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff delivering Technology Research ; # Improvements completed
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 41.25% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
Technology Infrastructure Project Plan QA | 2011-04-01 | 2011-06-30 | In-Progress | 75% | Past Due | % IT staff performing Technology Projects QA ; # Improvements completed
IT Security and Privacy Compliance/Approval | 2011-04-01 | 2011-07-31 | In-Progress | 80% | Past Due | % IT staff performing Technlology Projects Compliance # Improvements completed
Infrastructure Projects Financial Measures | 2011-04-01 | 2011-09-30 | In-Progress | 60% | R | % IT staff performing Infrastructure Projects Measures; # Improvements completed
Technology Infrastructure Compliance | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing IT Infrastructure Compliance; # Improvements completed
Technology Infrastructure Optimization | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing IT Infrastructure Optimization; # Improvements completed
Technology Infrastructure Benchmarking | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing IT Infrastructure Benchmarking; # Improvements completed
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 60.83% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
EAS Client Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 100% | Black | % IT staff performing Client Feedback; # Improvements completed
Vendors EAS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing Vendors Feedback; # Improvements completed
IT Outsourced Providers EAS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff performing IT Service Providers Feedback; # Improvements completed
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT Infrastructure Project Costs | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff managing IT Infrastructure Project Costs; # Improvements completed
IT Enterprise Architecture Costs | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff managing IT Enterprise Architecture Costs; # Improvements completed
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
EAS Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing Client Satisfaction Surveys ; # Improvements completed
EAS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing EAS Committ Meetings; # Improvements completed
EAS Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing Vendors Satisfaction Surveys; # Improvements completed
EAS IT Outsourced Providers Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing IT Service Providers Surveys; # Improvements completed
EAS Benchmarking Surveys/Results | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing EAS Benchmarking Surveys ; # Improvements completed
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
EAS IT Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing Progress Reporting ; # Improvements completed
EAS IT Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT Staff performing Staff Performance Contract ; # Improvements completed
EAS Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing Learning/Growth sessions; # Improvements completed
EAS Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing staff communications/meetings ; # Improvements completed
EAS Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black | % IT staff performing EAS retention/retraining; # Improvements completed
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT ENTERPRISE ARCHITECTURE | 2011-04-01 | 2012-03-31 | In-Progress | 44.73% | G
IT PROJECT PORTIFOLIO MANAGEMENT (PPM)
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT PPM Governance Framework | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G | % IT staff performing PPM Governance ; # Improvements completed
IT PPM Innovative Technical Direction | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff performing PPM Innovations ; # Improvements completed
PPM Projects Outsourcing Framework | 2011-04-01 | 2011-09-30 | In-Progress | 65% | Y | % IT staff performing PPM Outsourcing Strategies ; # Improvements completed
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 53.33% | G
OPERATIONAL-SD | Start Date | End Date | Status | % Complete | Indicator
IT Business Projects Monitoring/Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff delivering IT Business Projects Progress; # Improvements completed
Innovative PMO Communications tools | 2011-04-01 | 2011-09-30 | In-Progress | 75% | Y | % IT staff delivering PMO Tools ; # Improvements completed
IT PPM Productivity Tools and Processes | 2011-04-01 | 2012-09-30 | In-Progress | 40% | G | % IT staff delivering IT Sproductivity Processes ; # Improvements completed
PPM Systems and Regression Testing | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff delivering System Testing ; # Improvements completed
IT Project Management /Delivery | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff delivering IT Project Management ; # Improvements completed
IT Business Projects RFP/Contracts | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff delivering Business Projects RFPs; # Improvements completed
IT Business Projects Program/Projects Plan | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff delivering Business Projects Program/Project Plans ; # Improvements completed
IT Business Project Architecture/Design | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff delivering Business Projects Architecture ; # Improvements completed
IT PMO Support | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT PMO Support; # Improvements completed
IT Business Project Requirements Specifications | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff delivering Business Projects Specifications ; # Improvements completed
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 42% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
Business Projects Plan QA | 2011-04-01 | 2011-06-30 | In-Progress | 75% | Past Due | % IT staff performing Business Projects Plan QA ; # Improvements completed
IT Project Management Compliance/Approval | 2011-04-01 | 2011-07-31 | In-Progress | 80% | Past Due | % IT staff performing PM Compliance; # Improvements completed
Business Projects Financial Measures | 2011-04-01 | 2011-09-30 | In-Progress | 60% | R | % IT staff performing Business Projects Financial Measures; # Improvements completed
PMO Compliance | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing PMO Compliance ; # Improvements completed
Project Management Optimization | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing PM Optimization ; # Improvements completed
Business Projects Benchmarking Metrics | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing Business Projects Benchmarking ; # Improvements completed
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 60.83% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
PPM Client Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 100% | Black | % IT staff performing Client Feedback ; # Improvements completed
Vendors PPM Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing Vendors Innovations ; # Improvements completed
IT Outsourced Providers PPM Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff performing Service Providers Feedback ; # Improvements completed
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT Business Project Costs | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff managing Business Project Costs; # Improvements completed
IT PPM Costs | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff managing IT PPM Costs; # Improvements completed
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
PPM Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing Client Satisfaction Surveys; # Improvements completed
PPM Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff attending PPM Committee Meetings; # Improvements completed
PPM Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing Vendor Satisfaction Surveys; # Improvements completed
PPM IT Outsourced Providers Surveys | 2011-10-01 | 2012-03-31 | Not-Started | 0% |  | % IT staff performing IT Vendors Performance Measures; # Improvements completed
PPM Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing PPM Benchmarking surveys; # Improvements completed
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
PPM IT Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing Progress Reporting ; # Improvements completed
PPM IT Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT Staff performing Staff Performance Contract ; # Improvements completed
PPM Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing Learning/Growth sessions; # Improvements completed
PPM Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing staff communications/meetings ; # Improvements completed
PPM Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black | % IT staff performing PPM Benchmarking/retention/retraining ; # Improvements completed
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT PROJECT PORTIFOLIO SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.02% | G
IT APPLICATIONS MANAGEMENT SERVICES (AMS)
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT AMS Governance Framework | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G | % IT staff performing AMS Governance ; # Improvements completed
IT AMS Innovative Technical Direction | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff performing AMS Innovations ; # Improvements completed
AMS Outsourcing Framework | 2011-04-01 | 2011-09-30 | In-Progress | 65% | Y | % IT staff performing AMS Outsourcing Strategies ; # Improvements completed
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 53.33% | G
OPERATIONAL-SD | Budget | YTD Actual | Status | % Complete | Indicator
AMS Services & SLA mgmt | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering IT AMS Services & SLA Mgnt ; # Improvements completed
AMS SLA Support | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering AMS SLA Support; # Improvements completed
Web-Services Policy/Strategy Development | 2011-04-01 | 2011-06-30 | In-Progress | 50% | Past Due | % IT staff delivering Web-Services Strategy; # Improvements Completed
Innovative Communications tools | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering AMS Communications Tools; # Improvements completed
AMS RFP/Contract Mgnt | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering AMS RFP/Contract Mgnt; # Improvements completed
AMS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering AMS Committee Meetings; # Improvements completed
AMS Migrations | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering AMS Migrations; # Improvements completed
AMS Change Management | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering AMS Change Mgnt; # Improvements completed
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 45.62% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
AMS QA | 2011-04-01 | 2011-06-30 | In-Progress | 75% | Past Due | % IT staff performing AMS QA ; # Improvements completed
AMS Compliance/Approval | 2011-04-01 | 2011-07-31 | In-Progress | 80% | Past Due | % IT staff performing AMS Compliance; # Improvements completed
AMS Financial Measures | 2011-04-01 | 2011-09-30 | In-Progress | 60% | R | % IT staff performing AMS Financial Measures; # Improvements completed
AMS SLA Compliance | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing AMS SLA Compliance ; # Improvements completed
AMS Optimization | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing AMS Optimization ; # Improvements completed
AMS Benchmarking Metrics | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing AMS Benchmarking ; # Improvements completed
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 60.83% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
AMS Client Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 100% | Black | % IT staff performing Client Feedback ; # Improvements completed
Vendors AMS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing Vendors Innovations ; # Improvements completed
IT Outsourced Providers AMS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff performing Service Providers Feedback ; # Improvements completed
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT AMS Innovative Initiative Costs-Capital | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G | % IT staff managing AMS Capital Costs; # Improvements completed
IT AMS Operating Costs | 2011-04-01 | 2012-03-31 | In-Progress | 15% | R | % IT staff managing AMS Operating Costs; # Improvements completed
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 32.5% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
AMS Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing Client Satisfaction Surveys; # Improvements completed
AMS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff attending AMS Committee Meetings; # Improvements completed
AMS Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing Vendor Satisfaction Surveys; # Improvements completed
AMS IT Outsourced Providers Surveys | 2011-10-01 | 2012-03-31 | Not-Started | 0% |  | % IT staff performing IT Vendors Performance Measures; # Improvements completed
AMS Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing AMS Benchmarking surveys ; # Improvements completed
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
AMS Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing Progress Reporting ; # Improvements completed
AMS Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT Staff managing Staff Performance Contract ; # Improvements completed
AMS Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff attending Learning/Growth sessions; # Improvements completed
AMS Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing staff communications/meetings ; # Improvements completed
AMS Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black | % IT staff performing AMS retention/retraining ; # Improvements completed
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT APPLICATIONS SERVICES SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.9% | G
IT OPERATIONS SERVICES (TOS)
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
TOS Governance Framework | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G | % IT staff performing TOS Governance ; # Improvements completed
TOS Innovative Technical Direction | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff performing TOS Innovations ; # Improvements completed
TOS Outsourcing Framework | 2011-04-01 | 2011-09-30 | In-Progress | 65% | Y | % IT staff performing TOS Outsourcing Strategies ; # Improvements completed
TOS Data Centre Technology Direction | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff performing TOS Data Centre Technology Direction ; # Improvements completed
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 51.25% | G
OPERATIONAL-SD | Budget | YTD Actual | Status | % Complete | Indicator
TOS Services & SLA Management | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering IT TOS Services & SLA Mgnt ; # Improvements completed
TOS SLA Support | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering TOS SLA Support; # Improvements completed
Data Centre Policy/Strategy Development | 2011-04-01 | 2011-06-30 | In-Progress | 50% | Past Due | % IT staff delivering Dat Centre Strategy; # Improvements Completed
Innovative Communications tools | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering TOS Communications Tools; # Improvements completed
TOS RFP/Contract Mgnt | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering AMS RFP/Contract Mgnt; # Improvements completed
TOS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering TOS Committee Meetings; # Improvements completed
TOS Migrations | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering TOS Migrations; # Improvements completed
TOS Change Management | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering TOS Change Mgnt; # Improvements completed
Managed Operations Support | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering TOS Managed Operations; # Improvements completed
Technology Infrastructure Delivery | 2011-04-01 | 2011-06-30 | In-Progress | 50% | Past Due | % IT staff delivering Technology Infrastructure Delivery; # Improvements completed
TOS Innovative Productivity tools | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G | % IT staff delivering productivity tools; # Improvements completed
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 45.91% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
TOS QA | 2011-04-01 | 2011-06-30 | In-Progress | 75% | Past Due | % IT staff performing Business Projects Plan QA ; # Improvements completed
TOS Compliance/Approval | 2011-04-01 | 2011-07-31 | In-Progress | 80% | Past Due | % IT staff performing PM Compliance; # Improvements completed
TOS Financial Measures | 2011-04-01 | 2011-09-30 | In-Progress | 60% | R | % IT staff performing Business Projects Financial Measures; # Improvements completed
TOS SLA Compliance | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing PMO Compliance ; # Improvements completed
TOS Asset Optimization | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing PM Optimization ; # Improvements completed
TOS Benchmarking Metrics | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing Business Projects Benchmarking ; # Improvements completed
IT Infrastructure Purchases Approvals | 2011-04-01 | 2011-05-31 | In-Progress | 75% | Past Due | % IT staff performing IT Infrastructure Purchases Approvals ; # Improvements completed
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 62.86% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
TOS Client Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 100% | Black | % IT staff performing Client Feedback ; # Improvements completed
Vendors TOS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G | % IT staff performing Vendors Feedback ; # Improvements completed
IT Outsourced Providers TOS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y | % IT staff performing Service Providers Feedback ; # Improvements completed
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT TOS Innovative Initiative Costs-Capital | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G | % IT staff managing TOS Capital Costs; # Improvements completed
IT TOS Operating Costs | 2011-04-01 | 2012-03-31 | In-Progress | 15% | R | % IT staff managing TOS Operating Costs; # Improvements completed
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 32.5% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
TOS Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff performing Client Satisfaction Surveys; # Improvements completed
TOS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y | % IT staff attending PPM Committee Meetings; # Improvements completed
TOS Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G | % IT staff performing Vendor Satisfaction Surveys; # Improvements completed
TOS IT Outsourced Providers Surveys | 2011-10-01 | 2012-03-31 | Not-Started | 0% |  | % IT staff performing IT Vendors Performance Measures; # Improvements completed
TOS Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing TOS Benchmarking surveys; # Improvements completed
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
TOS Staff Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black | % IT staff performing Progress Reporting ; # Improvements completed
TOS Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT Staff managing Staff Performance Contract ; # Improvements completed
TOS Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff attending Learning/Growth sessions; # Improvements completed
TOS Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y | % IT staff performing staff communications/meetings ; # Improvements completed
TOS Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black | % IT staff performing TOS retention/retraining ; # Improvements completed
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT OPERATIONS SERVICES SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.93% | G

## Overview
IT PERFORMANCE DASHBOARD (2011-2012) ANALYTICS
IT EXEC LEADERSHIP & RELATION SUMMARY | 55.36%
IT PLANNING & ADMIN SUMMARY | 52.16%
IT ARCHITECT & INNOVATION SUMMARY | 44.73%
IT PROJECT PORTFOLIO SUMMARY | 50.02%
IT APPLICATIONS AND SERVICES SUMMARY | 50.9%
IT OPERATIONS SERVICES (TOS) SUMMARY | 50.93%
TOTAL % Complete | 50.68%
IT DASHBOARD (2011-2012) ANALYTICS | Start Date | End Date | Status | % Complete | Indicator
IT EXEC LEADERSHIP & RELATION SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 55.36% | Past Due
IT PLANNING & ADMIN RELATION SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 52.16% | Past Due
IT ARCHITECT & INNOVATION RELATION SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 44.73% | Past Due
IT PROJECT PORTIFOLIO SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.02% | Past Due
IT APPLICATIONS AND SERVICES SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.9% | Past Due
IT OPERATIONS SERVICES (TOS) SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.93% | Past Due
TOTAL % Complete | 2011-04-01 | 2012-03-31 | In-Progress | 50.68% | Past Due
64% Managed Operations and 36% Projects (Forester Research Ideal Utilization range)
Formulas:
Start Date = SMALL(B16:[Start Date, row above],1)
End Date = LARGE(C16:[End Date, row above],1)

## EXEC
IT EXEC LEADERSHIP & RELATIONSHIP Mgmt
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT Governance Accountability Framework | 2011-04-01 | 2011-12-31 | In-Progress | 60% | G
HR Performance Contract Alignment | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
Executive Management (EM) Progress Status | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
Executive Management Presentation/Approvals | 2011-04-01 | 2012-03-31 | In-Progress | 60% | G
IT Policies and Procedures | 2011-04-01 | 2012-03-31 | In-Progress | 60% | G
IT Operational Accountability Framework | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 56.67% | G
OPERATIONAL-SD | StartDate | End Date | Status | % Complete | Indicator
IT Contract Accountability Framework | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
IT Consultants NDA | 2011-04-01 | 2011-09-30 | In-Progress | 70% | Y
CIO Approvals-RFP | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
CIO Approvals-IT Infrastructure Impact | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
IT Equipment Purchases Records | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G
CIO Approvals-Business Projects | 2011-04-01 | 2011-09-30 | In-Progress | 90% | G
CIO Approvals-Technology Infrastructure Projects | 2011-04-01 | 2012-03-31 | Not-Started | 40% | G
CIO Approvals-IT Equipment Expenditures | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
CIO Approvals-IT Outsourced/Consulting Services | 2011-04-01 | 2011-08-31 | In-Progress | 80% | R
CIO/CEO Approvals-Special Business Projects | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
CIO/CEO Approvals-Special Technology Projects | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 63.18% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
IT Management Policies Framework | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
IT Management Procedures | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
IT Business Council Accountability Framework | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
IT Compliance - Industry Performance Measures | 2011-04-01 | 2012-03-31 | Not-Started | 30% | Y
IT Benchmarking Metrics | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 54% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
Executive Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
Business Areas Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
Vendors Relations/Feedback | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
IT Outsourced Providers Relations/Feedback | 2011-10-01 | 2012-03-31 | Not-Started | 0%
IT Contracted Resources Relations/Feedback | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT Capital Costs | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
IT Operational Costs | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
IT Outsourced/Consulting Costs | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
IT Staff Costs | 2011-10-01 | 2012-03-31 | Not-Started | 0%
Major Business Projects Costs | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
Major Technology Infrastructure Project Costs | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 56.67% | G
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
IT Business Council Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
Vendor Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
IT Outsourced Providers Performance Measures | 2011-10-01 | 2012-03-31 | Not-Started | 0%
IT Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
IT Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
IT Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Staff Learning/Growth | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT EXECUTIVE LEADERSHIP SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 55.36% | G

## PAS
IT PLANNING & ADMIN RELATIONSHIP Mgmt
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT Strategic Planning Framework | 2011-04-01 | 2011-09-30 | In-Progress | 100% | Black
IT Operating Planning Framework | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
IT Budgeting Planning Framework | 2011-04-01 | 2011-12-31 | In-Progress | 30% | R
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
OPERATIONAL-SD | Start Date | End Date | Status | % Complete | Indicator
IT Strategic and Operating Plan | 2011-04-01 | 2011-04-30 | In-Progress | 100% | Black
IT Budget Plan | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G
IT Budget Plan status/ progress/forecasts | 2012-01-01 | 2012-03-31 | Not-Started | 0%
IT Capital/Operating Expenditures Coding | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
IT Invoice Processing & Financial Admin | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
IT Contract Agreement Status | 2011-04-01 | 2011-06-30 | In-Progress | 55% | Past Due
Stakeholders Financial Support | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
Finance and HR collaborations | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48.12% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
IT Strategic/Operating Plan-Guidelines | 2011-04-01 | 2011-06-30 | In-Progress | 80% | Past Due
IT Financial Accountability Framework | 2011-04-01 | 2011-06-30 | In-Progress | 80% | Past Due
IT Financial Guidelines | 2011-04-01 | 2011-06-30 | In-Progress | 90% | Past Due
IT Financial Compliance-Financial Measures | 2011-04-01 | 2011-06-30 | In-Progress | 100% | Black
IT Financial Benchmarking Metrics | 2011-04-01 | 2011-06-30 | In-Progress | 90% | Past Due
OPERATIONAL-SE Summary | 2011-04-01 | 2011-06-30 | In-Progress | 88% | Past Due
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
Financial Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
Vendors PAS Relations/Fedback | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
IT Outsourced Providers PAS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT Planning Costs | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
IT Administration Costs | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
PAS Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
PAS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
PAS Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
PAS IT Outsourced Providers Surveys | 2011-10-01 | 2012-03-31 | Not-Started | 0%
PAS Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
PAS Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
PAS Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
PAS Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
PAS Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
PAS Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 50% | Past Due
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 51% | G
IT PLANNING & ADMINISTRATION SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 52.16% | G

## EAS
IT ARCHITECT & INNOVATION mgmt
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT Enterprise Architecture Framework | 2011-04-01 | 2011-09-30 | In-Progress | 25% | R
Information Management Framework | 2011-04-01 | 2011-09-30 | In-Progress | 25% | R
Technology Project Management Governance | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
OPERATIONAL-SD | Budget | YTD Actual | Status | % Complete | Indicator
Business Systems Planning Support | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
Business Case/Architecture Support | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
IT Enterprise Architectures | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
IT Enterprise Architecture Standards | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
IT Security Plans | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
IT Security Implementation | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
Innovative Communications tools | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Technology Projects Contract Management | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Technology Program/Project Management | 2011-04-01 | 2011-09-30 | In-Progress | 90% | G
IT Productivity Tools and Framework | 2011-04-01 | 2011-09-30 | In-Progress | 40% | R
Technology Infrastructure Delivery/Support | 2011-04-01 | 2011-09-30 | In-Progress | 35% | R
Technology Research/Trends | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 41.25% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
Technology Infrastructure Project Plan QA | 2011-04-01 | 2011-06-30 | In-Progress | 75% | Past Due
IT Security and Privacy Compliance/Approval | 2011-04-01 | 2011-07-31 | In-Progress | 80% | Past Due
Infrastructure Projects Financial Measures | 2011-04-01 | 2011-09-30 | In-Progress | 60% | R
Technology Infrastructure Compliance | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Technology Infrastructure Optimization | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Technology Infrastructure Benchmarking | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 60.83% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
EAS Client Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 100% | Black
Vendors EAS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Outsourced Providers EAS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT Infrastructure Project Costs | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
IT Enterprise Architecture Costs | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
EAS Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
EAS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
EAS Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
EAS IT Outsourced Providers Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
EAS Benchmarking Surveys/Results | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
EAS IT Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
EAS IT Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
EAS Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
EAS Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
EAS Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT ENTERPRISE ARCHITECTURE | 2011-04-01 | 2012-03-31 | In-Progress | 44.73% | G

## PPM
IT PROJECT PORTIFOLIO mgmt
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT PPM Governance Framework | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G
IT PPM Innovative Technical Direction | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
PPM Projects Outsourcing Framework | 2011-04-01 | 2011-09-30 | In-Progress | 65% | Y
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 53.33% | G
OPERATIONAL-SD | Start Date | End Date | Status | % Complete | Indicator
IT Business Projects Monitoring/Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
Innovative PMO Communications tools | 2011-04-01 | 2011-09-30 | In-Progress | 75% | Y
IT PPM Productivity Tools and Processes | 2011-04-01 | 2012-09-30 | In-Progress | 40% | G
PPM Systems and Regression Testing | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Project Management /Delivery | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Business Projects RFP/Contracts | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Business Projects Program/Projects Plan | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Business Project Architecture/Design | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT PMO Support | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Business Project Requirements Specifications | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 42% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
Business Projects Plan QA | 2011-04-01 | 2011-06-30 | In-Progress | 75% | Past Due
IT Project Management Compliance/Approval | 2011-04-01 | 2011-07-31 | In-Progress | 80% | Past Due
Business Projects Financial Measures | 2011-04-01 | 2011-09-30 | In-Progress | 60% | R
PMO Compliance | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Project Management Optimization | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
Business Projects Benchmarking Metrics | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 60.83% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
PPM Client Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 100% | Black
Vendors PPM Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Outsourced Providers PPM Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT Business Project Costs | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
IT PPM Costs | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
PPM Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
PPM Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
PPM Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
PPM IT Outsourced Providers Surveys | 2011-10-01 | 2012-03-31 | In-Progress | 0%
PPM Benchmarking Surveys/Results |  | 2011-06-30 | In-Progress | 100% | Black
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
PPM IT Progress Reporting | 2011-04-01 | 2011-06-30 | In-Progress | 100% | Black
PPM IT Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
PPM Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
PPM Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
PPM Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT PROJECT PORTIFOLIO SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.02% | G

## AMS
IT APPLICATIONS & SERVICES mgmt
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
IT AMS Governance Framework | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G
IT AMS Innovative Technical Direction | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
AMS Outsourcing Framework | 2011-04-01 | 2011-09-30 | In-Progress | 65% | Y
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 53.33% | G
OPERATIONAL-SD | Budget | YTD Actual | Status | % Complete | Indicator
AMS Services & SLA mgmt | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
AMS SLA Support | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
Web-Services Policy/Strategy Development | 2011-04-01 | 2011-06-30 | In-Progress | 50% | Past Due
Innovative Communications tools | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
AMS RFP/Contract Mgnt | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
AMS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
AMS Migrations | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
AMS Change Management | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 45.62% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
AMS QA | 2011-04-01 | 2011-06-30 | In-Progress | 75% | Past Due
AMS Compliance/Approval | 2011-04-01 | 2011-07-31 | In-Progress | 80% | Past Due
AMS Financial Measures | 2011-04-01 | 2011-09-30 | In-Progress | 60% | R
AMS SLA Compliance | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
AMS Optimization | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
AMS Benchmarking Metrics | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 60.83% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
AMS Client Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 100% | Black
Vendors AMS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Outsourced Providers AMS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT AMS Innovative Initiative Costs-Capital | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G
IT AMS Operating Costs | 2011-04-01 | 2012-03-31 | In-Progress | 15% | R
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 32.5% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
AMS Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
AMS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
AMS Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
AMS IT Outsourced Providers Surveys | 2011-10-01 | 2012-03-31 | Not-Started | 0%
AMS Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
AMS Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
AMS Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
AMS Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
AMS Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
AMS Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT APPLICATIONS SERVICES SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.9% | G

## TOS
IT OPERATIONS SERVICES mgmt
OPERATIONAL-FM | Start Date | End Date | Status | % Complete | Indicator
TOS Governance Framework | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G
TOS Innovative Technical Direction | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
TOS Outsourcing Framework | 2011-04-01 | 2011-09-30 | In-Progress | 65% | Y
TOS Data Centre Technology Direction | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
OPERATIONAL-FM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 51.25% | G
OPERATIONAL-SD | Budget | YTD Actual | Status | % Complete | Indicator
TOS Services & SLA Management | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
TOS SLA Support | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
Data Centre Policy/Strategy Development | 2011-04-01 | 2011-06-30 | In-Progress | 50% | Past Due
Innovative Communications tools | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
TOS RFP/Contract Mgnt | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
TOS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
TOS Migrations | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
TOS Change Management | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
Managed Operations Support | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
Technology Infrastructure Delivery | 2011-04-01 | 2011-06-30 | In-Progress | 50% | Past Due
TOS Innovative Productivity tools | 2011-04-01 | 2012-03-31 | In-Progress | 45% | G
OPERATIONAL-SD Summary | 2011-04-01 | 2012-03-31 | In-Progress | 45.91% | G
OPERATIONAL-SE | Start Date | End Date | Status | % Complete | Indicator
TOS QA | 2011-04-01 | 2011-06-30 | In-Progress | 75% | Past Due
TOS Compliance/Approval | 2011-04-01 | 2011-07-31 | In-Progress | 80% | Past Due
TOS Financial Measures | 2011-04-01 | 2011-09-30 | In-Progress | 60% | R
TOS SLA Compliance | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
TOS Asset Optimization | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
TOS Benchmarking Metrics | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
IT Infrastructure Purchases Approvals | 2011-04-01 | 2011-05-31 | In-Progress | 75% | Past Due
OPERATIONAL-SE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 62.86% | G
OPERATIONAL-RM | Start Date | End Date | Status | % Complete | Indicator
TOS Client Management Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 100% | Black
Vendors TOS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 40% | G
IT Outsourced Providers TOS Relations/Feedback | 2011-04-01 | 2012-03-31 | In-Progress | 25% | Y
OPERATIONAL-RM Summary | 2011-04-01 | 2012-03-31 | In-Progress | 55% | G
FINANCIAL | Start Date | End Date | Status | % Complete | Indicator
IT TOS Innovative Initiative Costs-Capital | 2011-04-01 | 2011-12-31 | In-Progress | 50% | G
IT TOS Operating Costs | 2011-04-01 | 2012-03-31 | In-Progress | 15% | R
FINANCIAL Summary | 2011-04-01 | 2012-03-31 | In-Progress | 32.5% | Y
CUSTOMER | Start Date | End Date | Status | % Complete | Indicator
TOS Client Relationships/Satisfaction Surveys | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
TOS Committee Meetings | 2011-04-01 | 2012-03-31 | In-Progress | 30% | Y
TOS Vendors Relationships/Satisfaction Surveys | 2011-04-01 | 2011-09-30 | In-Progress | 80% | G
TOS IT Outsourced Providers Surveys | 2011-10-01 | 2012-03-31 | Not-Started | 0%
TOS Benchmarking Surveys/Results | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
CUSTOMER Summary | 2011-04-01 | 2012-03-31 | In-Progress | 48% | G
EMPLOYEE | Start Date | End Date | Status | % Complete | Indicator
TOS Staff Progress Reporting | 2011-04-01 | 2011-06-30 | Complete | 100% | Black
TOS Staff Performance Contract | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
TOS Staff Learning/Growth Reporting | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
TOS Staff Meetings/Communications | 2011-04-01 | 2012-03-31 | In-Progress | 35% | Y
TOS Staff Retention/Retraining/Reward Reporting | 2011-04-01 | 2011-07-31 | In-Progress | 100% | Black
EMPLOYEE Summary | 2011-04-01 | 2012-03-31 | In-Progress | 61% | G
IT OPERATIONS SERVICES SUMMARY | 2011-04-01 | 2012-03-31 | In-Progress | 50.93% | G