## Sheet1
GoBlock's Basic Roles and Responsibility Matrix for Automation Projects
This list represents the top 24 activities to consider in a R&R Matrix
The matrix should be expanded and edited to fit the particular needs of the project.
*for public use*
Activity | Responsibility
Define project scope and objectives | Buyer
Develop high-level project plan | Buyer
Site preparation (floor, racking, power) | Buyer
Facility access and security clearances | Buyer
Procurement of equipment and software | Vendor
Detailed solution design | Vendor
System integration design | Vendor
IT infrastructure setup | Buyer
Custom coding / interfaces | Buyer
Configuration of software (WMS, controls) | Vendor
Factory acceptance testing (FAT) | Vendor
Shipping and logistics for equipment | Vendor
Customs clearance (if applicable) | Vendor
On-site installation of equipment | Vendor
Network and systems connectivity | Buyer
System commissioning and start-up | Vendor
Site acceptance testing (SAT) | Vendor
User training sessions | Buyer
Development of SOPs and work instructions | Buyer
Data migration (if needed) | Buyer
Performance testing and optimization | Vendor
Go-live support | Vendor
Post-go-live hypercare | Vendor
Ongoing maintenance and support | Buyer