## Project Overview
[7 empty] | Estimated Remaining Project Costs | -44560672.25
[7 empty] | Grant Funds Remaining | 2440971
[7 empty] | Cash Available for Projects | 8845217
[7 empty] | Bond Proceeds | 33500000
[7 empty] | Excess (Defiency) of funds | 225515.75
Forecasted based on Unaudited YTD through May
Actual
| 2020(1) | 2021(1) | 2022(1) | 2023(1) | 2024(2)
Assessment Charges
Assessment Revenue | 1140549 | 1465258 | 1712923 | 4643109 | 1603097.31 | 0
User Rate | 0 | 0 | 0 | 0 | 0 | 0
Facility Maintenance Fee (debt service fee) | 0 | 0 | 0 | 0 | 1495381.5 | 0
City of Shelley | 547892 | 573374 | 609073 | 626242 | 509355 | 0
City of Ammon | 1451058.96 | 1508376.96 | 1528440.96 | 1612362.96 | 1294425 | 0
EIRSD Capacity Replacement Fee (connection fee) | 0 | 0 | 0 | 0 | 2363382 | 0
Leachate Revenue | 0 | 0 | 0 | 0 | 259875 | 0
Other Revenue | 915574 | 1659534 | 2420316 | 1007229 | 0 | 0
Interest Income | 0 | 0 | 0 | 0 | 788062.5 | 0
Total Revenue | 4055073.96 | 5206542.96 | 6270752.96 | 7888942.96 | 8313578.31
Operating Expense (less depreciation) | 1095827 | 1361378 | 1451497 | 1439917 | 1557867.27
Funds available for Debt Service | 2959246.96 | 3845164.96 | 4819255.96 | 6449025.96 | 6755711.04
Debt Service
- Ammon DEQ Loan | 1068522.84 | 1068522.84 | 1068522.84 | 1068522.84 | 1018575.14
- Shelley DEQ Loan (3) | 487350 | 487350 | 487350 | 487350 | 487350
| 1555872.84 | 1555872.84 | 1555872.84 | 1555872.84 | 1505925.14
Debt service coverage ratio | 1.902 | 2.4714 | 3.0975 | 4.145 | 4.4861
Income (loss) from operations | 1395142.96 | 2283040.96 | 3255151.96 | 4885581.96 | 5192267.04
Forecasted(1)
| 2025 | 2026 | 2027 | 2028 | 2029
Total Revenue | 6913690.2685 | 6672973.6033 | 6733191.0248 | 6805771.8852 | 7084836.3758
Operating Expense (less depreciation) | 1620181.9608 | 1684989.2392 | 1752388.8088 | 1822484.3612 | 1895383.7356
Funds available for Debt Service | 5293508.3077 | 4987984.3641 | 4980802.216 | 4983287.524 | 5189452.6402
Debt Service (including anticipated debt service)
- Shelley DEQ Loan | 487350 | 487350 | 487350 | 487350 | 487350
- Ammon DEQ Loan | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14
- 2024 Sewer Revenue Bond | 2205800 | 2205800 | 2205800 | 2205800 | 2205800
| 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14
Debt service coverage ratio | 1.4262 | 1.3438 | 1.3419 | 1.3426 | 1.3981
|  | Principal Payment Date (September 15) | Principal Amount | Principal Payment Date (September 15) | Principal Amount
|  | 2025 | 525000 | 2040 | 1145000
|  | 2026 | 620000 | 2041 | 1200000
|  | 2027 | 645000 | 2042 | 1250000
|  | 2028 | 675000 | 2043 | 1310000
|  | 2029 | 705000 | 2044 | 1370000
|  | 2030 | 740000 | 2045 | 1430000
|  | 2031 | 770000 | 2046 | 1495000
|  | 2032 | 805000 | 2047 | 1560000
|  | 2033 | 845000 | 2048 | 1630000
|  | 2034 | 880000 | 2049 | 1705000
|  | 2035 | 920000 | 2050 | 1780000
|  | 2036 | 960000 | 2051 | 1860000
|  | 2037 | 1005000 | 2052 | 1945000
|  | 2038 | 1050000 | 2053 | 2030000
|  | 2039 | 1095000 | 2054 | 2125000
|  |  |  | Total | 36075000

## Historical Financial Info
Forecasted Based on YTD through May
| Actual |  |  |  |  | Forecast
| 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055
Assessment Charges
Assessment Revenue | 1140549 | 1465258 | 1712923 | 4643109 | 1603097.31
User Rate | [5 empty] | 1762513.1685 | 1888811.311 | 2031548.5588 | 2185105.291 | 2350303.2818 | 2528026.8049 | 2719227.3916 | 2924928.9502 | 3146233.2762 | 3352094.3056 | 3571470.5483 | 3805251.1438 | 4054383.8001 | 4319878.655 | 4602812.3913 | 4904332.6239 | 5225662.5766 | 5568106.066 | 5933052.8162 | 6321984.1219 | 6736478.8865 | 7178220.0581 | 7649001.4896 | 8150735.2519 | 8685459.4291 | 9255346.428 | 9862711.8359 | 10510023.8624 | 11199913.4045 | 11935184.7751 | 12718827.1396
Facility Maintenance Fee (debt service fee) |  |  |  |  | 1495381.5 | 2496120 | 2547606.6 | 2609646.6 | 2673237.6 | 2738418.375 | 2805228.6694 | 2873709.2211 | 2943901.7866 | 3015849.1663 | 3089595.2305 | 3165184.9462 | 3242664.4049 | 3322080.85 | 3403482.7062 | 3486919.6089 | 3572442.4341 | 3660103.33 | 3749955.7482 | 3842054.4769 | 3936455.6739 | 4033216.9007 | 4132397.1582 | 4234056.9222 | 4338258.1802 | 4445064.4697 | 4554540.9165 | 4666754.2744 | 4781772.9663 | 4899667.1254 | 5020508.6385 | 5144371.1895
City of Shelley | 547892 | 573374 | 609073 | 626242 | 509355
City of Ammon | 1451058.96 | 1508376.96 | 1528440.96 | 1612362.96 | 1294425
EIRSD Capacity Replacement Fee (connection fee) |  |  |  |  | 2363382 | 1534788 | 1690244.9323 | 2036700.726 | 1947428.9942 | 1996114.719 | 2046017.587 | 2097168.0267 | 2149597.2273 | 2203337.158 | 2258420.587 | 2314881.1016 | 2372753.1292 | 2432071.9574 | 2492873.7563 | 2555195.6002 | 2619075.4902 | 2684552.3775 | 2751666.1869 | 2820457.8416 | 2890969.2877 | 2963243.5198 | 3037324.6078 | 3113257.723 | 3191089.1661 | 3270866.3953 | 3352638.0551 | 3436454.0065 | 3522365.3567 | 3610424.4906 | 3700685.1029 | 3793202.2304
Leachate Revenue |  |  |  |  | 259875 | Forecast 2025: 200000; Forecast 2026: 100000
Other Revenue | 915574 | 1659534 | 2420316 | 1007229
Interest Income |  |  |  |  | 788062.5 | Forecast 2025: 920269.1; Forecast 2026: 446310.76; Forecast 2027: 55295.14
Total Revenue | 4055073.96 | 5206542.96 | 6270752.96 | 7888942.96 | 8313578.31 | 6913690.2685 | 6672973.6033 | 6733191.0248 | 6805771.8852 | 7084836.3758 | 7379273.0613 | 7690104.6394 | 8018427.9642 | 8365419.6005 | 8700110.123 | 9051536.5961 | 9420668.6778 | 9808536.6075 | 10216235.1176 | 10644927.6004 | 11095850.5483 | 11570318.284 | 12069728.0012 | 12595565.1347 | 13149409.0834 | 13732939.307 | 14347941.8241 | 14996316.1348 | 15680082.5982 | 16401390.2941 | 17162525.3996 | 17965920.1168 | 18814162.1853 | 19710005.0205 | 20656378.5165 | 21656400.5595
Operating Expense (less depreciation) | 1095827 | 1361378 | 1451497 | 1439917 | 1557867.27 | 1620181.9608 | 1684989.2392 | 1752388.8088 | 1822484.3612 | 1895383.7356 | 1971199.085 | 2050047.0484 | 2132048.9304 | 2217330.8876 | 2306024.1231 | 2398265.088 | 2494195.6915 | 2593963.5192 | 2697722.06 | 2805630.9423 | 2917856.18 | 3034570.4272 | 3155953.2443 | 3282191.3741 | 3413479.0291 | 3550018.1902 | 3692018.9178 | 3839699.6746 | 3993287.6615 | 4153019.168 | 4319139.9347 | 4491905.5321 | 4671581.7534 | 4858445.0235 | 5052782.8245 | 5254894.1375
Funds available for Debt Service | 2959246.96 | 3845164.96 | 4819255.96 | 6449025.96 | 6755711.04 | 5293508.3077 | 4987984.3641 | 4980802.216 | 4983287.524 | 5189452.6402 | 5408073.9763 | 5640057.591 | 5886379.0338 | 6148088.7129 | 6394085.9999 | 6653271.5081 | 6926472.9863 | 7214573.0883 | 7518513.0576 | 7839296.6581 | 8177994.3683 | 8535747.8568 | 8913774.7569 | 9313373.7606 | 9735930.0543 | 10182921.1168 | 10655922.9063 | 11156616.4602 | 11686794.9367 | 12248371.1261 | 12843385.4649 | 13474014.5847 | 14142580.432 | 14851559.997 | 15603595.6921 | 16401506.4221
Debt Service | 1555872.84 | 1555872.84 | 1555872.84 | 1555872.84 | 1505925.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800
Debt service coverage ratio | 1.902 | 2.4714 | 3.0975 | 4.145 | 4.4861 | 1.4262 | 1.3438 | 1.3419 | 1.3426 | 1.3981 | 1.457 | 1.5195 | 1.8256 | 1.9068 | 1.983 | 2.0634 | 2.1482 | 2.2375 | 2.3318 | 2.4313 | 2.5363 | 2.6473 | 2.7645 | 2.8884 | 4.4138 | 4.6164 | 4.8309 | 5.0579 | 5.2982 | 5.5528 | 5.8226 | 6.1084 | 6.4115 | 6.733 | 7.0739 | 7.4356
Depreciation | 1564104 | 1562124 | 1564104 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444 | 1563444
Income (loss) from operations | 1395142.96 | 2283040.96 | 3255151.96 | 4885581.96 | 5192267.04 | 3730064.3077 | 3424540.3641 | 3417358.216 | 3419843.524 | 3626008.6402 | 3844629.9763 | 4076613.591 | 4322935.0338 | 4584644.7129 | 4830641.9999 | 5089827.5081 | 5363028.9863 | 5651129.0883 | 5955069.0576 | 6275852.6581 | 6614550.3683 | 6972303.8568 | 7350330.7569 | 7749929.7606 | 8172486.0543 | 8619477.1168 | 9092478.9063 | 9593172.4602 | 10123350.9367 | 10684927.1261 | 11279941.4649 | 11910570.5847 | 12579136.432 | 13288115.997 | 14040151.6921 | 14838062.4221
,
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $2.3mm in connection fee revenue
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Made up of account 62-340-101 and 62-340-103 per Jennifer from Ammon
Note on O22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Shelly loan rolls off
Note on AA22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ammon Loan rolls off

## Inputs
Assumed Fees for Scenarios Below | Summary of Fees Currently Charged
| Ammon | Shelley | County Customers
CONNECTION FEE
EIRSD Capacity Replacement Fee | 5639 | 5639 | 5639 |  | 6221 | residential | 3947300
Surcharge (in place until fully operational 2027) | 582 | 582 | 582
Added Connection Fee by Entity | 1300 | 500
Total Connection Fee | 7521 | 6721 | 6221
MONTHLY FEE
EIRSD Monthly O&M Fee | 14.09 | 14.09 | 14.09
Current Debt Service Fee | 22 | 22
Future membrane replacement/???? |  |  | 8.85
Reserve fund for future upgrades |  |  | 22
City Monthly O&M Fee | 13.96 | 8.08
Total Monthly Sewer Fee | 50.05 | 44.17 | 44.94
Average Monthly Household Income (Census.gov) | 6372.5833 | 5398.5833 | 5885.5833
Sewer Fee as a % of ave household income | 0.7854% | 0.8182% | 0.7636%
Debt Service Payments
Ammon Loan - Old | 1068522.84
Ammon Loan - new | 1018575.14 |  | 385738 | 340612
Shelly Loan | 487350 |  | 729404 | 738874 | 16047
New Loan ($36.075mm loan, $33.5mm in proceeds) | 2205800 |  | 1115142 | 1079486 | 237397.7
Total Debt Service | 3711725.14 |  |  |  | 296863.7
348761.4
Ammon Loan - Old | 1068522.84 |  |  |  | 185500.2
1084570
Expense Inflation | 4%
Annual O & M fee increase | 5%
| 2021 | 2022 | 2023
City of Ammon | 534261.3 | 1068522.72 | 1068522.7
Anticipated Connection Fee increase | Increase | 14%
Year 1 | 7091.94 | 7091.94 | 7091.94
Year 2 | 8084.8116 | 8084.8116 | 8084.8116

## Debt Profile
| 2025-09-30 | 2026-09-30 | 2027-09-30 | 2028-09-30 | 2029-09-30 | 2030-09-30 | 2031-09-30 | 2032-09-30 | 2033-09-30 | 2034-09-30 | 2035-09-30 | 2036-09-30 | 2037-09-30 | 2038-09-30 | 2039-09-30 | 2040-09-30 | 2041-09-30 | 2042-09-30 | 2043-09-30 | 2044-09-30 | 2045-09-30 | 2046-09-30 | 2047-09-30 | 2048-09-30 | 2049-09-30 | 2050-09-30 | 2051-09-30 | 2052-09-30 | 2053-09-30 | 2054-09-30
2024 Sewer Revenue Bonds | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800
DEQ - Ammon Loan | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 1018575.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DEQ - Shelly Loan | 487350 | 487350 | 487350 | 487350 | 487350 | 487350 | 487350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Debt Service | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3711725.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 3224375.14 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800 | 2205800

## ERU Forecast
Existing Ammon 30-Year Loan
Per Jennifer on 10/24/2022
Maturity date = | [7 empty] | 2043-04-24
Current date = | [7 empty] | 2022-09-20
Years remaining = | [7 empty] | 20.6055
Original loan amount = | [7 empty] | 23213934
Principal outstanding = | [7 empty] | 16731104.63 | as of current date
Principal paid to date = | [7 empty] | 6482829.37
Loan rate = | [7 empty] | 2.25%
Loan period = | [7 empty] | 30 | years
Annual payment = | [7 empty] | 1072468.48
Existing Shelley 20-Year Loan
Per Shelley amortization schedule from Sandy on 10/4/2022
Maturity date = | [7 empty] | 2031-09-15
Current date = | [7 empty] | 2022-09-20
Years remaining = | [7 empty] | 8.9918
Original loan amount = | [7 empty] | 8000000
Principal outstanding = | [7 empty] | 3995622 | as of current date
Principal paid to date = | [7 empty] | 4004378
Loan rate = | [7 empty] | 2%
Loan period = | [7 empty] | 20 | years
Annual payment = | [7 empty] | 487350 | 489253.745
Future EIRSD Loan
Principal to pay off City Loans = | [7 empty] | 0 | Assume existing City loans are transferred to EIRSD and paid by existing customers
Upgrades project cost = | [7 empty] | 51000000
Other funds available = | [7 empty] | -17000000
Principal for Total Upgrades = | [7 empty] | 34000000
Principal for Upgrades to Existing = | [7 empty] | 11000000
Principal for Remaining Upgrades = | [7 empty] | 23000000
Total Principal of Loan = | [7 empty] | 34000000
Loan term, n (years) = | [7 empty] | 30
Loan rate = | [7 empty] | 5%
Annual pmt for City Loans = | [7 empty] | 0 | Assume existing City loans are transferred to EIRSD and paid by existing customers
Annual pmt for "Upgrades to Existing" = | [7 empty] | 715565.7859
Annual pmt for "Remaining Upgrades" = | [7 empty] | 1496183.0068 |  | 1597806
Annual pmt for Total = | [7 empty] | 2211748.7927
Year | [7 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| 2020(3) | 2021(3) | 2022(3) | 2023(3) | 2024(2) | 2024 | 2025(1) | 2026(1) | 2027(1) | 2028(1) | 2029(1) | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056
O&M fee | [5 empty] | 14.7945 | 15.5342 | 16.3109 | 17.1265 | 17.9828 | 18.8819 | 19.826 | 20.8173 | 21.8582 | 22.9511 | 23.8692 | 24.8239 | 25.8169 | 26.8496 | 27.9236 | 29.0405 | 30.2021 | 31.4102 | 32.6666 | 33.9733 | 35.3322 | 36.7455 | 38.2153 | 39.7439 | 41.3337 | 42.987 | 44.7065 | 46.4948 | 48.3546 | 50.2887 | 52.3003 | 54.3923 | 56.568
[7 empty] | 7091.94 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116 | 8084.8116
ERUs Connected
Assumed annual population growth | [7 empty] | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5%
Additional ERUs coming on board in 2024 | [5 empty] | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
Ammon |  |  |  | 6201 |  | 6190 | 6350 | 6500 | 6662.5 | 6829.0625 | 6999.7891 | 7174.7838 | 7354.1534 | 7538.0072 | 7726.4574 | 7919.6188 | 8117.6093 | 8320.5495 | 8528.5633 | 8741.7774 | 8960.3218 | 9184.3298 | 9413.9381 | 9649.2865 | 9890.5187 | 10137.7817 | 10391.2262 | 10651.0069 | 10917.282 | 11190.2141 | 11469.9694 | 11756.7187 | 12050.6366 | 12351.9026 | 12660.7001 | 12977.2176 | 13301.6481 | 13634.1893
Shelley |  |  |  | 2212 |  | 2250 | 2270 | 2300 | 2357.5 | 2416.4375 | 2476.8484 | 2538.7696 | 2602.2389 | 2667.2949 | 2733.9772 | 2802.3267 | 2872.3848 | 2944.1945 | 3017.7993 | 3093.2443 | 3170.5754 | 3249.8398 | 3331.0858 | 3414.3629 | 3499.722 | 3587.2151 | 3676.8954 | 3768.8178 | 3863.0383 | 3959.6142 | 4058.6046 | 4160.0697 | 4264.0714 | 4370.6732 | 4479.94 | 4591.9385 | 4706.737 | 4824.4054
Counties |  |  |  | 373 |  | 565 | 585 | 600 | 615 | 630.375 | 646.1344 | 662.2877 | 678.8449 | 695.8161 | 713.2115 | 731.0417 | 749.3178 | 768.0507 | 787.252 | 806.9333 | 827.1066 | 847.7843 | 868.9789 | 890.7034 | 912.971 | 935.7952 | 959.1901 | 983.1699 | 1007.7491 | 1032.9428 | 1058.7664 | 1085.2356 | 1112.3665 | 1140.1756 | 1168.68 | 1197.897 | 1227.8444 | 1258.5405
Total ERU's | 7914 | 8030 | 8405 | 8786 | 8965 | 9255 | 9455 | 9650.025 | 9885.025 | 10125.9 | 10372.7969 | 10625.8662 | 10885.2622 | 11151.1431 | 11423.6711 | 11703.0122 | 11989.3369 | 12282.8197 | 12583.6396 | 12891.9799 | 13208.0288 | 13531.9789 | 13864.0278 | 14204.3778 | 14553.2367 | 14910.8169 | 15277.3367 | 15653.0195 | 16038.0944 | 16432.7961 | 16837.3654 | 17252.0489 | 17677.0995 | 18112.7764 | 18559.3452 | 19017.0782 | 19486.2545 | 19967.1602
Resulting annual growth, ERUs/year = | [5 empty] | 445.5 | 200 | 195.025 | 235 | 240.875 | 246.8969 | 253.0693 | 259.396 | 265.8809 | 272.528 | 279.3412 | 286.3247 | 293.4828 | 300.8199 | 308.3404 | 316.0489 | 323.9501 | 332.0488 | 340.3501 | 348.8588 | 357.5803 | 366.5198 | 375.6828 | 385.0749 | 394.7017 | 404.5693 | 414.6835 | 425.0506 | 435.6769 | 446.5688 | 457.733 | 469.1763 | 480.9057

## Capacity
Current Capacity with Project 1 complete | 9,500-10,000
Capacity with completion of 2 and 3 | 16000

## ERU Sum by Month
EIRSD - ERU Tracking |  | No update received
ERUs Currently Connected and Billed
Location |  | 2022-09-16 | 2022-10-22 | 2022-11-14 | 2022-12-13 | 2023-01-14 | 2023-02-19 | 2023-03-20 | 2023-04-18 | 2023-05-16 | 2023-06-14 | 2023-07-18 | 2023-08-22 | 2023-09-19
Ammon |  | 5745 | 5745 | 5796 | 5796 | 5805 | 5817 | 5824 | 5855 | 5853 | 5883 | 5924 | 5939 | 5965
IBSD (by Ammon) |  | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117 | 117
Shelley |  | 2073 | 2073 | 2073 | 2088 | 2188 | 2188 | 2191 | 2193 | 2198 | 2203 | 2205 | 2205 | 2205
County Areas
Falls W&S District |  | 178 | 176 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 178 | 179 | 179
Woodville W&S District |  | 4 | 4 | 4 | 4 | 5 | 14 | 15 | 15 | 15 | 15 | 19 | 19 | 19
North Interceptor |  | 287.5 | 291.5 | 291.5 | 291.5 | 291.5 | 302.5 | 308.5 | 308.5 | 308.5 | 299.5 | 299.5 | 299.5 | 299.5
East Interceptor |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Total |  | 8429.5 | 8431.5 | 8484.5 | 8499.5 | 8609.5 | 8641.5 | 8658.5 | 8691.5 | 8694.5 | 8720.5 | 8767.5 | 8783.5 | 8809.5
Avg Growth - normalized to annual | 4.424% |  | 0.2847% | 7.543% | 2.122% | 15.53% | 4.46% | 2.361% | 4.574% | 0.4142% | 3.588% | 6.468% | 2.19% | 3.552%

## Const cost summary
EIRSD - Funding Summary for Improvements
FUNDS CURRENTLY AVAILABLE | Balances on 4/16/24 per Janice | Funds that could be applied toward Upgrades |  | Funds that can't be applied toward Upgrades
Reserve Funds
EIRSD
BoC Checking - 10000 - 0367 | 60000 | 60000 |  |  | also used to cover O&M expenses
BoC Sweep - Money Market 5% (acct 2678) | 8743753 | 7926673 |  | 817080 | used to cover O&M expenses
Ammon bond fund - Money Market (acct 2918) | 1090070
Shelley bond fund - Money Market (acct 2884) | 500938
BoC County Debt Service | 129003 | 129003
BoC City Debt Service (pending) | 729541 | 729541
BoC Money Market for Emergency Reserves (pending) | 1600000
Reserve Funds Balance | 12853305 | 8845217 |  | 817080
Grant Funds
ARPA fund contributions from entities
Bingham County | 0 | as of 9/19/23; originally $1,500,000
Bonneville County | 0 | as of 10/4/23; originally $1,500,000
City of Ammon | now in checking | $1.6M; roughly 45% of ARPA allotment
City of Shelley | now in checking | ~$400K (~45% of allotment similar to Ammon per Jeff in June 2021 board mtg)
DEQ ARPA Grant | 2440971 | 2440971 | as of 4/22/24 | originally $4,659,278
Other potential grant funds
Block Grant | ??? | Need to apply if direct connection to jobs can be made
US Army Corps 595 | ??? | 10/3/23 - Karen at the Corps has requested $2M in grant for EIRSD; won't know until Congress passes a year-long budget rather than just a stop-gap measure
DEQ loan forgiveness | ??? | Median household income may be too high for this
Other Federal Grant(s) | ???
Grant Funds Balance | 2440971
Total Funds Currently Available |  | 11286188 | [7 empty] | Scenario A |  | Scenario B |  | Scenario C-1 |  | Scenario C |  | Scenario D
Potential revenue in 7 months remaining to FY end per Janice | 1045861 | not included as currently available | [7 empty] | Project 1 only |  | Project 1 and all Project 2/3 except bio and membrane (not recommend as it doesn't add capacity) |  | Project 1 and Project 2 but only part of membrane (not recommended as it doesn't add capacity) |  | Project 1 and Project 2/3 except no LS or headworks upgrades |  | All of Project 1 and Project 2/3
UPCOMING ESTIMATED COSTS FOR UPGRADES | [9 empty] | Included? | Cost | Included? | Cost | Included? | Cost | Included? | Cost | Included? | Cost
Complete Proj 1 Const, Proj 2 Design, and Proj 2 Loan Applic | 14404822
| Construction - GSE | 2.4% | Construction - GSE | CM/GC - GSE | 8% | 4% | 0.25%
Project 2 Construction | IFC est (no cont) | Contingency | IFC est (w/cont) |  | CMS - J-U-B | RPR - J-U-B | Ctrl Prog - AWerks | Subtotal
Riverbend Lift Station | 3332747.2 | 79985.9328 | 3414700 |  | 273176 | 136588 | 8536.75 | 3833000.75 |  |  | 0 | x | 3833000.75 |  | 0 |  | 0 | x | 3833000.75
Headworks Screening | 5490878.4 |  | 5625900 |  | 450072 | 225036 | 14064.75 | 6315072.75
Biological Treatment remaining | 2894620.8 | 69470.8992 | 2965800 |  | 237264 | 118632 | 7414.5 | 3329110.5 |  |  | 0 |  | 0 | x | 3329110.5 | x | 3329110.5 | x | 3329110.5
Membrane System | 16112686.4 | 386704.4736 | 16508900 |  | 1320712 | 660356 | 41272.25 | 18531240.25 |  |  | 0 |  | 0 | x | 12000000 | x | 18531240.25 | x | 18531240.25
NPW System | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | x | 0 | x | 0 | x | 0 | x | 0
UV Disinfection | 188953.6 | 4534.8864 | 193600 |  | 15488 | 7744 | 484 | 217316 |  |  | 0 | x | 217316 | x | 217316 | x | 217316 | x | 217316
Forklift | 200000 | 4800 | 200000 |  | 16000 | 8000 | 500 | 224500 |  |  | 0
Cost Savings | [7 empty] | 0
Switching to a PEMB |  |  | 0 |  | 0 | 0 | 0 | 0 | GSE should have something early next week; will need foundation redesign at some point
TMOS mods | -536000 |  | -536000 |  | -42880 | -21440 | -1340 | -601660
No roof on new TMOS |  |  |  |  | 0 | 0 | 0 | 0
Reduced headworks pumping | -186000 |  | -186000 |  | -14880 | -7440 | -465 | -208785
Not populating the 4th membrane train | -512000 |  | -512000 |  | -40960 | -20480 | -1280 | -574720
Not paving the new access road | -450000 |  | -450000 |  | -36000 | -18000 | -1125 | -505125
Unused contingency from Project 1 | -360000 |  | -360000 |  | -28800 | -14400 | -900 | -404100
|  |  | 0 |  | 0 | 0 | 0 | 0
CM/GC services |  | 0 | 0 |  | 0 | 0 | 0 | 0
Subtotals | 26175886.4 | 545496.192 | 26864900 | 0 | 2149192 | 1074596 | 67162.25 | 30155850.25 |  |  | 0 |  | 4050316.75 |  | 15546426.5 |  | 22077666.75 |  | 25910667.5
Subtotal | 30155850.25
Potential future costs not included above:
Infrastructure for implementing reuse on adjacent land
Blackfoot Phase 2
Construction cost | 15100000
CMS total (included bidding and award) | 1750000 | 11.59%
Engr | 1190000 | 7.881%
RPR | 560000 | 3.709%
Note on C39: Alan Giesbrecht: GSE's IFC estimate includes 2.4% contingency
Note on A48: Alan Giesbrecht: Potential for $900K in savings if eliminated
Note on A50: Alan Giesbrecht: 5/28/24 - potential for $445K in savings if eliminated

## Const cost
[14 empty] | Currently Available Funds | 11286000
[15 empty] | Cap Fee | 6223 | before Project 1
[16 empty] | 7000 | after Project 1
Total Cost | 19392041 | 599199 | 1444325 | 25000 | 500000 | 22390 | 0 | 26864900 | 0 | 3223788 | 75000 |  |  |  | Added ERUs | 0 | per year
Before Apr 2024 | 7356002 | 222131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | per month
Remaining | 12036039 | 377068 | 1444325 | 25000 | 500000 | 22390 | 0 | 26864900 | 0 | 3223788 | 75000 |  |  |  |  | (281 in past 12 months)
Month | GSE Proj 1 Const | GSE Proj 1 CM/GC | J-U-B Proj 1 CMS | AWerks Proj 1 | J-U-B Proj 2 Design/Bid | Dupont Proj 2 | Clearwater Proj 2 | GSE Proj 2 Const | GSE Proj 2 CM/GC | J-U-B Proj 2 CMS | Awerks Proj 2 | Project 1+ Costs Remain | Project 2 Costs Remain | Total Project Costs Remain | Available Funds for Projects | Connection Fee | Potential Fee Revenue | Loan Draw | Available Fund Balance | Project 1 % Remain | Project 2 % Remain
2024-01-01 | [11 empty] | 0 | 0 | 0 |  |  | 0 |  | 0
2024-02-01 | [11 empty] | 0 | 0 | 0 |  |  | 0 |  | 0
2024-03-01 | [11 empty] | 0 | 0 | 0 |  |  | 0 |  | 0
2024-04-01 | 812977.6343 |  | 103166.0714 | 1785.7143 |  |  | 0 |  |  |  |  | -917929.42 | 0 | -917929.42 | 11286000 | 6223 | 0 |  | 10368070.58 | 6.755%
2024-05-01 | 341647.9385 | 300000 | 103166.0714 | 1785.7143 | 100000 | 22390 | [5 empty] | -868989.7242 | 0 | -868989.7242 | 10368070.58 | 6223 | 0 |  | 9499080.8558 | 2.839%
2024-06-01 | 1024943.8155 | 20000 | 103166.0714 | 1785.7143 | 100000 | [6 empty] | -1249895.6012 | 0 | -1249895.6012 | 9499080.8558 | 6223 | 0 |  | 8249185.2546 | 8.516%
2024-07-01 | 1708239.6925 | 20000 | 103166.0714 | 1785.7143 | 100000 | [6 empty] | -1933191.4782 | 0 | -1933191.4782 | 8249185.2546 | 6223 | 0 |  | 6315993.7764 | 14.19%
2024-08-01 | 1285663.8985 | 20000 | 103166.0714 | 1785.7143 | 100000 | [6 empty] | -1510615.6843 | 0 | -1510615.6843 | 6315993.7764 | 6223 | 0 |  | 4805378.0922 | 10.68%
2024-09-01 | 1238046.7171 | 17068 | 103166.0714 | 1785.7143 | 100000 | [6 empty] | -1460066.5028 | 0 | -1460066.5028 | 4805378.0922 | 6223 | 0 |  | 3345311.5893 | 10.29%
2024-10-01 | 1281179.7694 |  | 103166.0714 | 1785.7143 |  |  |  | 1421920.7786 | 0 | 107459.6 | 2500 | -1386131.5551 | -1531880.3786 | -2918011.9336 | 3345311.5893 | 6223 | 0 |  | 427299.6557 | 10.64% | 5.293%
2024-11-01 | 469765.9154 |  | 103166.0714 | 1785.7143 |  |  |  | 7222628.365 | 0 | 107459.6 | 2500 | -574717.7011 | -7332587.965 | -7907305.6661 | 427299.6557 | 6223 | 0 | 7480006.0104 | 0 | 3.903% | 26.88%
2024-12-01 | 640589.8847 |  | 103166.0714 | 1785.7143 |  |  |  | 605592.4136 | 0 | 107459.6 | 2500 | -745541.6704 | -715552.0136 | -1461093.684 | 0 | 6223 | 0 | 1461093.684 | 0 | 5.322% | 2.254%
2025-01-01 | 640589.8847 |  | 103166.0714 | 1785.7143 |  |  |  | 743773.9457 | 0 | 107459.6 | 2500 | -745541.6704 | -853733.5457 | -1599275.2161 | 0 | 6223 | 0 | 1599275.2161 | 0 | 5.322% | 2.769%
2025-02-01 | 512471.9077 |  | 103166.0714 | 1785.7143 |  |  |  | 787889.9494 | 0 | 107459.6 | 2500 | -617423.6935 | -897849.5494 | -1515273.2428 | 0 | 6223 | 0 | 1515273.2428 | 0 | 4.258% | 2.933%
2025-03-01 | 768707.8616 |  | 103166.0714 | 1785.7143 |  |  |  | 802109.1571 | 0 | 107459.6 | 2500 | -873659.6473 | -912068.7571 | -1785728.4045 | 0 | 6223 | 0 | 1785728.4045 | 0 | 6.387% | 2.986%
2025-04-01 | 341647.9385 |  | 103166.0714 | 1785.7143 |  |  |  | 729190.1429 | 0 | 107459.6 | 2500 | -446599.7242 | -839149.7429 | -1285749.4671 | 0 | 6223 | 0 | 1285749.4671 | 0 | 2.839% | 2.714%
2025-05-01 | 969605.1418 |  | 103166.0714 | 1785.7143 |  |  |  | 787889.9494 | 0 | 107459.6 | 2500 | -1074556.9275 | -897849.5494 | -1972406.4769 | 0 | 6223 | 0 | 1972406.4769 | 0 | 8.056% | 2.933%
2025-06-01 | [7 empty] | 802109.1571 | 0 | 107459.6 | 2500 | 0 | -912068.7571 | -912068.7571 | 0 | 7000 | 0 | 912068.7571 | 0 |  | 2.986%
2025-07-01 | [7 empty] | 780233.4529 | 0 | 107459.6 | 2500 | 0 | -890193.0529 | -890193.0529 | 0 | 7000 | 0 | 890193.0529 | 0 |  | 2.904%
2025-08-01 | [7 empty] | 74377.3946 | 0 | 107459.6 | 2500 | 0 | -184336.9946 | -184336.9946 | 0 | 7000 | 0 | 184336.9946 | 0 |  | 0.2769%
2025-09-01 | [7 empty] | 787889.9494 | 0 | 107459.6 | 2500 | 0 | -897849.5494 | -897849.5494 | 0 | 7000 | 0 | 897849.5494 | 0 |  | 2.933%
2025-10-01 | [7 empty] | 656271.1286 | 0 | 107459.6 | 2500 | 0 | -766230.7286 | -766230.7286 | 0 | 7000 | 0 | 766230.7286 | 0 |  | 2.443%
2025-11-01 | [7 empty] | 583716.7094 | 0 | 107459.6 | 2500 | 0 | -693676.3094 | -693676.3094 | 0 | 7000 | 0 | 693676.3094 | 0 |  | 2.173%
2025-12-01 | [7 empty] | 546892.6071 | 0 | 107459.6 | 2500 | 0 | -656852.2071 | -656852.2071 | 0 | 7000 | 0 | 656852.2071 | 0 |  | 2.036%
2026-01-01 | [7 empty] | 455743.8393 | 0 | 107459.6 | 2500 | 0 | -565703.4393 | -565703.4393 | 0 | 7000 | 0 | 565703.4393 | 0 |  | 1.696%
2026-02-01 | [7 empty] | 364595.0714 | 0 | 107459.6 | 2500 | 0 | -474554.6714 | -474554.6714 | 0 | 7000 | 0 | 474554.6714 | 0 |  | 1.357%
2026-03-01 | [7 empty] | 529027.4486 | 0 | 107459.6 | 2500 | 0 | -638987.0486 | -638987.0486 | 0 | 7000 | 0 | 638987.0486 | 0 |  | 1.969%
2026-04-01 | [7 empty] | 860808.9636 | 0 | 107459.6 | 2500 | 0 | -970768.5636 | -970768.5636 | 0 | 7000 | 0 | 970768.5636 | 0 |  | 3.204%
2026-05-01 | [7 empty] | 860808.9636 | 0 | 107459.6 | 2500 | 0 | -970768.5636 | -970768.5636 | 0 | 7000 | 0 | 970768.5636 | 0 |  | 3.204%
2026-06-01 | [7 empty] | 860808.9636 | 0 | 107459.6 | 2500 | 0 | -970768.5636 | -970768.5636 | 0 | 7000 | 0 | 970768.5636 | 0 |  | 3.204%
2026-07-01 | [7 empty] | 860808.9636 | 0 | 107459.6 | 2500 | 0 | -970768.5636 | -970768.5636 | 0 | 7000 | 0 | 970768.5636 | 0 |  | 3.204%
2026-08-01 | [7 empty] | 860808.9636 | 0 | 107459.6 | 2500 | 0 | -970768.5636 | -970768.5636 | 0 | 7000 | 0 | 970768.5636 | 0 |  | 3.204%
2026-09-01 | [7 empty] | 860808.9636 | 0 | 107459.6 | 2500 | 0 | -970768.5636 | -970768.5636 | 0 | 7000 | 0 | 970768.5636 | 0 |  | 3.204%
2026-10-01 | [7 empty] | 860808.9636 | 0 | 107459.6 | 2500 | 0 | -970768.5636 | -970768.5636 | 0 | 7000 | 0 | 970768.5636 | 0 |  | 3.204%
2026-11-01 | [7 empty] | 364595.0714 | 0 | 107459.6 | 2500 | 0 | -474554.6714 | -474554.6714 | 0 | 7000 | 0 | 474554.6714 | 0 |  | 1.357%
2026-12-01 | [7 empty] | 291676.0571 | 0 | 107459.6 | 2500 | 0 | -401635.6571 | -401635.6571 | 0 | 7000 | 0 | 401635.6571 | 0 |  | 1.086%
2027-01-01 | [7 empty] | 109378.5214 | 0 | 107459.6 | 2500 | 0 | -219338.1214 | -219338.1214 | 0 | 7000 | 0 | 219338.1214 | 0 |  | 0.4071%
2027-02-01 | [7 empty] | 48491.1445 | 0 | 107459.6 | 2500 | 0 | -158450.7445 | -158450.7445 | 0 | 7000 | 0 | 158450.7445 | 0 |  | 0.1805%
2027-03-01 | [7 empty] | 1343245 | 0 | 107459.6 | 2500 | 0 | -1453204.6 | -1453204.6 | 0 | 7000 | 0 | 1453204.6 | 0 |  | 5%
[12 empty] | 0 | 0 | 0
TOTAL | 19392080.0001 | 377068 | 1444325 | 25000 | 500000 | 22390 | 0 | 26864900 | 0 | 3223788 | 75000 | -14404861.0001 | -30163688 | -44568549.0001 |  |  | 0 | 33282549.0001
[14 empty] | Total Project Costs Remaining | -44568549.0001
[14 empty] | Current Available Funds | 11286000
[14 empty] | Potential Fee Revenue | 0
[14 empty] | Total Loan Draw | -33282549.0001
[14 empty] | Available Loan | 33500000
[14 empty] | Delta | 217450.9999

## fromGSE
Actual
[6 empty] | based on: | 35000000 |  | 26900000
From GSE (3/13/24) for Project 1: |  | From GSE (4/9/24) for Project 2:
2024
Contract Amount | 19392041 | Afternoon Alan, we think it could look a bit more like this: |  |  |  | January
Remaining | 12771999 |  |  |  |  | February
Months Remaining | 13 Bills |  | 2024 | 2025 | 2026 | March
Average/Month | 982461.4615 | January |  | 20214000 | 10105500 | April
|  | February |  | 19114000 | 9380000 | May
Forecasting |  | March |  | 18114000 | 8199500 | June
March | 600000 | April |  | 17033500 | 7019000 | July
April | 500000 | May |  | 15933500 | 5838500 | August | 35000000
May | 400000 | June |  | 14863500 | 4658000 | September | 33050000 | 1852500 | 1423778.5714
June | 1200000 | July |  | 14761500 | 3477500 | October | 23145000 | 9409750 | 7232065
July | 2000000 | August | 35000000 | 13681000 | 2297000 | November | 22314500 | 788975 | 606383.6429
August | 1505250 | September | 33050000 | 12781000 | 1116500 | December | 21294500 | 969000 | 744745.7143
September | 1449500 | October | 23145000 | 11980500 | 616500 | January | 20214000 | 1026475 | 788919.3571
October | 1500000 | November | 22314500 | 11230500 | 216500 | February | 19114000 | 1045000 | 803157.1429
November | 550000 | December | 21294500 | 10605500 | 66500 | March | 18114000 | 950000 | 730142.8571
December | 750000 |  |  |  |  | April | 17033500 | 1026475 | 788919.3571
January | 750000 | Accounted for an earlier start to the project, as well as a little bell curving of flow to resemble what we traditionally see on projects. |  |  |  | May | 15933500 | 1045000 | 803157.1429
February | 600000 |  |  |  |  | June | 14863500 | 1016500 | 781252.8571
March | 900000 |  |  |  |  | July | 14761500 | 96900 | 74474.5714
Total | 12704750 |  |  |  |  | August | 13681000 | 1026475 | 788919.3571
[6 empty] | September | 12781000 | 855000 | 657128.5714
[6 empty] | October | 11980500 | 760475 | 584479.3571
[6 empty] | November | 11230500 | 712500 | 547607.1429
[6 empty] | December | 10605500 | 593750 | 456339.2857
[6 empty] | January | 10105500 | 475000 | 365071.4286
[6 empty] | February | 9380000 | 689225 | 529718.6429
[6 empty] | March | 8199500 | 1121475 | 861933.6429
[6 empty] | April | 7019000 | 1121475 | 861933.6429
[6 empty] | May | 5838500 | 1121475 | 861933.6429
[6 empty] | June | 4658000 | 1121475 | 861933.6429
[6 empty] | July | 3477500 | 1121475 | 861933.6429
[6 empty] | August | 2297000 | 1121475 | 861933.6429
[6 empty] | September | 1116500 | 1121475 | 861933.6429
[6 empty] | October | 616500 | 475000 | 365071.4286
[6 empty] | November | 216500 | 380000 | 292057.1429
[6 empty] | December | 66500 | 142500 | 109521.4286
[6 empty] | January |  | 63175 | 48554.5
[6 empty] | February |  | 1750000 | 1345000