## Sheet1
Rockwall Housing Authority
|  |  | Capital Funds 2022/23 |  | TX01P09550122 |  |  | Sept
Contract Contributions: $134,027
Projected Expenditures
1 |  | Item |  |  |  | Projected date | Estimated cost |  | Actual cost
2 |  | HVAC purchase ten units at $905. 00 per unit |  |  |  | May-June | 9050 |  | 9050
3 |  | Install windows for Project 2 |  |  |  | April-August | 24792 |  | 10000
76 windows at 636 per window
4 |  | Repair | parking lot at 702-71 | 2 Sam Houston |  | August | 3750 |  | 13000
5 |  | Roof repairs |  |  |  | August | 7000 |  | 5000
6 |  | Seal, Cap and install new turbines on roof project 3 |  |  |  | March-April | 4000 |  | 350
3
7 |  | Elevator equipment |  | Fire Alarm |  | August-September | 7000 |  | 7000
8 |  | Purchase 5 stoves and 5 refrigerators |  |  |  | September | 12000 |  | 6725
9 |  | Plumbing repairs, pipes replacement, toilets |  |  |  | Jan-September | 10935 |  | 21544
sinks, water heaters, faucets
10 |  | Refurbish public bathroom project 3 |  |  |  | September | 35000 |  | 38000
|  | new urinals, toilet, sinks, stalls |  |  | halway floor
11 |  | Paint/ Flooring |  |  |  | Jan-September | 6500 |  | 6322
12 |  | Move-out/Clean out |  | Handy man maintenance |  | Jan-September | 9000 |  | 12036
13 |  | Tree and Trash removal |  |  |  | Jan-September | 5000 |  | 5000
|  | YTD Cost | [5 empty] | 0
|  | Budget |  |  |  |  | 134027 |  | 134027
|  | Balance | [5 empty] | 0
Tony Rios, Executive Director
Rockwall Housing Authority