## Cover
Project Management in Action
Welcome to the Change Order Tracker. This Excel sheet is used to track Change Orders for commercial construction project.
Please fill in the following information
Your Company Name: | Project Innovations Incorporated
Your Company Address: | 123 Main Street, Milton, Ontario
Your Project Name: | Bell's Aerobic and Fitness Center
Your Project Number: | 2003-12
Your Project Address: | 123 Keefer Street
Project Architect:
Construction Manager: | Matthew Coulson, Jordan Melo
Original Contract Amount: | 1754249
Construction Start Date: | 1999-04-01
Construction End Date: | 1999-12-30
Days: | 273
Markup (O and P) | 26%
To begin all contemplated change orders must be entered.
CHANGE ORDER
Note on D6: Enter your PM Team Number.
Note on D11: If Architect's name is not in the list please go to Architect Sheet and enter their name.
Note on D13: Enter the final tender (which is the contract value) here including profit and overhead.
Note on D14: Project start according to the specifications and stated in the contract.
Note on D15: Project completion according to the specifications and stated in the contract.
Note on C17: O and P = Overhead and Profit as a percentage

## CCO
Project Name: | Bell's Aerobic and Fitness Center
Project Number: | 2003-12
Project Architect: | G/A Architects and Designers
C.C.O # | C.C.O. Description | Date Received
1 | Modify Rebar & Concrete in Grade Beam | 05/04/1999
2 | Main Structural Steel Beam | 04/05/1999
3 | Deep Roof OWSJ | 10/05/1999
4 | Automatic Main Door Opener | 13/05/1999
5 | Efficient Toilets | 14/05/1999
6 | Glass Block | 15/05/1999
7 | Painting Mural | 23/06/1999
8 | Finish Hardware | 16/06/1999
9 | Toilet Partition | 26/06/1999
10 | Signage | 12/07/1999
Note on E8: Enter CCO date received

## CCE-1
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #1
Date: | 05/04/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Modify Rebar & Concrete in Grade Beam
We are please to submit the following change order.
Description: | Modify the rebar and Mpa of concrete in the Grade Beam:
Detail of cost break down as follows:
| Rebar | Raymond Steel |  | 6500
| Concrete | LaFarge |  | 8250
| Trade | Trade Name |  | 0
14750
|  | Overhead and Profit | 26% | 3835
18585
| Duration change to contract: |  | 9 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-2
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #2
Date: | 04/05/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Main Structural Steel Beam
We are please to submit the following change order.
Description: | Revised flange and drill pattern to accommodate bearing plates
Detail of cost break down as follows:
| Structural Steel Contractor | Atlas Steel Fabricators |  | 10500
0
0
10500
|  | Overhead and Profit | 26% | 2730
13230
| Duration change to contract: |  | 9 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-3
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #3
Date: | 10/05/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Deep Roof OWSJ
We are please to submit the following change order.
Description: | Deep Roof Joist to eliminate middle main steel beam.
Detail of cost break down as follows:
| OWSJ SubContractor | Cambrian Roof System |  | 74500
| Trade | Trade Name |  | 0
| Trade | Trade Name |  | 0
74500
|  | Overhead and Profit | 26% | 19370
93870
| Duration change to contract: |  | 18 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-4
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #4
Date: | 13/05/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Automatic Main Door Opener
We are please to submit the following change order.
Description: | Supply and installation of an automatic main door opener.
Detail of cost break down as follows:
| Doors | Auto Door Ltd. |  | 9900
0
0
9900
|  | Overhead and Profit | 26% | 2574
12474
| Duration change to contract: |  | 3 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-5
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #5
Date: | 14/05/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Efficient Toilets
We are please to submit the following change order.
Description: | Replace existing toilets specified with low flush toilets.
Detail of cost break down as follows:
| Plumber | Jackson Mechanical Co. |  | 5500
| Trade | Trade Name |  | 0
| Trade | Trade Name |  | 0
5500
|  | Overhead and Profit | 26% | 1430
6930
| Duration change to contract: |  | 0 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-6
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #6
Date: | 15/05/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Glass Block
We are please to submit the following change order.
Description: | Managers office windows to be glass block
Detail of cost break down as follows:
| Masonry | Frontenac Masonry |  | 4500
|  | Sub Trade Deduction |  | -1600
0
2900
|  | Overhead and Profit | 26% | 754
3654
| Duration change to contract: |  | 0 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-7
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #7
Date: | 23/06/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Painting Mural
We are please to submit the following change order.
Description: | Wall mural in the main exercise area.
Detail of cost break down as follows:
| Painter | Enrest Paint Co. |  | 9500
| Trade | Trade Name |  | 0
| Trade | Trade Name |  | 0
9500
|  | Overhead and Profit | 26% | 2470
11970
| Duration change to contract: |  | 0 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-8
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #8
Date: | 16/06/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Finish Hardware
We are please to submit the following change order.
Description: | Supply of hardware (Oakville Hardware Limited) upgrade for all doors.
Detail of cost break down as follows:
| Hardware | Oakville Hardware Ltd. |  | 11600
0
0
11600
|  | Overhead and Profit | 26% | 3016
14616
| Duration change to contract: |  | 10 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-9
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #9
Date: | 16/06/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Toilet Partition
We are please to submit the following change order.
Description: | Toilet partition upgrade from existing specifications.
Detail of cost break down as follows:
| Plumbing | Uniform Specialties Ltd. |  | 12500
| Trade | Trade Name |  | 0
| Trade | Trade Name |  | 0
12500
|  | Overhead and Profit | 26% | 3250
15750
| Duration change to contract: |  | 20 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CCE-10
Project Innovations Incorporated
CHANGE ORDER ESTIMATE #10
Date: | 16/06/1999
To: | G/A Architects and Designers
Project: | Bell's Aerobic and Fitness Center
re: | Signage
We are please to submit the following change order.
Description: | Interior Signage Omitted in Specifications
Detail of cost break down as follows:
| Sign | Speers Signs Co. |  | 18200
0
0
18200
|  | Overhead and Profit | 26% | 4732
22932
| Duration change to contract: |  | 0 | days
by: | Matthew Coulson, Jordan Melo
Project Innovations Incorporated

## CO Recap
CHANGE ORDER RECAP FORM
Matthew Coulson, Jordan Melo
|  |  |  | Duration | Change | Change | Change |  |  | Subtrade
|  | CCO | CCO | Change | Order | Order | Order | Subtrade | Subtrade | Notice
CCO | Description | Date | Estimate | Days | Approval | Date | Amount | Name | Amount | Posted
1 | Modify Rebar & Concrete in Grade Beam | 05/04/1999 | 18585 | 9 | 1 | 1999-04-26 | 18585 | LaFarge | 8250 | 1999-04-26
[8 empty] | Trade Name | 0 | 1999-04-26
[8 empty] | Raymond Steel | 6500 | 1999-04-26
2 | Main Structural Steel Beam | 04/05/1999 | 13230 | 9 | 1 | 1999-05-12 | 13230 | Atlas Steel Fabricators | 10500 | 1999-05-12
[8 empty] | 0 | 0 | 1999-05-12
[8 empty] | 0 | 0 | 1999-05-12
3 | Deep Roof OWSJ | 10/05/1999 | 93870 | 18 | 2 | 1999-05-15 | 93870 | Cambrian Roof System | 74500 | 1999-05-15
[8 empty] | Trade Name | 0 | 1999-05-15
[8 empty] | Trade Name | 0 | 1999-05-15
4 | Automatic Main Door Opener | 13/05/1999 | 12474 | 3 | 1 | 1999-05-22 | 12474 | Auto Door Ltd. | 9900 | 1999-05-22
[8 empty] | 0 | 0 | 1999-05-22
[8 empty] | 0 | 0 | 1999-05-22
5 | Efficient Toilets | 14/05/1999 | 6930 | 0 | 1 | 1999-05-24 | 6930 | Jackson Mechanical Co. | 5500 | 1999-05-24
[8 empty] | Trade Name | 0 | 1999-05-24
[8 empty] | Trade Name | 0 | 1999-05-24
6 | Glass Block | 15/05/1999 | 3654 | 0 | 1 | 1999-05-15 | 3654 | Frontenac Masonry | 4500 | 1999-05-15
[8 empty] | Sub Trade Deduction | -1600 | 1999-05-15
[8 empty] | 0 | 0 | 1999-05-15
7 | Painting Mural | 23/06/1999 | 11970 | 0 | 1 | 1999-06-23 | 11970 | Enrest Paint Co. | 9500 | 1999-06-23
[8 empty] | Trade Name | 0 | 1999-06-23
[8 empty] | Trade Name | 0 | 1999-06-23
8 | Finish Hardware | 16/06/1999 | 14616 | 10 | 1 | 1999-06-22 | 14616 | Oakville Hardware Ltd. | 11600 | 1999-06-22
[8 empty] | 0 | 0 | 1999-06-22
[8 empty] | 0 | 0 | 1999-06-22
9 | Toilet Partition | 16/06/1999 | 15750 | 20 | 0 |  |  | Uniform Specialties Ltd. | 12500
[8 empty] | Trade Name | 0
[8 empty] | Trade Name | 0
10 | Signage | 16/06/1999 | 22932 | 0 | 1 | 1999-07-18 | 22932 | Speers Signs Co. | 18200 | 1999-07-18
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Formulas:
Subtrade = +IF([Change]=1,+[Change],+IF([Change]=2,[Change],""))
Subtrade = +IF([Change, row above]=1,+[Change, row above],+IF([Change, row above]=2,[Change, row above],""))
Note on G9: 0=in progress 1=approved 2=rejected
Note on G13: 0=in progress 1=approved 2=rejected
Note on G17: 0=in progress 1=approved 2=rejected
Note on G21: 0=in progress 1=approved 2=rejected
Note on G25: 0=in progress 1=approved 2=rejected
Note on G29: 0=in progress 1=approved 2=rejected
Note on G33: 0=in progress 1=approved 2=rejected
Note on G37: 0=in progress 1=approved 2=rejected
Note on G41: 0=in progress 1=approved 2=rejected
Note on G45: 0=in progress 1=approved 2=rejected

## Forecast
Matthew Coulson, Jordan Melo |  |  |  | Code: | 61.5658
CHANGE ORDER FORECAST
CCE | CHANGE |  | CHANGES |  | ORIGINAL | CHANGES
ORDER | ORDER | ORIGINAL | TO | REVISED | FINISH | TO | REVISED
# | STATUS | CONTRACT | CONTRACT | CONTACT | DATE | DURATION | FINISH
1 | approved | 1754249 | 18585 | 1772834 | 1999-12-30 | 9 | 2000-01-08
2 | approved | 1772834 | 13230 | 1786064 | 2000-01-08 | 9 | 2000-01-17
3 | rejected | 1786064 | 0 | 1786064 | 2000-01-17 | 0 | 2000-01-17
4 | approved | 1786064 | 12474 | 1798538 | 2000-01-17 | 3 | 2000-01-20
5 | approved | 1798538 | 6930 | 1805468 | 2000-01-20 | 0 | 2000-01-20
6 | approved | 1805468 | 3654 | 1809122 | 2000-01-20 | 0 | 2000-01-20
7 | approved | 1809122 | 11970 | 1821092 | 2000-01-20 | 0 | 2000-01-20
8 | approved | 1821092 | 14616 | 1835708 | 2000-01-20 | 10 | 2000-01-30
9 | in progress | 1835708 | 0 | 1835708 | 2000-01-30 | 0 | 2000-01-30
10 | approved | 1835708 | 22932 | 1858640 | 2000-01-30 | 0 | 2000-01-30
|  | Change Orders Approved | 72576 |  | Extended Time Approved | 13
|  | Revised Contract Amount | 1858640 |  | Revised Finish Date | 2000-01-30
Formulas:
ORIGINAL = +[REVISED, row above]
REVISED = +[ORIGINAL]+[CHANGES]

## Architect
Architects Directory
| 1 | none
| 2 | Peter Pivko Architects
| 3 | Murray and Murray Architects
| 4 | Benson Designs Corporation
| 5 | Holland Architectural Group
| 6 | Mars Design Associates
| 7 | Brydon Architects and Associates
| 8 | A-B-D Designers and Engineers
| 9 | G/A Architects and Designers
| 10 | Carver Engineers and Architects
| 11 | Robert Architects
9

## CSI
MASTERFORMAT
DIVISION 1 GENERAL CONDITIONS
DIVISION 1 GENERAL CONDITIONS | 100 | Instruction To Bidders
DIVISION 1 GENERAL CONDITIONS | 225 | Geotechnical Report
DIVISION 1 GENERAL CONDITIONS | 1001 | General Requirements
DIVISION 1 GENERAL CONDITIONS | 1010 | Summary
DIVISION 1 GENERAL CONDITIONS | 1021 | Allowances
DIVISION 1 GENERAL CONDITIONS | 1030 | Alternatives
DIVISION 1 GENERAL CONDITIONS | 1041 | Project Coordination
DIVISION 1 GENERAL CONDITIONS | 1045 | Cutting and Patching
DIVISION 1 GENERAL CONDITIONS | 1200 | Project Meetings
DIVISION 1 GENERAL CONDITIONS | 1300 | Submittals
DIVISION 1 GENERAL CONDITIONS | 1310 | Construction Schedule
DIVISION 1 GENERAL CONDITIONS | 1400 | Quality Control
DIVISION 1 GENERAL CONDITIONS | 1501 | Temporary Work
DIVISION 1 GENERAL CONDITIONS | 1510 | Temporary Utilities
DIVISION 1 GENERAL CONDITIONS | 1535 | Temporary Facilities
DIVISION 1 GENERAL CONDITIONS | 1560 | Temporary Controls
DIVISION 1 GENERAL CONDITIONS | 1601 | Material and Equipment
DIVISION 1 GENERAL CONDITIONS | 1655 | Facility Start-Up
DIVISION 1 GENERAL CONDITIONS | 1660 | Testing, Adjusting and Balancing of Systems
DIVISION 1 GENERAL CONDITIONS | 1700 | Contract Closeout
DIVISION 1 GENERAL CONDITIONS | 1711 | Cleaning
DIVISION 1 GENERAL CONDITIONS | 1750 | Maintenance Materials
DIVISION 2 SITEWORK | 2060 | Demolition of Structures
DIVISION 2 SITEWORK | 2080 | Asbestos Abatement
DIVISION 2 SITEWORK | 2104 | Shrub and Trees Preservation
DIVISION 2 SITEWORK | 2111 | Clearing and Grubbing
DIVISION 2 SITEWORK | 2151 | Bracing and Shoring
DIVISION 2 SITEWORK | 2210 | Site Grading
DIVISION 2 SITEWORK | 2211 | Rock Removal
DIVISION 2 SITEWORK | 2223 | Excavation, Trenching and Backfilling
DIVISION 2 SITEWORK | 2233 | Granular Base
DIVISION 2 SITEWORK | 2234 | Granular Sub-Base
DIVISION 2 SITEWORK | 2242 | Dust Control
DIVISION 2 SITEWORK | 2271 | Rip-Rap
DIVISION 2 SITEWORK | 2351 | Pile Foundation
DIVISION 2 SITEWORK | 2363 | Steel Pipe Piles
DIVISION 2 SITEWORK | 2366 | Steel H Pipe
DIVISION 2 SITEWORK | 2487 | Steel Sheet Pile
DIVISION 2 SITEWORK | 2498 | Geotextiles
DIVISION 2 SITEWORK | 2512 | Hot Mix Asphalt Paving
DIVISION 2 SITEWORK | 2515 | Unit Pavers
DIVISION 2 SITEWORK | 2523 | Concrete Walks and Curbs
DIVISION 2 SITEWORK | 2526 | Precast Parking Curbs
DIVISION 2 SITEWORK | 2666 | Water Mains
DIVISION 2 SITEWORK | 2710 | Sub Drainage
DIVISION 2 SITEWORK | 2721 | Storm Sewers
DIVISION 2 SITEWORK | 2725 | Manholes and Catch Basins
DIVISION 2 SITEWORK | 2731 | Storm Sewers
DIVISION 2 SITEWORK | 2831 | Chain Link Fence and Gate
DIVISION 2 SITEWORK | 2870 | Site Furnishings
DIVISION 2 SITEWORK | 2921 | Top Soil and Finish Grading
DIVISION 2 SITEWORK | 2933 | Seeding
DIVISION 2 SITEWORK | 2939 | Sodding
DIVISION 2 SITEWORK | 2950 | Trees, Shrubs and Plants
DIVISION 3 CONCRETE | 3100 | Concrete Formwork and Falsework
DIVISION 3 CONCRETE | 3200 | Concrete Reinforcement
DIVISION 3 CONCRETE | 3300 | Cast-In-Place Concrete
DIVISION 3 CONCRETE | 3345 | Concrete Floor Finish
DIVISION 3 CONCRETE | 3365 | Post Tensioning
DIVISION 3 CONCRETE | 3410 | Precast Structural Concrete
DIVISION 3 CONCRETE | 3450 | Precast Architectural Concrete
DIVISION 3 CONCRETE | 3900 | Concrete Accessories
DIVISION 4 MASONRY | 4050 | Masonry Prcedures
DIVISION 4 MASONRY | 4100 | Mortar and Grout for Masonry
DIVISION 4 MASONRY | 4160 | Masonry Accessories
DIVISION 4 MASONRY | 4210 | Brick Masonry
DIVISION 4 MASONRY | 4220 | Concrete Unit Masonry
DIVISION 4 MASONRY | 4465 | Granite
DIVISION 5 STEEL | 5120 | Structural Steel
DIVISION 5 STEEL | 5210 | Steel Joists
DIVISION 5 STEEL | 5311 | Steel Deck
DIVISION 5 STEEL | 5500 | Metal Fabrication
DIVISION 5 STEEL | 5501 | Embeddments
DIVISION 5 STEEL | 5502 | Loose Lintels
DIVISION 5 STEEL | 5503 | Plates
DIVISION 5 STEEL | 5502 | Handrail
DIVISION 5 STEEL | 5510 | Metal Stairs
DIVISION 5 STEEL | 5810 | Expansion Joint Cover
DIVISION 6 WOOD and PLASTICS | 6100 | Rough Carpentry
DIVISION 6 WOOD and PLASTICS | 6192 | Prefabricated Wood Trusses
DIVISION 6 WOOD and PLASTICS | 6200 | Finish Carpentry
DIVISION 6 WOOD and PLASTICS | 6240 | Laminated Plastic
DIVISION 6 WOOD and PLASTICS | 6400 | Architectural Woodwork
DIVISION 7 THERMAL PROTECTION | 7111 | Elastomeric Sheet Membrane Waterproofing
DIVISION 7 THERMAL PROTECTION | 7122 | Hot Applied Rubberized Asphalt Waterproofing
DIVISION 7 THERMAL PROTECTION | 7130 | Bentonite Waterproofing
DIVISION 7 THERMAL PROTECTION | 7160 | Bituminous Damproofing
DIVISION 7 THERMAL PROTECTION | 7190 | Sheet Vapour Barrier
DIVISION 7 THERMAL PROTECTION | 7211 | Loose Fill Insulation
DIVISION 7 THERMAL PROTECTION | 7212 | Board Insulation
DIVISION 7 THERMAL PROTECTION | 7213 | Batt and Blanket Insulation
DIVISION 7 THERMAL PROTECTION | 7250 | Fireproofing
DIVISION 7 THERMAL PROTECTION | 7510 | Built-Up Bituminous Roofing
DIVISION 7 THERMAL PROTECTION | 7570 | Traffic Topping
DIVISION 7 THERMAL PROTECTION | 7620 | Metal Flashing and Trim
DIVISION 7 THERMAL PROTECTION | 7900 | Sealants
DIVISION 8 WINDOWS and DOORS | 8111 | Steel Doors and Frames
DIVISION 8 WINDOWS and DOORS | 8120 | Aluminum Doors and Frames
DIVISION 8 WINDOWS and DOORS | 8210 | Wood Doors
DIVISION 8 WINDOWS and DOORS | 8213 | Plastic Faced Wood Doors
DIVISION 8 WINDOWS and DOORS | 8311 | Sliding Glass Doors: Aluminum
DIVISION 8 WINDOWS and DOORS | 8320 | Metal Clad Doors
DIVISION 8 WINDOWS and DOORS | 8351 | According Folding Doors
DIVISION 8 WINDOWS and DOORS | 8352 | Panel Folding Doors
DIVISION 8 WINDOWS and DOORS | 8521 | Windows
DIVISION 8 WINDOWS and DOORS | 8710 | Finish Hardware
DIVISION 8 WINDOWS and DOORS | 8800 | Glazing
DIVISION 9 FINISHES | 9111 | Metal Stud System
DIVISION 9 FINISHES | 9130 | Suspension System -Acoustic Ceilings
DIVISION 9 FINISHES | 9250 | Gypsum Board
DIVISION 9 FINISHES | 9310 | Ceramic Tile
DIVISION 9 FINISHES | 9330 | Quarry Tile
DIVISION 9 FINISHES | 9511 | Acoustical Panels and Tiles
DIVISION 9 FINISHES | 9517 | Metal Linear Ceilings
DIVISION 9 FINISHES | 9520 | Acoustic Wall Treatment
DIVISION 9 FINISHES | 9560 | Wood Flooring
DIVISION 9 FINISHES | 9660 | Resilient Tile Flooring
DIVISION 9 FINISHES | 9665 | Resilient Sheet Flooring
DIVISION 9 FINISHES | 9680 | Carpeting
DIVISION 9 FINISHES | 9900 | Painting
DIVISION 9 FINISHES | 9955 | Vinyl Coated Fabric Wall Covering
DIVISION 10 SPECIALTIES | 10110 | Chalkboards
DIVISION 10 SPECIALTIES | 10120 | Tackboards
DIVISION 10 SPECIALTIES | 10160 | Metal Partitions
DIVISION 10 SPECIALTIES | 10165 | Laminated Plastic Toilet Partitions
DIVISION 10 SPECIALTIES | 10185 | Shower and Dressing Compartments
DIVISION 10 SPECIALTIES | 10200 | Louvre and Vents
DIVISION 10 SPECIALTIES | 10260 | Wall and Corner Guards
DIVISION 10 SPECIALTIES | 10270 | Access Flooring
DIVISION 10 SPECIALTIES | 10350 | Flag Poles
DIVISION 10 SPECIALTIES | 10500 | Lockers
DIVISION 10 SPECIALTIES | 10616 | Demountable Partitions
DIVISION 10 SPECIALTIES | 10655 | According Folding Partitions
DIVISION 10 SPECIALTIES | 10675 | Metal Storage Shelving
DIVISION 10 SPECIALTIES | 10800 | Toilet and Bath Accessories
DIVISION 11 EQUIPMENT | 11021 | Vault Doors and Frames
DIVISION 11 EQUIPMENT | 11150 | Parking Equipment
DIVISION 11 EQUIPMENT | 11161 | Dock Levellers
DIVISION 11 EQUIPMENT | 11165 | Dock Bumpers
DIVISION 11 EQUIPMENT | 11405 | Prefabricated Walk-In Freezers
DIVISION 11 EQUIPMENT | 11408 | Food Service Catalogued Equipment
DIVISION 12 FURNISHINGS | 12346 | Steel Laboratory Casework
DIVISION 12 FURNISHINGS | 12511 | Vertical Louvre Blinds
DIVISION 12 FURNISHINGS | 12512 | Horizontal Louvre Blinds
DIVISION 12 FURNISHINGS | 12522 | Light-proof Shades
DIVISION 12 FURNISHINGS | 12801 | Interior Planting
DIVISION 13 SPECIAL CONSTRUCTION | 13126 | Steel Building Systems
DIVISION 13 SPECIAL CONSTRUCTION | 13127 | Prefabricated Buildings
DIVISION 13 SPECIAL CONSTRUCTION | 13500 | Integrated Ceiling
DIVISION 14 CONVEYING SYSTEMS | 14250 | Hydraulic Elevators
DIVISION 14 CONVEYING SYSTEMS | 14260 | Electric Elevators
DIVISION 14 CONVEYING SYSTEMS | 14610 | Escalators
DIVISION 14 CONVEYING SYSTEMS | 14720 | Moving Walks
DIVISION 15 MECHANICAL - Plumbing | 15010 | Mechanical General Requirements
DIVISION 15 MECHANICAL - Plumbing | 15260 | Insulation For Piping
DIVISION 15 MECHANICAL - Plumbing | 15305 | Portable Fire Extinguishers
DIVISION 15 MECHANICAL - Plumbing | 15330 | Wet Sprinkler System
DIVISION 15 MECHANICAL - Plumbing | 15335 | Dry Sprinkler System
DIVISION 15 MECHANICAL - Plumbing | 15412 | Water Supply
DIVISION 15 MECHANICAL - Plumbing | 15413 | Drainage Waste
DIVISION 15 MECHANICAL - Plumbing | 15440 | Plumbing Fiztures
DIVISION 15 MECHANICAL - Plumbing | 15452 | Pumps
DIVISION 15 MECHANICAL - Plumbing | 15456 | Pipe Fittings and Valves
DIVISION 15 MECHANICAL - Plumbing | 15551 | Oil Storage Tanks
DIVISION 15 MECHANICAL - Heating | 15610 | Forced Warm Air Furnaces
DIVISION 15 MECHANICAL - Heating | 15681 | Chillers
DIVISION 15 MECHANICAL - Heating | 15755 | Heat Exchangers
DIVISION 15 MECHANICAL - Heating | 15782 | Rooftop HVAC Units
DIVISION 15 MECHANICAL - Heating | 15801 | Ductwork
DIVISION 15 MECHANICAL - Heating | 15825 | Dampers
DIVISION 15 MECHANICAL - Heating | 15851 | Louvres and Vents
DIVISION 15 MECHANICAL - Heating | 15860 | Commercial Fans
DIVISION 15 MECHANICAL - Heating | 15869 | Exhaust Hoods
DIVISION 15 MECHANICAL - Heating | 15870 | Wall Exhausters
DIVISION 15 MECHANICAL - Heating | 15875 | Grilles and Diffusers
DIVISION 15 MECHANICAL - Heating | 15885 | Built-In Vacuflow
DIVISION 16 - ELECTRICAL | 16100 | Electrical
DIVISION 16 - ELECTRICAL | 16105 | Encased Duct Banks
DIVISION 16 - ELECTRICAL | 16111 | Conduits
DIVISION 16 - ELECTRICAL | 16114 | Cabletroughs
DIVISION 16 - ELECTRICAL | 16115 | Busways
DIVISION 16 - ELECTRICAL | 16122 | Wires and Cables
DIVISION 16 - ELECTRICAL | 16132 | Outlet Boxes
DIVISION 16 - ELECTRICAL | 16311 | Unit Substation
DIVISION 16 - ELECTRICAL | 16321 | Distribution Transformer
DIVISION 16 - ELECTRICAL | 16323 | Pad Mounted Distribution Transformer
DIVISION 16 - ELECTRICAL | 16350 | Circuit Breakers
DIVISION 16 - ELECTRICAL | 16401 | Overhead Service
DIVISION 16 - ELECTRICAL | 16402 | Underground
DIVISION 16 - ELECTRICAL | 16421 | Service Entrance Board
DIVISION 16 - ELECTRICAL | 16471 | Panelboard Breaker Type
DIVISION 16 - ELECTRICAL | 16478 | Fuses
DIVISION 16 - ELECTRICAL | 16505 | Lighting Equipment
DIVISION 16 - ELECTRICAL | 16519 | Exit Lights
DIVISION 16 - ELECTRICAL | 16536 | Emergency Lighting
DIVISION 16 - ELECTRICAL | 16550 | Street Lighting Poles
DIVISION 16 - ELECTRICAL | 16721 | Fire Alarm System
DIVISION 16 - ELECTRICAL | 16726 | Building Entrance Control System
DIVISION 16 - ELECTRICAL | 16770 | Public Address
DIVISION 16 - ELECTRICAL | 16851 | Electric Heating and Cooling Controls
DIVISION 16 - ELECTRICAL | 16870 | Unit Heaters
DIVISION 16 - ELECTRICAL | 16896 | Electric Forced Air Furnace

## Sheet1
Tuesay Morning Class