## Cover Page
PM in Action
Welcome to the Progress Claim Tracker. This excel sheet is used to track Progress Claims for a commercial construction project.
Please fill in the following information
General Contractors Name: | Project Innovations Incorporation
Gen Contractor's Address: | 12 Canoteck Road, Ottawa, Ontario
Owner's Name: | Highland Development Corporation
Your Project Name: | Bells Aerobic and Fitness Center
Your Project Number: | 2012-69
Project Address: | 123 Front Street, Brockville, Ontario
Project Architectural Firm:
Architect Contact: | Karen Jackson
Project Manager: | Matthew Coulson, Jordan Melo
November 27, 2014 format
PROGRESS CLAIM TRACKER
Note on D15: If Architect's name is not in the list please go to Architect Sheet and enter their name.

## Summary of Estimate
Project Innovations Incorporation
SUMMARY OF THE ESTIMATE
| Your Project Name: | Bells Aerobic and Fitness Center
| Project Architectural Firm: | G/A Architects & Designers
SECTIONS
| General Conditions |  | 160250
| Sitework |  | 28500
| Excavation |  | 36540
| Concrete/Formwork |  | 154250
| Masonry |  | 85450
| Roofing and Flashing |  | 67405
| Drywall |  | 68500
| Painting |  | 38500
| Mirrors |  | 12500
| Flooring |  | 56222
| Specialties |  | 75600
| Electrical |  | 285250
| Mechanical |  | 345750
|  | Sub Total | 1414717
| Overhead | 16% | 226354.72
| Profit | 8% | 113177.36
|  | Total | 1754249.08
FOR THE
GENERAL
CONTRACTORS
EYES ONLY
From the Summary of the Estimate on the paper handout enter the Sections (beginning at General Conditions, Amounts and Overhead and Profit!
Note on C8: Enter section name here.
Note on E8: Enter section amount here.
Note on C9: Enter section name here.
Note on E9: Enter section amount here.
Note on C10: Enter section name here.
Note on E10: Enter section amount here.
Note on C11: Enter section name here.
Note on E11: Enter section amount here.
Note on C12: Enter section name here.
Note on E12: Enter section amount here.
Note on C13: Enter section name here.
Note on E13: Enter section amount here.
Note on C14: Enter section name here.
Note on E14: Enter section amount here.
Note on C15: Enter section name here.
Note on E15: Enter section amount here.
Note on C16: Enter section name here.
Note on E16: Enter section amount here.
Note on C17: Enter section name here.
Note on E17: Enter section amount here.
Note on C18: Enter section name here.
Note on E18: Enter section amount here.
Note on C19: Enter section name here.
Note on E19: Enter section amount here.
Note on C20: Enter section name here.
Note on E20: Enter section amount here.
Note on D22: Enter Overhead %
Note on D23: Enter Profit %

## Calculations
Front End Loading Calculation
| Overhead | 226354.72
| Profit | 113177.36
| Distributed Costs | 339532.08
| Total Construction Cost | 1754249.08
| Less Distributed Cost | 339532.08
1414717
Distributed Costs
| Excavation | 28500 | / | 1414717 | = | 2.015%
| New Excavation Value | 2.015% | of | 1754249.08 | = | 35340
| Concrete & Formwork | 36540 | / | 1414717 | = | 2.583%
| New Concrete & Form Value | 2.583% | of | 1754249.08 | = | 45309.6
| Masonry | 154250 | / | 1414717 | = | 10.9%
| New Masonry Value | 10.9% | of | 1754249.08 | = | 191270
| Structural Steel | 85450 | / | 1414717 | = | 6.04%
| New Structural Steel Value | 6.04% | of | 1754249.08 | = | 105958
| Insulation & Roofing | 67405 | / | 1414717 | = | 4.765%
| New Insul & Roof Value | 4.765% | of | 1754249.08 | = | 83582.2
| Drywall Finishes | 68500 | / | 1414717 | = | 4.842%
| New Ddrywall Value | 4.842% | of | 1754249.08 | = | 84940
| Hardware | 38500 | / | 1414717 | = | 2.721%
| New Hardware Value | 2.721% | of | 1754249.08 | = | 47740
| Carpentry | 12500 | / | 1414717 | = | 0.8836%
| New Carpentry Value | 0.8836% | of | 1754249.08 | = | 15500
| Painting | 56222 | / | 1414717 | = | 3.974%
| New Painting Value | 3.974% | of | 1754249.08 | = | 69715.28
| Flooring | 75600 | / | 1414717 | = | 5.344%
| New Flooring Value | 5.344% | of | 1754249.08 | = | 93744
| Electrical | 285250 | / | 1414717 | = | 20.16%
| New Electrical Value | 20.16% | of | 1754249.08 | = | 353710
| Mechanical | 345750 | / | 1414717 | = | 24.44%
| New Mechanical Value | 24.44% | of | 1754249.08 | = | 428730
| General Conditions | 160250 | / | 1414717 | = | 11.33%
| New General Conditions Value | 11.33% | of | 1754249.08 | = | 198710
Nothing to do here but feast your eyes on the distributed costs.

## Schedule of Value
Project Innovations Incorporation
SCHEDULE of VALUES
| Your Project Name: | Bells Aerobic and Fitness Center
| Project Architectural Firm: | G/A Architects & Designers
SECTIONS
| General Conditions | 198710
| Sitework | 35340
| Excavation | 45309.6
| Concrete/Formwork | 191270
| Masonry | 105958
| Roofing and Flashing | 83582.2
| Drywall | 84940
| Painting | 47740
| Mirrors | 15500
| Flooring | 69715.28
| Specialties | 93744
| Electrical | 353710
| Mechanical | 428730
1754249.08
FOR THE
CONSULTANTS
EYES AS PER
CCDC CONTRACTS
Nothing to do here but feast your eyes on the distributed costs.

## Prog Bill 1
Project Innovations Incorporation
|  |  |  | PROGESS BILLING FOR MONTH OF | 1999-04-30
| Owner: | Bells Aerobic and Fitness Center
| Project #: | 2012-69
| Architect: | G/A Architects & Designers
| Date: | 1999-04-30 |  |  |  |  | Claim # | 1
|  |  | Schedule | % Completed |  |  | Amount
| SECTIONS |  | Values | Total | Current | Previous | Total | Current | Previous
| General Conditions |  | 198710 | 20% | 20% | 0% | 39742 | 39742 | 0
| Sitework |  | 35340 | 25% | 25% | 0% | 8835 | 8835 | 0
| Excavation |  | 45309.6 | 95% | 95% | 0% | 43044.12 | 43044.12 | 0
| Concrete/Formwork |  | 191270 | 8% | 8% | 0% | 15301.6 | 15301.6 | 0
| Masonry |  | 105958 | 0% | 0% | 0% | 0 | 0 | 0
| Roofing and Flashing |  | 83582.2 | 0% | 0% | 0% | 0 | 0 | 0
| Drywall |  | 84940 | 0% | 0% | 0% | 0 | 0 | 0
| Painting |  | 47740 | 0% | 0% | 0% | 0 | 0 | 0
| Mirrors |  | 15500 | 0% | 0% | 0% | 0 | 0 | 0
| Flooring |  | 69715.28 | 0% | 0% | 0% | 0 | 0 | 0
| Specialties |  | 93744 | 0% | 0% | 0% | 0 | 0 | 0
| Electrical |  | 353710 | 5% | 5% | 0% | 17685.5 | 17685.5 | 0
| Mechanical |  | 428730 | 0% | 0% | 0% | 0 | 0 | 0
|  | Total Contract | 1754249.08 |  |  |  | 124608.22 | 124608.22 | 0
|  | Change Orders This Claim | 18585
|  | Change Orders To Date | 18585 | 12% | 12% | 0% | 2230.2 | 2230.2 | 0
|  | Revised Contract Amount | 1772834.08 |  |  |  | 126838.42 | 126838.42 | 0
|  | Builer's Lien Holdback |  |  |  |  | 12683.842 | 12683.842 | 0
|  | TOTAL RECEIVABLE |  |  |  |  | 114154.578 | 114154.578 | 0
|  | Paid To Date |  |  |  |  | 0 |  | 0
|  | NET RECEIVABLE |  |  |  |  | 114154.578 | 114154.578 | 0
Note on G5: DO NOT ENTER ANY DATES HERE. THIS MEANS YOU.
Note on D10: Enter the date of the Progrress Claim.
Note on E29: Enter Change Order approved this moonth here!

## Cert 1
G/A Architects & Designers
Consulting Engineers and Architects |  |  |  | Certificate For Payment
234 Maple Road, Kingston, Ontario
TO: | Project Innovations Incorporation |  | Project: |  | Bells Aerobic and Fitness Center
| 12 Canoteck Road, Ottawa, Ontario |  | Project No.: |  | 2012-69
| Belleville, Ontario |  | Date Issued: |  | 1999-04-30
|  |  | Certificate No.: |  | 1
We hereby certify that in accordance with your contract with the owner
Highland Development Corporation
the contractor
Project Innovations Incorporation
|  |  | to entitled to payment in the amount of |  | 114154.578 | for work performed.
PRESENT STATUS OF ACCOUNT:
| Original Contract Sum |  | 1754249.08
| Authorized Change Orders |  | 0
| Balance |  | 1754249.08
|  |  | Revised Contract Sum |  |  | 1754249.08
|  |  | Less Certificates To Date |  |  | 0
|  |  | Balance Not Certified |  |  | 1754249.08
| Value of Work Furnished |  | 126838.42
| Less 10% Holdback |  | 12683.842
114154.578
| Add Holdback Released |  | 0
114154.578
| Less Previous Certificates |  | 0
| Amount of This Certificate |  | 114154.578 |  |  | 114154.578
| Architect: | Karen Jackson
| Title: | Associate Architect

## Prog Bill 2
Project Innovations Incorporation
|  |  |  | PROGESS BILLING FOR MONTH OF | 1999-05-30
| Owner: | Bells Aerobic and Fitness Center
| Project #: | 2012-69
| Architect: | G/A Architects & Designers
| Date: | 1999-05-30 |  |  |  |  | Claim # | 2
|  |  | Schedule | % Completed |  |  | Amount
| SECTIONS |  | Values | Total | Current | Previous | Total | Current | Previous
| General Conditions |  | 198710 | 40% | 20% | 20% | 79484 | 39742 | 39742
| Sitework |  | 35340 | 40% | 15% | 25% | 14136 | 5301 | 8835
| Excavation |  | 45309.6 | 100% | 5% | 95% | 45309.6 | 2265.48 | 43044.12
| Concrete/Formwork |  | 191270 | 100% | 92% | 8% | 191270 | 175968.4 | 15301.6
| Masonry |  | 105958 | 75% | 75% | 0% | 79468.5 | 79468.5 | 0
| Roofing and Flashing |  | 83582.2 | 95% | 95% | 0% | 79403.09 | 79403.09 | 0
| Drywall |  | 84940 | 2% | 2% | 0% | 1698.8 | 1698.8 | 0
| Painting |  | 47740 | 0% | 0% | 0% | 0 | 0 | 0
| Mirrors |  | 15500 | 0% | 0% | 0% | 0 | 0 | 0
| Flooring |  | 69715.28 | 0% | 0% | 0% | 0 | 0 | 0
| Specialties |  | 93744 | 0% | 0% | 0% | 0 | 0 | 0
| Electrical |  | 353710 | 20% | 15% | 5% | 70742 | 53056.5 | 17685.5
| Mechanical |  | 428730 | 0% | 0% | 0% | 0 | 0 | 0
|  | Total Contract | 1754249.08 |  |  |  | 561511.99 | 436903.77 | 124608.22
|  | Change Orders To Date | 18585
|  | Change Order This Period | 36288
|  | Change Orders Total | 54873 | 38% | 26% | 12% | 20851.74 | 18621.54 | 2230.2
|  | Revised Contract | 1809122.08 |  |  |  | 582363.73 | 455525.31 | 126838.42
|  | Builer's Lien Holdback |  |  |  |  | 58236.373 | 45552.531 | 12683.842
|  | TOTAL RECEIVABLE |  |  |  |  | 524127.357 | 409972.779 | 114154.578
|  | Paid To Date |  |  |  |  | 114154.578 |  | 114154.578
|  | NET RECEIVABLE |  |  |  |  | 409972.779 | 409972.779 | 0
Note on E30: Enter Change Order approved this moonth here!

## Cert 2
G/A Architects & Designers
Consulting Engineers and Architects |  |  |  | Certificate For Payment
234 Maple Road, Kingston, Ontario
TO: | Project Innovations Incorporation |  | Project: |  | Highland Development Corporation
| 234 Baycrest Park |  | Project No.: |  | 2012-69
| Belleville, Ontario |  | Date Issued: |  | 1999-05-30
|  |  | Certificate No.: |  | 2
We hereby certify that in accordance with your contract with the owner
Highland Development Corporation
the contractor
Project Innovations Incorporation
|  |  | to entitled to payment in the amount of |  | 409972.779 | for work performed.
PRESENT STATUS OF ACCOUNT:
| Original Contract Sum |  | 1754249.08
| Authorized Change Orders |  | 54873
| Balance |  | 1809122.08
|  |  | Revised Contract Sum |  |  | 1809122.08
|  |  | Less Certificates To Date |  |  | 0
|  |  | Balance Not Certified |  |  | 1809122.08
| Value of Work Furnished |  | 582363.73
| Less 10% Holdback |  | 58236.373
524127.357
| Add Holdback Released |  | 0
524127.357
| Less Previous Certificates |  | 114154.578
| Amount of This Certificate |  | 409972.779 |  |  | 409972.779
| Architect: | Karen Jackson
| Title: | Associate Architect

## Prog Bill 3
Project Innovations Incorporation
|  |  |  | PROGESS BILLING FOR MONTH OF | 1999-06-29
| Owner: | Bells Aerobic and Fitness Center
| Project #: | 2012-69
| Architect: | 1999-06-29
| Date: | 1999-06-29 |  |  |  |  | Claim # | 3
|  |  | Schedule | % Completed |  |  | Amount
| SECTIONS |  | Values | Total | Current | Previous | Total | Current | Previous
| General Conditions |  | 198710 | 60% | 20% | 40% | 119226 | 39742 | 79484
| Sitework |  | 35340 | 55% | 15% | 40% | 19437 | 5301 | 14136
| Excavation |  | 45309.6 | 100% | 0% | 100% | 45309.6 | 0 | 45309.6
| Concrete/Formwork |  | 191270 | 100% | 0% | 100% | 191270 | 0 | 191270
| Masonry |  | 105958 | 95% | 20% | 75% | 100660.1 | 21191.6 | 79468.5
| Roofing and Flashing |  | 83582.2 | 100% | 5% | 95% | 83582.2 | 4179.11 | 79403.09
| Drywall |  | 84940 | 77% | 75% | 2% | 65403.8 | 63705 | 1698.8
| Painting |  | 47740 | 80% | 80% | 0% | 38192 | 38192 | 0
| Mirrors |  | 15500 | 25% | 25% | 0% | 3875 | 3875 | 0
| Flooring |  | 69715.28 | 0% | 0% | 0% | 0 | 0 | 0
| Specialties |  | 93744 | 0% | 0% | 0% | 0 | 0 | 0
| Electrical |  | 353710 | 35% | 15% | 20% | 123798.5 | 53056.5 | 70742
| Mechanical |  | 428730 | 20% | 20% | 0% | 85746 | 85746 | 0
|  | Total Contract | 1754249.08 |  |  |  | 876500.2 | 314988.21 | 561511.99
|  | Change Orders To Date | 54873
|  | Change Order This Period | 26586
|  | Change Orders Total | 81459 | 55% | 17% | 38% | 44802.45 | 23950.71 | 2230.2
|  | Revised Contract | 1835708.08 |  |  |  | 921302.65 | 338938.92 | 563742.19
|  | Builer's Lien Holdback |  |  |  |  | 92130.265 | 33893.892 | 56374.219
|  | TOTAL RECEIVABLE |  |  |  |  | 829172.385 | 305045.028 | 524127.357
|  | Paid To Date |  |  |  |  | 524127.357 |  | 524127.357
|  | NET RECEIVABLE |  |  |  |  | 305045.028 | 305045.028 | 0
Note on E30: Enter Change Order approved this moonth here!

## Cert 3
G/A Architects & Designers
Consulting Engineers and Architects |  |  |  | Certificate For Payment
234 Maple Road, Kingston, Ontario
TO: | Project Innovations Incorporation |  | Project: |  | Highland Development Corporation
| 234 Baycrest Park |  | Project No.: |  | 2012-69
| Belleville, Ontario |  | Date Issued: |  | 1999-06-29
|  |  | Certificate No.: |  | 3
We hereby certify that in accordance with your contract with the owner
Highland Development Corporation
the contractor
Project Innovations Incorporation
|  |  | to entitled to payment in the amount of |  | 305045.028 | for work performed.
PRESENT STATUS OF ACCOUNT:
| Original Contract Sum |  | 1754249.08
| Authorized Change Orders |  | 81459
| Balance |  | 1835708.08
|  |  | Revised Contract Sum |  |  | 1835708.08
|  |  | Less Certificates To Date |  |  | 0
|  |  | Balance Not Certified |  |  | 1835708.08
| Value of Work Furnished |  | 921302.65
| Less 10% Holdback |  | 92130.265
829172.385
| Add Holdback Released |  | 0
829172.385
| Less Previous Certificates |  | 524127.357
| Amount of This Certificate |  | 305045.028 |  |  | 305045.028
| Architect: | Karen Jackson
| Title: | Associate Architect

## Prog Bill 4
Project Innovations Incorporation
|  |  |  | PROGESS BILLING FOR MONTH OF | 1999-07-29
| Owner: | Bells Aerobic and Fitness Center
| Project #: | 2012-69
| Architect: | G/A Architects & Designers
| Date: | 1999-07-29 |  |  |  |  | Claim # | 4
|  |  | Schedule | % Completed |  |  | Amount
| SECTIONS |  | Values | Total | Current | Previous | Total | Current | Previous
| General Conditions |  | 198710 | 80% | 20% | 60% | 158968 | 39742 | 119226
| Sitework |  | 35340 | 70% | 15% | 55% | 24738 | 5301 | 19437
| Excavation |  | 45309.6 | 100% | 0% | 100% | 45309.6 | 0 | 45309.6
| Concrete/Formwork |  | 191270 | 100% | 0% | 100% | 191270 | 0 | 191270
| Masonry |  | 105958 | 100% | 5% | 95% | 105958 | 5297.9 | 100660.1
| Roofing and Flashing |  | 83582.2 | 100% | 0% | 100% | 83582.2 | 0 | 83582.2
| Drywall |  | 84940 | 100% | 23% | 77% | 84940 | 19536.2 | 65403.8
| Painting |  | 47740 | 90% | 10% | 80% | 42966 | 4774 | 38192
| Mirrors |  | 15500 | 80% | 55% | 25% | 12400 | 8525 | 3875
| Flooring |  | 69715.28 | 65% | 65% | 0% | 45314.932 | 45314.932 | 0
| Specialties |  | 93744 | 15% | 15% | 0% | 14061.6 | 14061.6 | 0
| Electrical |  | 353710 | 60% | 25% | 35% | 212226 | 88427.5 | 123798.5
| Mechanical |  | 428730 | 40% | 20% | 20% | 171492 | 85746 | 85746
|  | Total Contract | 1754249.08 |  |  |  | 1193226.332 | 316726.132 | 876500.2
|  | Change Orders To Date | 81459
|  | Change Order This Period | 22932
|  | Change Orders Total | 104391 | 65% | 10% | 55% | 67854.15 | 23051.7 | 44802.45
|  | Revised Contract | 1858640.08 |  |  |  | 1261080.482 | 339777.832 | 921302.65
|  | Builder's Lien Holdback |  |  |  |  | 126108.0482 | 33977.7832 | 92130.265
|  | TOTAL RECEIVABLE |  |  |  |  | 1134972.4338 | 305800.0488 | 829172.385
|  | Paid To Date |  |  |  |  | 829172.385 |  | 829172.385
|  | NET RECEIVABLE |  |  |  |  | 305800.0488 | 305800.0488 | 0
Note on E30: Enter Change Order approved this moonth here!

## Cert 4
G/A Architects & Designers
Consulting Engineers and Architects |  |  |  | Certificate For Payment
234 Maple Road, Kingston, Ontario
TO: | Project Innovations Incorporation |  | Project: |  | Highland Development Corporation
| 234 Baycrest Park |  | Project No.: |  | 2012-69
| Belleville, Ontario |  | Date Issued: |  | 1999-07-29
|  |  | Certificate No.: |  | 4
We hereby certify that in accordance with your contract with the owner
Highland Development Corporation
the contractor
Project Innovations Incorporation
|  |  | to entitled to payment in the amount of |  | 305800.0488 | for work performed.
PRESENT STATUS OF ACCOUNT:
| Original Contract Sum |  | 1754249.08
| Authorized Change Orders |  | 104391
| Balance |  | 1858640.08
|  |  | Revised Contract Sum |  |  | 1858640.08
|  |  | Less Certificates To Date |  |  | 0
|  |  | Balance Not Certified |  |  | 1858640.08
| Value of Work Furnished |  | 1261080.482
| Less 10% Holdback |  | 126108.0482
1134972.4338
| Add Holdback Released |  | 0
1134972.4338
| Less Previous Certificates |  | 829172.385
| Amount of This Certificate |  | 305800.0488 |  |  | 305800.0488
| Architect: | Karen Jackson
| Title: | Associate Architect

## Prog Bill 5
Project Innovations Incorporation
|  |  |  | PROGESS BILLING FOR MONTH OF | 1999-08-28
| Owner: | Bells Aerobic and Fitness Center
| Project #: | 2012-69
| Architect: | G/A Architects & Designers
| Date: | 1999-08-28 |  |  |  |  | Claim # | 5
|  |  | Schedule | % Completed |  |  | Amount
| SECTIONS |  | Values | Total | Current | Previous | Total | Current | Previous
| General Conditions |  | 198710 | 100% | 20% | 80% | 198710 | 39742 | 158968
| Sitework |  | 35340 | 90% | 20% | 70% | 31806 | 7068 | 24738
| Excavation |  | 45309.6 | 100% | 0% | 100% | 45309.6 | 0 | 45309.6
| Concrete/Formwork |  | 191270 | 100% | 0% | 100% | 191270 | 0 | 191270
| Masonry |  | 105958 | 100% | 0% | 100% | 105958 | 0 | 105958
| Roofing and Flashing |  | 83582.2 | 100% | 0% | 100% | 83582.2 | 0 | 83582.2
| Drywall |  | 84940 | 100% | 0% | 100% | 84940 | 0 | 84940
| Painting |  | 47740 | 95% | 5% | 90% | 45353 | 2387 | 42966
| Mirrors |  | 15500 | 90% | 10% | 80% | 13950 | 1550 | 12400
| Flooring |  | 69715.28 | 80% | 15% | 65% | 55772.224 | 10457.292 | 45314.932
| Specialties |  | 93744 | 55% | 40% | 15% | 51559.2 | 37497.6 | 14061.6
| Electrical |  | 353710 | 95% | 35% | 60% | 336024.5 | 123798.5 | 212226
| Mechanical |  | 428730 | 75% | 35% | 40% | 321547.5 | 150055.5 | 171492
|  | Total Contract | 1754249.08 |  |  |  | 1565782.224 | 372555.892 | 1193226.332
|  | Change Orders To Date | 104391
|  | Change Order This Period | 0
|  | Change Orders Total | 104391 | 87% | 22% | 65% | 90820.17 | 22966.02 | 67854.15
|  | Revised Contract | 1858640.08 |  |  |  | 1656602.394 | 395521.912 | 1261080.482
|  | Builer's Lien Holdback |  |  |  |  | 165660.2394 | 39552.1912 | 126108.0482
|  | TOTAL RECEIVABLE |  |  |  |  | 1490942.1546 | 355969.7208 | 1134972.4338
|  | Paid To Date |  |  |  |  | 1134972.4338 |  | 1134972.4338
|  | NET RECEIVABLE |  |  |  |  | 355969.7208 | 355969.7208 | 0
Note on E30: Enter Change Order approved this moonth here!

## Cert 5
G/A Architects & Designers
Consulting Engineers and Architects |  |  |  | Certificate For Payment
234 Maple Road, Kingston, Ontario
TO: | Project Innovations Incorporation |  | Project: |  | Highland Development Corporation
| 234 Baycrest Park |  | Project No.: |  | 2012-69
| Belleville, Ontario |  | Date Issued: |  | 1999-08-28
|  |  | Certificate No.: |  | 5
We hereby certify that in accordance with your contract with the owner
Highland Development Corporation
the contractor
Project Innovations Incorporation
|  |  | to entitled to payment in the amount of |  | 355969.7208 | for work performed.
PRESENT STATUS OF ACCOUNT:
| Original Contract Sum |  | 1754249.08
| Authorized Change Orders |  | 104391
| Balance |  | 1858640.08
|  |  | Revised Contract Sum |  |  | 1858640.08
|  |  | Less Certificates To Date |  |  | 0
|  |  | Balance Not Certified |  |  | 1858640.08
| Value of Work Furnished |  | 1656602.394
| Less 10% Holdback |  | 165660.2394
1490942.1546
| Add Holdback Released |  | 0
1490942.1546
| Less Previous Certificates |  | 1134972.4338
| Amount of This Certificate |  | 355969.7208 |  |  | 355969.7208
| Architect: | Karen Jackson
| Title: | Associate Architect

## Prog Bill 6
Project Innovations Incorporation
|  |  |  | PROGESS BILLING FOR MONTH OF | 1999-09-27
| Owner: | Bells Aerobic and Fitness Center
| Project #: | 2012-69
| Architect: | G/A Architects & Designers
| Date: | 1999-09-27 |  |  |  |  | Claim # | 6
|  |  | Schedule | % Completed |  |  | Amount
| SECTIONS |  | Values | Total | Current | Previous | Total | Current | Previous
| General Conditions |  | 198710 | 100% | 0% | 100% | 198710 | 0 | 198710
| Sitework |  | 35340 | 100% | 10% | 90% | 35340 | 3534 | 31806
| Excavation |  | 45309.6 | 100% | 0% | 100% | 45309.6 | 0 | 45309.6
| Concrete/Formwork |  | 191270 | 100% | 0% | 100% | 191270 | 0 | 191270
| Masonry |  | 105958 | 100% | 0% | 100% | 105958 | 0 | 105958
| Roofing and Flashing |  | 83582.2 | 100% | 0% | 100% | 83582.2 | 0 | 83582.2
| Drywall |  | 84940 | 100% | 0% | 100% | 84940 | 0 | 84940
| Painting |  | 47740 | 100% | 5% | 95% | 47740 | 2387 | 45353
| Mirrors |  | 15500 | 100% | 10% | 90% | 15500 | 1550 | 13950
| Flooring |  | 69715.28 | 100% | 20% | 80% | 69715.28 | 13943.056 | 55772.224
| Specialties |  | 93744 | 100% | 45% | 55% | 93744 | 42184.8 | 51559.2
| Electrical |  | 353710 | 100% | 5% | 95% | 353710 | 17685.5 | 336024.5
| Mechanical |  | 428730 | 100% | 25% | 75% | 428730 | 107182.5 | 321547.5
|  | Total Contract | 1754249.08 |  |  |  | 1754249.08 | 188466.856 | 1565782.224
|  | Change Orders To Date | 104391
|  | Change Order This Period | 0
|  | Change Orders Total | 104391 | 100% | 13% | 87% | 104391 | 13570.83 | 67854.15
|  | Revised Contract | 1858640.08 |  |  |  | 1858640.08 | 202037.686 | 1633636.374
|  | Builer's Lien Holdback |  |  |  |  | 185864.008 | 20203.7686 | 165660.2394
|  | TOTAL RECEIVABLE |  |  |  |  | 1672776.072 | 181833.9174 | 165660.2394
|  | Paid To Date |  |  |  |  | 1490942.1546 |  | 165660.2394
|  | NET RECEIVABLE |  |  |  |  | 181833.9174 | 181833.9174 | 0
Note on E30: Enter Change Order approved this moonth here!

## Cert 6
G/A Architects & Designers
Consulting Engineers and Architects |  |  |  | Certificate For Payment
234 Maple Road, Kingston, Ontario
TO: | Project Innovations Incorporation |  | Project: |  | Highland Development Corporation
| 234 Baycrest Park |  | Project No.: |  | 2012-69
| Belleville, Ontario |  | Date Issued: |  | 1999-09-27
|  |  | Certificate No.: |  | 6
We hereby certify that in accordance with your contract with the owner
Highland Development Corporation
the contractor
Project Innovations Incorporation
|  |  | to entitled to payment in the amount of |  | 181833.9174 | for work performed.
PRESENT STATUS OF ACCOUNT:
| Original Contract Sum |  | 1754249.08
| Authorized Change Orders |  | 104391
| Balance |  | 1858640.08
|  |  | Revised Contract Sum |  |  | 1858640.08
|  |  | Less Certificates To Date |  |  | 0
|  |  | Balance Not Certified |  |  | 1858640.08
| Value of Work Furnished |  | 1858640.08
| Less 10% Holdback |  | 185864.008
1672776.072
| Add Holdback Released |  | 0
1672776.072
| Less Previous Certificates |  | 1490942.1546
| Amount of This Certificate |  | 181833.9174 |  |  | 181833.9174
| Architect: | Karen Jackson
| Title: | Associate Architect

## PC Summary
Project Innovations Incorporation
SCHEDULE OF VALUE AND WORK PERFORMED SUMMARY
| Owner: | Highland Development Corporation
| Project #: | 2012-69
| Architect: | Karen Jackson
| Date: | 1999-07-29
|  |  | APPROVED | REVISED | REVISED |  | NET
|  | ORIGINAL | CHANGE | CONTRACT | AMOUNT |  | AMOUNT | %
| DESCRIPTION | CONTRACT | ORDERS | AMOUNT | CLAIMED | HOLDBACK | CLAIMED | CLAIMED | REMARKS
| Claim 1 | 1754249.08 | 18585 | 1772834.08 | 126838.42 | 12683.842 | 114154.578 | 6.824%
| Claim 2 | 1754249.08 | 54873 | 1809122.08 | 455525.31 | 45552.531 | 409972.779 | 24.51%
| Claim 3 | 1754249.08 | 81459 | 1835708.08 | 338938.92 | 33893.892 | 305045.028 | 18.24%
| Claim 4 | 1754249.08 | 104391 | 1858640.08 | 339777.832 | 33977.7832 | 305800.0488 | 18.28%
| Claim 5 | 1754249.08 | 104391 | 1858640.08 | 395521.912 | 39552.1912 | 355969.7208 | 21.28%
| Claim 6 | 1754249.08 | 104391 | 1858640.08 | 202037.686 | 20203.7686 | 181833.9174 | 10.87%
[5 empty] | 1858640.08 | 185864.008 | 1672776.072 | 100%

## Architect
Architects Directory
| 1 | none
| 2 | A-B-D Designers and Engineers
| 3 | Benson Designs Corporation
| 4 | Brydon Architects and Associates
| 5 | Carver Engineers and Architects
| 6 | G/A Architects & Designers
| 7 | Holland Architectural Group
| 8 | Jack Finish Architects
| 9 | Peter Pivko Architects
| 10 | Mars Design Associates
| 11 | Murray and Murray Architects
| 12 | Robert Architects
| 13 | Sticko and Bracken Designs
6