## Compare Analysis (hidden)
Training Need/Task | MHS E-Logs | PEGA Exceptions | MHS Manual Interventions
1095 Inquiries | After correcting elog - manually reProof & Post | Add Transaction Exception | Add an Applicant
Adding Notes/Completing (Submit) | After Loading of Payment | Add Transaction Not Found | Modify an Applicant Demographics
AG/Regulatory Complaints | After posting payment, Proof & Post (MHS auto proofs & post) | Change in Effective Date | Cancel an Applicant |  | Demographics
APIC Member Reconciliation | After Proof & post E-logs | Change Transaction Exception | Add a Member/Subscriber |  | Payments
APIC Payment Posting | AR Proof and Post the Invoice batch in ARTMAS | Member Identification |  |  | Does it need training?
APIC Refund Process (Refund and Elgibility Review) | EEIMAS File Creation | MHS Load Error | Duplicate Add a Member
Billing Expedites | EEIMAS File Creation & Effectuation of Fully Subsidized | PCP AA: Unable to find provider | Terminate a Member | This should be in the Demoraphics/Payment section
Binder Data to Member Services to Outreach Applicants | EEIMAS File Creation & Effectuation of Fully Subsidized -> OutMEMOM | Term Transaction Exception | Modify Group Span
Binder Invoice (Needs Internal Review) | Effectuation Load MEP051 - Checking of payment to prep for Effectauation | Unable to find match in Benefit Mapping Grid | Modify Financial Information
Binder Invoicing (One Click-QA) | EP Subsidized Delinquency Letter Batch process |  | Modify Member Demographics
Binder Invoicing- SEPs (One Click-QA) | HF Sourced Cancellation Process |  | Modify Billing and/or BenPckg
Biztalk Spreadsheet | HF Sourced Cancellation Process -> OutMEMOM |  | PCP Changes
Cancellation Process- BUL Fallouts | Marketplace Binder Invoice Process (Creating an ARTMAS record) |  | Modify Med County
Cancellation Process- BUL Run | ME1021/22 posting
Cancellation Report-One Click - Report Prep | Premium billing no update E-log
Cancelled 834 Retro Transactions | Premium billing with AN Update E-log
CMS Reconciliation | Premium Proof & Post AR022
Daily NAMI Run | QHP Non Subsidized Delinquency Letter Batch process
Daily Overwritten History | QHP Subsidized (APTC) Delinquency Letter Batch process
Delinquency Process Run | State Source Cancellation Process
DOH Inquiries
Dummy PCP Vendor Clarifications
Duplicate Member ID- Creation
Effectuation Issue Work Around (Identify members to place back in QH99- Send to IT- IT Sends back results- OA validates)
Effectuation Report - Payment verification QlickView
Effectuation Workaround (Gihan File)
eLog/Working a Example - ME1022 (Manual Intervention)
eLog/Working a Example - ME1023 (Manual Intervention)
E-Logs (New)
End of Month Adjustment BUL (Write-Offs)
Enrollment Benefit update from Reject Payment Report
Enrollment Expedites
HF Sourced Cancellation Reconciliation (MAR)
HF Sourced Disenrollment (BUL Fallouts)
HF Sourced Disenrollment (BUL)
HF Sourced Disenrollment (One Click- Report Prep)
HF Sourced Disenrollment Reconciliation- (MAR) Outbound Transaction Recon
HNY Application Process - Thinking does not require training
HNY Monthly Billing
Identifying an APIC Member in ACA
Introduce MHS Screens (ME1022 & ME1023)
Key Changes
MACESS Service Forms
Main Page exploration (includes Filters)
Manual Invoicing
MHS Error Log - Effectuations
MHS Screens - ME1022
MHS Screens - ME1023
Missing Relationship
NYSoH QHP Complaints
NYSoH QHP Complaints Inquiry Tracker
One Click - Report Prep
Ongoing Invoice (Needs Internal Review)
Ongoing Invoice Report (One Click - Report Prep -
Outbound Reconciliation - Missing Transacions
Outbound Reconciliation - Rejected Transactions
Outbound Reconciliation -Reinstatements (H014)
P1 Complaints
Payment Transfer Log
PCP BUL
PEGA EIM Failed Task Error Logs
PEGA EIM SME Task (Vendor Clarifications)
PEGA UWF Billing
PEGA UWF Billing (Pending Further Info)
PEGA UWF Enrollment
PEGA UWF Enrollment (Pending Further Info)
PEGA UWF Inventory Extract
Premium Billing Post MHS (AN Update)
Premium Billing Run
QHP Delinquency Data to Member Services
QHP Delinquency Letter (15/30/60)
QHP Membership Volume Data Pull (For stakeholders during N-OEP & OEP)
QHP Off Exchange Application Process - Thinking does not require training
QHP Return Mail- Address Verification & Distribution
QHP/EP Overlapping Spans
Reinstatement Log (NYSoH)
Returned Payments- Cancel/Term Eligiblity
Save Function
Search Function/Options
Select Action Items
Send to State
Split Billing Error Log
Unresolved PCP Cap
Warning Logs (New)
Working a Case
Note on C6: Author: Moved to Demographics section
Note on C8: Author: Added to demographics section
Note on A39: Author: (Intake- Create Ticket for IT to create Group in MHS- Ensure payment is with application- Load member into MHS- Effectuate member) - Thinking this does not require training
Note on A42: Author: Introduce PEMMAS vs. MEMMAS
Note on A60: Author: EDPT Spreadsheet says out of scope, can this be removed.
Note on A74: Author: (Intake-Ensure payment is with Application-Load Member in MHS- Effectuate) Thinking this does not require training.

## Asset Calculatorby_AssetType
2024 Operations Development
Instructions: Enter the Start date in column C, 1st row under header or by End Date in Column G, last row under header.
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | Topic/Task> Milestones | START | END | # DAYS (Includes WKNDS) | START | END | # DAYS (Includes WKNDS)
eLearning-NEW |  | 2026-04-15 | 2026-07-20 | 90 | 2026-02-24 | 2026-05-01 | 48
| Content Gathering | 2026-04-15 | 2026-04-25 | 10 | 2026-02-24 | 2026-03-02 | 5
| Alpha Development | 2026-04-26 | 2026-06-10 | 45 | 2026-03-03 | 2026-03-23 | 15
| Alpha Review | 2026-06-11 | 2026-06-16 | 5 | 2026-03-24 | 2026-03-30 | 5
| Beta Development | 2026-06-17 | 2026-07-02 | 15 | 2026-03-31 | 2026-04-09 | 8
| Beta Review | 2026-07-03 | 2026-07-08 | 5 | 2026-04-10 | 2026-04-16 | 5
| Final Development/WD Testing | 2026-07-09 | 2026-07-19 | 10 | 2026-04-17 | 2026-04-30 | 10
| Learning Release | 2026-07-20 | 2026-07-20 | 0 | 2026-05-01 | 2026-05-01 | 0
eLearning, Demo, PPT -Update |  | 2026-09-16 | 2026-11-15 | 55 | 2026-09-01 | 2026-11-15 | 55
| Alpha Development | 2026-09-16 | 2026-10-11 | 25 | 2026-09-01 | 2026-10-05 | 25
| Alpha Review | 2026-10-12 | 2026-10-15 | 3 | 2026-10-06 | 2026-10-08 | 3
| Beta Development | 2026-10-16 | 2026-10-31 | 15 | 2026-10-09 | 2026-10-29 | 15
| Beta (External) Review | 2026-11-01 | 2026-11-03 | 2 | 2026-10-30 | 2026-11-02 | 2
| Final Development | 2026-11-04 | 2026-11-09 | 5 | 2026-11-03 | 2026-11-09 | 5
| Uploaded in Workday | 2026-11-10 | 2026-11-15 | 5 | 2026-11-10 | 2026-11-15 | 5
ILT - PPT-NEW |  | 2026-05-01 | 2026-08-15 | 98 | 2026-01-05 | 2026-05-01 | 76
| Content Gathering | 2026-05-01 | 2026-05-21 | 20 | 2026-01-05 | 2026-01-19 | 10
| Alpha Development | 2026-05-22 | 2026-06-21 | 30 | 2026-01-20 | 2026-02-17 | 20
| Alpha Review | 2026-06-22 | 2026-06-27 | 5 | 2026-02-18 | 2026-02-23 | 3
| Beta Development | 2026-06-28 | 2026-07-08 | 10 | 2026-02-24 | 2026-03-10 | 10
| Beta (External) Review | 2026-07-09 | 2026-07-12 | 3 | 2026-03-11 | 2026-03-16 | 3
| Final Development | 2026-07-13 | 2026-07-18 | 5 | 2026-03-17 | 2026-03-24 | 5
| Teachbacks (Train-the-Trainer) | 2026-07-19 | 2026-07-24 | 5 | 2026-03-25 | 2026-04-01 | 5
| Uploaded in Workday | 2026-07-25 | 2026-08-04 | 10 | 2026-04-02 | 2026-04-16 | 10
| Learning Delivery Starts | 2026-08-05 | 2026-08-15 | 10 | 2026-04-17 | 2026-05-01 | 10
Video - NEW |  | 2026-04-20 | 2026-06-07 | 40 | 2026-04-10 | 2026-06-07 | 40
| Identify content for each role | 2026-04-20 | 2026-04-30 | 10 | 2026-04-10 | 2026-04-23 | 10
| Create/Approve Outline (Prototype) | 2026-05-01 | 2026-05-06 | 5 | 2026-04-24 | 2026-04-30 | 5
| Alpha Development | 2026-05-07 | 2026-05-17 | 10 | 2026-05-01 | 2026-05-14 | 10
| Alpha Review | 2026-05-18 | 2026-05-23 | 5 | 2026-05-15 | 2026-05-21 | 5
| Beta Development | 2026-05-24 | 2026-05-29 | 5 | 2026-05-22 | 2026-05-28 | 5
| Beta (External) Review | 2026-05-30 | 2026-06-02 | 3 | 2026-05-29 | 2026-06-02 | 3
| Final Development | 2026-06-03 | 2026-06-05 | 2 | 2026-06-03 | 2026-06-04 | 2
| Upload to designated Final Shared Location of source files for LXP | 2026-06-06 | 2026-06-06 | 0 | 2026-06-05 | 2026-06-05 | 0
| Confirm access and ability to open as designed… Confirm w/ testing | 2026-06-07 | 2026-06-07 | 0 | 2026-06-07 | 2026-06-07 | 0

## Asset Calculator by Date
Instructions: Enter the Start date in CELL C3, or by End Date in CELL D15, last row under header.
| Topic/Task> Milestones | START | END | # WORKDAYS
By Start Date | Milestones | 2026-05-01 | 2026-07-09
| Content Gathering | 2026-05-01 | 2026-05-08 | 5
| Alpha Development | 2026-05-11 | 2026-05-25 | 10
| Alpha Review | 2026-05-26 | 2026-06-02 | 5
| Beta Development | 2026-06-03 | 2026-06-24 | 15
| Beta Review | 2026-06-25 | 2026-07-02 | 5
| Final Development/LMS Testing | 2026-07-03 | 2026-07-17 | 10
| Learning Release | 2026-07-20 | 2026-07-20 | 0
|  |  | Total # Workdays | 50
| Topic/Task> Milestones | START | END | # WORKDAYS
By END Date | Milestones | 2026-01-15 | 2026-05-01
| Content Gathering | 2026-01-15 | 2026-01-22 | 5
| Alpha Development | 2026-01-23 | 2026-03-06 | 30
| Alpha Review | 2026-03-09 | 2026-03-16 | 5
| Beta Development | 2026-03-17 | 2026-04-07 | 15
| Beta Review | 2026-04-08 | 2026-04-15 | 5
| Final Development/LMS Testing | 2026-04-16 | 2026-04-30 | 10
| Learning Release | 2026-05-01 | 2026-05-01 | 0
|  |  | Total # Workdays | 70
Formulas:
END = IF(OR([START]="",E11=""),"",IF(E11=0,[START],WORKDAY([START],E11-1)))
END = WORKDAY([START],+E4)
START = [START, row above]
START = WORKDAY([END, row above],1)

## Data Tables (hidden)
asset type data table | Dev. Time Per Hour or Unit(s)
eLearn (<30)-80 | 80
eLearn(>30)-160 | 160
Flyer-8 | 8
Guide-8 | 8
Image-4 | 4
iPDF-40 | 40
NA-80 | 80
PPT (<1)-40 | 40
PPT (>1)-80 | 80
QRG-4 | 4
Quiz-8 | 8
Rise-80 | 32
Storyline Level 1 | 80
SEE IT-32 | 32
TRY IT-20 | 20
Video-40 | 40