## OVERVIEW
EXHIBIT B SCHEDULE OF VALUES
Project: | Somerworth NH - Contractor Bays |  |  |  |  | Date:
Location: | 187 NH-108, Somersworth, NH 03878
Owners: | Patriot Holdings LLC
Cost |  | Scheduled | From Previous |  | Total | Balance to | %
Code | Item | Value | Application | This Period | Completed | Complete
10 | General Cond | 33273.5 |  |  | 0 | 33273.5 | 0%
20 | Architectural | 6500 |  |  | 0 | 6500 | 0%
30 | Civil Engineer | 28000 |  |  | 0 | 28000 | 0%
40 | Builders Risk Insurance | 2800 |  |  | 0 | 2800 | 0%
50 | Permit Requirments | 18000 |  |  |  | 18000 | 0%
60 | Grading and Site Cleanup | 769570 |  |  | 0 | 769570 | 0%
70 | Paving | 290000 |  |  | 0 | 290000 | 0%
80 | Insulated Roll Up Doors | 50400 |  |  | 0 | 50400 | 0%
90 | Man Doors | 10800 |  |  | 0 | 10800 | 0%
100 | Landscaping | 6000 |  |  | 0 | 6000 | 0%
110 | Concrete | 396000 |  |  | 0 | 396000 | 0%
120 | Concrete Bollards | 4600 |  |  | 0 | 4600 | 0%
130 | Metal Buildings | 896030.77 |  |  | 0 | 896030.77 | 0%
140 | Building Erection | 280000 |  |  | 0 | 280000 | 0%
150 | Drywall (Firewalls) | 96000 |  |  | 0 | 96000 | 0%
160 | Metal Framing for Office and Bathrooms | 72000 |  |  | 0 | 72000 | 0%
170 | FRP | 13400 |  |  | 0 | 13400 | 0%
180 | Signage | 7500 |  |  | 0 | 7500 | 0%
190 | Security | 10000 |  |  | 0 | 10000 | 0%
200 | Paint | 12800 |  |  | 0 | 12800 | 0%
210 | Plumbing | 234700 |  |  | 0 | 234700 | 0%
220 | Electrical | 290000 |  |  | 0 | 290000 | 0%
230 | Legal & Permits | 6654 |  |  | 0 | 6654 | 0%
240 | Hard Cost Contingency (4%) | 140414.97 |  |  | 0 | 140414.97 | 0%
250 | General Contractor / Developer Fee | 147017.73 |  |  | 0 | 147017.73 | 0%
| Totals | 3822460.97 | 0 | 0 | 0 | 3822460.97 | 0%
[5 empty] | PER SQFT | 95.5615