## 29 OCT
AOC - 2025 LOG of OPEN ITEMS |  |  |  | Update: 29 OCT 2025
AREA / DEPARTMENT | TOPIC / AREA OF CONCERN | DATE | LAST UPDATE / FOLLOW UP | STATUS
AIRLINE PROGRAMS
TERMINAL OPS /
T3 arrivals carrier signage at podiums. | Long pending item carriers requesting monitor screens. Issue has been raised multiple times with GTAA. Carrier signs are being damaged and impacting Brand image. | AOC T3 (Tabled 26FEB) | Update 26 Mar: No update given. Steph to investigate and provide an answer at Apr AOC. Update 30 Apr: Pending further update Jun 24: Waiting for confirmation from Dalia if this will go under T1/T3 Revit. Or priority prgm. Update 30 JUL: Work in progress - Pending update from GTAA Update 27 AUG: Request has been submitted to add screens above the customer service desks to display the airline logo. GTAA currently waiting for budget approval. UPDATE 24 SEP: Awaiting budget approval and implementation. | Open
T3 - Additional Signage Storage Facilities | T3 Airlines: Looking for additional storage space for gate signage. Current space is not sufficient signs are piled up and getting damaged | AOC (30 JUL) | Update 30 JUL: Item tabled with GTAA for follow up Update 27 AUG: is looking for a designated storage area. No update was provided UPDATE 24 SEP: identified a possible room near gate C30 and are currently attempting to verify access so we can investigate if it's available | TBD
BAGGAGE / Mike Dyl
CASS Common Handler Performance | Pain points with program mainly with spike in cost, unjustified invoicing, lack of scanning mechanism and supporting data ( issue tabled for T1 and T3) | AOC (Tabled 26MAR) | Update 26 Mar: GTAA working on the amendment of the contract covering carry down per scanned piece and the carousel management. Major amendment to the contract going forward making carry down optional Meeting is sked for 27 Mar with CASS , outcome to be reviewed with GTAA then brough forward to ACC for approval, looking to fix before the summer Update 30 Apr:Working group in progress; CASS contacting AI carriers for Carry Down discussions. Update Jun 24: This was presented at ACC level, ballot coming up beginning of July - if you have questions please reach out to Dan Riddle - he can provide individual Numbers Update 30 JUL: Work in progress: Ballots are out. CASS is looking into any miss-charges (airlines should have received a Credit by now (Oversize Cary down) airlines to reach out to CASS for invoicing issues and clarifications Update 27 AUG: Next update at the September AOC scheduled for Sep 16th | TBD
CASS Common Handler Performance | 27 AUG: Carousel Management is now the responsibility of the airlines, as per the recently approved contract amendment. Airlines must coordinate with their ground handling or manage with their own staff. • Consequence of Non-Compliance: GTAA will clear the carousels using CASS and bill the airlines. |  | Update 27 AUG: New SOP shared with AOC community (effective Sep 3rd). PENDING: Chargeback model and procedure being finalized and will be shared in advance of any chargeback model going live. Update 24 SEP: Productive conversations at subcommittees level, SSBD support T3 and T1 and Oversize is divided equally ( majority goes to SSBD support) CASS requested to calibrate the charges as per actual use. Current billing is not reflective of actual volume per area. Item to be closed at AOC level and keep at SUBCOMMITTEE level - PENDING: Finalization of penalty structure and SOP application process by airport authority is still in progress. UPDATE 29 OCT: Chargeback Reporting for Carousel Alarms: Daily reports to be distributed to airlines regarding carousel full alarms. | TBD
FACILITIES / M. Regimbald
Bridges Maintenance Update / Operators Trainings | Need for better training for ground handlers and bridge operators. AOC inquired on planning of train the trainers sessions for increased awareness | AOC (Tabled 26MAR) | Update 26 Mar: Suggestions made for creating training videos to improve bridge operation. Update 30 Apr: Train the trainer sessions are planned for Jun and Sep GTAA planning to make the program a yearly base training done by manufacturer. Action Item: build a CALL DATA in order to do focus and targeted trainings. Action Item: Tie in providers and airlines in understanding what are the common/majority of issues and the trouble shooting possibilities. Action Item: Set up a working group with various stakeholders Update Jun 24: Update to be provided during today's meeting | Open
Bridge (PBB) Failures / Maintenance Update | AOC Requested continued updates on PBB progress.B27 Bridge has been our for months / Gate 73 -T1 alarm going on every day, and is a pending item for MThs despite daily calls Update 30 APR: (AVIANCA) Gate # 81 issues (auto level issues, various issues causing damage to aircraft door) Update 30 Apr: Many issues noted by various airlines, highlighting tardiness in improving bridges – AOC will push to make it a priority item for GTAA Revitalisation program | AOC (Tabled 26FEB) | Update 26 Mar: February's maintenance was impacted by weather. Continued efforts to catch up on preventive maintenance and address equipment issues Update 30 Apr: as detailed in GTAA presentation Update Jun 24: Update to be provided during meeting Update 30 JUL: GTAA to provide investigation updates for all incidents (Aero Mexico and Porter) AOC to escalate with GTAA for a thorough root cause analysis and satisfactory resolution, particularly regarding the repeated "faulty part" explanation and ensure GTAA communicates corrective actions to all affected carriers. Update 27 AUG: Action Item remain open until clear directions are established. Proposal: Form a working group with GTAA, focusing on establishing robust SOPs and guidelines for incident reporting, as the current handling by the airport authority is inconsistent UPDATE 24 SEP: All BRIDGE Items to remain open pending 1) Deployment of troubleshooting job aids at some gates (e.g., V1 at 173) has helped reduce operator errors. Suggest standardized deployment across all terminals.2) Bridges malfunctioning during extreme weather, heat, cold, and rain, including leaking canopies. Keep item open for monitoring and updates. | Open
| Aeromexico:Aircraft damage; investigation update from GTAA pending. Porter (June Incident):Incident involved a collapsed and shifted cap, resulting in an injury and loss of work.. Last update from GTAA 27 JUL explanation of "faulty part" is not satisfactory given the injury and operational impact. Air Transat: similar issue at the same gate a week after Porter incident. Significant aircraft damage occurred due to bridge jolting. Common Issue: All incidents appear related to the same gate/bridge ("Remain Open" scenario), suggesting an unresolved mechanical or procedural fault. | PD/TS/AM (30 JUL)
Bridges(PBB) during extreme heat/weather / SNOW Events(H&S) | Extreme heat on boarding bridges has become a significant challenge and major health and safety risk. Cleaning staff have fainted on two separate occasions. Multiple reports of staff feeling ill due to the heat Pax complaints with some feeling faint and boarding operations disrupted. | AOC (30 JUL) / (29 OCT) | Update 30 JUL: Short-Term Mitigation requests by AOC : Request implementation of temporary cooling solutions (fans, portable AC units, etc.) until a permanent fix is in place. Long-Term Solutions Recommendation by AOC: Review and upgrade of bridge temp control systems to ensure safe temperatures for staff and passengers 27 AUG: Item remain open ahead of the winter season, addressing freezing conditions on bridges during snow and cold events UPDATE 24 SEP: All BRIDGE Items to remain open pending UPDATE 29 OCT:Bridge snow accumulation concerns raised; updates requested next month. Testing of heated floors and baseboard heaters underway. | Open
People movers - Out of service (Jonthan Lock) | Congestion that is aggravated by surrey’s during peak hours, further impacted due to many People Movers are our of service | 24 Jun | Update 30 JUL: GTAA presented an update during the meeting (Presentation shared with AOC) New IT upgrade will allow to extract the performance of each unit for close follow up - GTAA to update | Open
Elevator at C36 | Elevator is fully functional , yet requires additional work on wall enclosure to bring into good service. | AOC tabled 22 Apr | Sue to follow up - Update Jun 24: Technical drawings received, quote received, awaiting financial approvals. Update 27 AUG: GTAA Continuing to improve monitoring software (i.e. critical units, sectors) Update given during meeting (GTAA Presentation) Update 24 SEP: The funding for elevator BH33 has been approved and maintenance is in the process of onboarding the contractor. Amaury will share a schedule once available | TBD
AIRPORT OPS /
OSS Identifier - Effective 31 MAR and Air Carrier Readiness | GTAA originally accepted PTM as an interim solution, was later refused. Concern from carriers about readiness and the need for interim solutions, i.e. PTM Challenges with timeline for integrating barcode identifiers by air carriers and the associated cost. BARCODE indicator is strictly a request from GTAA and deadline is also GTAA decision | AOC (Tabled 26MAR) | Update 26 Mar: GTAA to respond to AOC on why YYZ is only airport in Canada pressing the OSS identifier. GTAA to reach out to other airports for further inquiries on local processes and deadlines. Air Carriers are pressing for PTM process as an intermediate solution, GTAA to review. GTAA requested to come back with update on processes at April AOC Update 30 Apr: No other Airports in Canada are using PTM. AFKL to collaborate with GTAA on PTM project and possibility of use testing Update Jun 24: testing is still under way with AF/KLM Update 27 AUG: No updates Update 24 SEP: No updates | TBD
ITD - SPILL | 24 JUN: Porter reported lack of signage re-directing pax when SPILL is closed .30JUL Porter Airlines has requested a stationed TSR for guidance in place of relying solely on signage, to assist with passenger flow and security, particularly during peak early morning arrivals. | PD (30 JUL) | Update 30 JUL: Javier to organize a walkaround with Brittany and Porter to assess issues impacting early morning arrivals. AOC + GTAA Schedule a follow-up meeting to discuss findings and develop solutions. Update 27 AUG: Pending updates Update 24 SEP: No resources to have an OSR stand at Node B during off hours of SPIL. GTAA suggested to add a sign that can be deployed in the Node in addition to the sign that's currently at the entrance. The sign can advise the hours and direct passengers to follow signs for arrivals during those hours. | Open
ITD - PROGRAM Onboarding | Program Hold Operational impact: Several carriers are planning to introduce new flights in Q3 and Q4 and are awaiting onboarding at T3 | PD /TS (30 JUL) | Update 30 JUL: AOC Requested an update from GTAA or CBSA on the status and timeline for reopening the SBI gate/area Update 27 AUG: Program soon to be relaunched- updates to follow at next meeting UPDATE 24 SEP: CBSA has just restarted the onboarding process and has resumed risk assessments. This is the first step to onboarding a new route and/or airline which is a positive sign.
T3 International Baggage Hall access after 22:30 | Access Change and Operational Impact ==>As per recent changes to T3 international baggage hall access route, agents are no longer permitted to use the standard entry and must use the AT level access through departure security. Detour takes 15–20 minutes per agent, significantly impacting operational efficiency, particularly during late-night operations | AA (30 JUL) | Update 30 JUL: AOC is looking official communication from CBSA/GTAA regarding the rationale for the new access procedure and expected duration of this change. GTAA to follow up and advise if there are any alternative access options or expedited processes to minimize staff downtime and operational impact. 27 AUG:Pending follow up update 24 SEP: Root cause attributed to CBSA Staffing level. GTAA is following up with CBSA to explore possible workarounds. AOC will keep the item open and monitor for updates. | Open
Security / B.Scott
SWING Doors | AA escalating issue at various levels =>Multiple deficiencies identified during a recent walkaround in various locations: B11 and A08 Stanchion issues reported; American Airlines A07: Additional concerns noted as gaps found near swing doors, posing a security risk as items could potentially be introduced into secure zone. | AA (30 JUL) | Update 30 JUL: GTAA: Request to include the airlines in the Security Committee GTAA: Need to compile a list of all locations with similar deficiencies. Prioritize repairs or installation of additional security measures (e.g., stanchion adjustments, gap closures). UPDATE 24 SEP: A8 door alarm fixed, other security items remains pending | Open
Trafficking Incidents and significant impact on security | Recent incidents of unauthorized items being trafficked through Pearson Airport have raised serious concerns. Incidents were reported in the media and involved insider threats, where airport employees or ground handlers allegedly used their access to facilitate trafficking. | CX (29 NOV) | Action Items: 1.Focus Group Formation. 2.Regulatory Advocacy: GTAA and airlines to jointly approach Transport Canada (TC) and CATSA to recognise contraband as a civil aviation threat and push for regulatory changes to improve screening 3. Deployment of law enforcement and CBSA for random inspections. 4. 26 new cameras to be installed at all baggage induction points by year-end. 5. Written documentation requested for Project Vigilance to share with airline HQs. | Open
NPS 100% Screening - Effective 31 MAY 2025 | GTAA Airport readiness to implement upcoming NPS regulations, requiring 100% NPS screening | AOC (Tabled 26FEB) | Update 26 Mar: Involved stakeholders continues to prepare for the phased implementation of enhanced screening measures. Stress tests are ongoing to assess operational ability to meet these requirements. Requirement for 100% screening is planned for 31 May 2025. Update 30 Apr: Testings are ongoing, AOC requested feedback from GTAA on test results and airport readiness . JUNE 24: waiting for confirmation if GTAA can share data from testing. Update 27 AUG: Deadline pushed to 2026 UPDATE 24 SEP: Canada passes are causing delays at screening points (ASP T3) | Open
AIRSIDE OPS / G. Henderson
STAIRS - Ramp | Concern raised by CX re the height of stairs used for Water uplift on wide body aircraft ==> Stairs are often used in a workaround manner (turned sideways or backwards) to reach the required height, creating a fall hazard. The workaround also brings the stairs dangerously close to sensitive fuselage areas. Item presented to GTAA during the meeting for follow up | CX (30 JUL) | Update 30 JUL: CX requesting a review of the current equipment provided for ramp operations. =>Suggest procurement of appropriately-sized, purpose-built stairs for water/lav servicing on widebody aircraft. =>Urgent need to address this issue to comply with H&S standards and to prevent potential injuries. =>GTAA to inquire and advise possibility to permit carriers to bring and use own compliant stairs if suitable airport equipment is not available Update 27 AIG: GTAA is looking into Update 27 AUG: work in progress UPDATE 24 SEP:GTAA is conducting a risk management assessment., remains work in progress | Open
FOD | FOD issues are trending - UPAK bins are noted often as overflowing. Concern echoed by airlines auditors on site visits (Tabled by KE/WG/UA and supported by all AOC) Concern raised with lack of proactive action noted by UPAK during recent high wind advisory. Cans were full, open and some overflowing | AOC (Tabled 26FEB) | Update 26 Mar: Tabled at AOSC GTAA to provide updates through AOC on the installation of new compactor bins. GTAA to continue addressing ramp cleanliness and FOD issues and wildlife mitigation at the waste transfer station. Update 30 Apr: UPAK improvement action plan in place, in addition to a working group. Item is being addressed at AOSC, to be kept also on AOC action log for close follow up Update June 24: Updated at ACC next steps for Upak contract // Request from BA for focus cleaning of chutes wheels due to accumulation of garbage. | Open
| Significant FOD presence, particularly in Terminal 3 (T3), remains a major issue and noted in recent audit. Current measure of garbage removal and increasing number of bins proved to be insufficient. GTAA reliance on calls is reactive remains problematic, indicating a need for a more proactive approach. | CX (30 JUL) | GTAA is requested to implement proactive FOD management strategies, not just respond to calls. Regular sweeps and visible cleaning staff should supplement (not replace) the call-based reporting system. Request for GTAA to deploy additional pickers and cleaners on-site at T3. Recommendation: Need for a proactive FOD management plan to GTAA, including routine patrols and dedicated FOD removal staff, to ensure ongoing cleanliness and safety in T3. •Update 27 Aug: Action Item: possibility of embedding ramp garbage removal into the new common handler contract. UPDATE 24 SEP: Proposal is under review by the technical working group. Awaiting feedback from GTAA and confirmation on whether ramp cleaning will be added to the RFP | Open
NEW ITEMS - 24 SEP | Emirates (EK) raised concerns about lengthy EMS assessment protocols during medical calls at the gate. Impact: Delays in emergency response due to extensive questioning before dispatch. Action raised with GTA and EMS to review streamlining procedures for urgent cases. | AOC
NEW ITEMS - 24 SEP | Delta Incident Debrief Pending No formal debrief or learnings shared from the Delta incident. Action: Request GTAA to provide incident summary and operational takeaways for carrier awareness and training. | AOC
NEW ITEMS - 24 SEP | LEE Restaurant’s patio setup encroaches on boarding gate space, causing congestion during peak departures. Action: Request removal or relocation of patio structure to restore passenger flow and gate access | ACO T1
NEW ITEMS - 24 SEP | New Cleaning provider T3 Only - Transition Period between BEST and DEXTERRA / Airlines requesting what is the cleaning SCOPE /STANDARDS // Airlines requested contact and info | AOC
GTAA | Winter Readiness planning: GTA to share winter readiness plans, including: Equipment maintenance. De-icing protocols. Bridge canopy inspections. | GTAA | Presented during OCT 29th Meeting | Ready

## 24 SEP
AOC - 2025 LOG of OPEN ITEMS |  |  |  | Update: 24 SEP 2025
AREA / DEPARTMENT | TOPIC / AREA OF CONCERN | DATE | LAST UPDATE / FOLLOW UP | STATUS
AIRLINE PROGRAMS / K.Minocher
TERMINAL OPS /
T3 arrivals carrier signage at podiums. | Long pending item carriers requesting monitor screens. Issue has been raised multiple times with GTAA. Carrier signs are being damaged and impacting Brand image. | AOC T3 (Tabled 26FEB) | Update 26 Mar: No update given. Steph to investigate and provide an answer at Apr AOC. Update 30 Apr: Pending further update Jun 24: Waiting for confirmation from Dalia if this will go under T1/T3 Revit. Or priority prgm. Update 30 JUL: Work in progress - Pending update from GTAA Update 27 AUG: Request has been submitted to add screens above the customer service desks to display the airline logo. GTAA currently waiting for budget approval. UPDATE 24 SEP: Awaiting budget approval and implementation. | Open
Transborder Gate Storage Facilities(AA) | Need to find a permanent storage solution for airlines operating in transborder area to store their materials to use at the gates. Going back and forth through security and hauling a bag with materials seems counterproductive, increase check in time at the security checkpoint and inefficiencies at NPS. | 26 FEB (AA) | Update 26 Mar: Item presented to GTAA Update 30 Apr: Cabinets ordered, arriving in 4 weeks; combination code to be shared with the community Update Jun 24: Waiting for update from Amaury Update 27 AUG: is looking for a designated storage area. No update was provided UPDATE 24 SEP: Designated storage now located in US Area .Airlines to contact GTAA for access code ( Keep open for International Area T3. T1 carriers to also check for a need and advise | Ready
T3 - Additional Signage Storage Facilities | T3 Airlines: Looking for additional storage space for gate signage. Current space is not sufficient signs are piled up and getting damaged | AOC (30 JUL) | Update 30 JUL: Item tabled with GTAA for follow up Update 27 AUG: is looking for a designated storage area. No update was provided UPDATE 24 SEP: identified a possible room near gate C30 and are currently attempting to verify access so we can investigate if it's available | TBD
KIOSK performance | Reports by Sunwing on some KIOSKS ripping passports | WG / CX (30 APR) | presented to GTAA for Follow up Update Jun 24: IT will be conducting daily checks on PSPT readers - Ask to the community if this is seeing in other locations - 5 incidents so far Update 30 JUL: Work in progress - Problem identified, KIOSKs are being checked and tested on a weekly basis (2 specific KIOSK in Zone 5) Item to remain open till AUG meeting // GTAA replacing Update 27 AUG: GTAA IT has increased its checks on kiosks and will also see what can be done from a vendor's perspective. UPDATE 24 SEP: TO CLOSE . No additional reports received. GTAA is following closely. | Ready
BAGGAGE / Mike Dyl
CASS Common Handler Performance | Pain points with program mainly with spike in cost, unjustified invoicing, lack of scanning mechanism and supporting data ( issue tabled for T1 and T3) | AOC (Tabled 26MAR) | Update 26 Mar: GTAA working on the amendment of the contract covering carry down per scanned piece and the carousel management. Major amendment to the contract going forward making carry down optional Meeting is sked for 27 Mar with CASS , outcome to be reviewed with GTAA then brough forward to ACC for approval, looking to fix before the summer Update 30 Apr:Working group in progress; CASS contacting AI carriers for Carry Down discussions. Update Jun 24: This was presented at ACC level, ballot coming up beginning of July - if you have questions please reach out to Dan Riddle - he can provide individual Numbers Update 30 JUL: Work in progress: Ballots are out. CASS is looking into any miss-charges (airlines should have received a Credit by now (Oversize Cary down) airlines to reach out to CASS for invoicing issues and clarifications Update 27 AUG: Next update at the September AOC scheduled for Sep 16th | TBD
CASS Common Handler Performance | 27 AUG: Carousel Management is now the responsibility of the airlines, as per the recently approved contract amendment. Airlines must coordinate with their ground handling or manage with their own staff. • Consequence of Non-Compliance: GTAA will clear the carousels using CASS and bill the airlines. |  | Update 27 AUG: New SOP shared with AOC community (effective Sep 3rd). PENDING: Chargeback model and procedure being finalized and will be shared in advance of any chargeback model going live. Update 24 SEP: Productive conversations at subcommittees level, SSBD support T3 and T1 and Oversize is divided equally ( majority goes to SSBD support) CASS requested to calibrate the charges as per actual use. Current billing is not reflective of actual volume per area. Item to be closed at AOC level and keep at SUBCOMMITTEE level - PENDING: Finalization of penalty structure and SOP application process by airport authority is still in progress. | Ready
FACILITIES / M. Regimbald
Bridges Maintenance Update / Operators Trainings | Need for better training for ground handlers and bridge operators. AOC inquired on planning of train the trainers sessions for increased awareness | AOC (Tabled 26MAR) | Update 26 Mar: Suggestions made for creating training videos to improve bridge operation. Update 30 Apr: Train the trainer sessions are planned for Jun and Sep GTAA planning to make the program a yearly base training done by manufacturer. Action Item: build a CALL DATA in order to do focus and targeted trainings. Action Item: Tie in providers and airlines in understanding what are the common/majority of issues and the trouble shooting possibilities. Action Item: Set up a working group with various stakeholders Update Jun 24: Update to be provided during today's meeting | Open
Bridge (PBB) Failures / Maintenance Update | AOC Requested continued updates on PBB progress.B27 Bridge has been our for months / Gate 73 -T1 alarm going on every day, and is a pending item for MThs despite daily calls Update 30 APR: (AVIANCA) Gate # 81 issues (auto level issues, various issues causing damage to aircraft door) Update 30 Apr: Many issues noted by various airlines, highlighting tardiness in improving bridges – AOC will push to make it a priority item for GTAA Revitalisation program | AOC (Tabled 26FEB) | Update 26 Mar: February's maintenance was impacted by weather. Continued efforts to catch up on preventive maintenance and address equipment issues Update 30 Apr: as detailed in GTAA presentation Update Jun 24: Update to be provided during meeting Update 30 JUL: GTAA to provide investigation updates for all incidents (Aero Mexico and Porter) AOC to escalate with GTAA for a thorough root cause analysis and satisfactory resolution, particularly regarding the repeated "faulty part" explanation and ensure GTAA communicates corrective actions to all affected carriers. Update 27 AUG: Action Item remain open until clear directions are established. Proposal: Form a working group with GTAA, focusing on establishing robust SOPs and guidelines for incident reporting, as the current handling by the airport authority is inconsistent UPDATE 24 SEP: All BRIDGE Items to remain open pending 1) Deployment of troubleshooting job aids at some gates (e.g., V1 at 173) has helped reduce operator errors. Suggest standardized deployment across all terminals.2) Bridges malfunctioning during extreme weather, heat, cold, and rain, including leaking canopies. Keep item open for monitoring and updates. | Open
| Aeromexico:Aircraft damage; investigation update from GTAA pending. Porter (June Incident):Incident involved a collapsed and shifted cap, resulting in an injury and loss of work.. Last update from GTAA 27 JUL explanation of "faulty part" is not satisfactory given the injury and operational impact. Air Transat: similar issue at the same gate a week after Porter incident. Significant aircraft damage occurred due to bridge jolting. Common Issue: All incidents appear related to the same gate/bridge ("Remain Open" scenario), suggesting an unresolved mechanical or procedural fault. | PD/TS/AM (30 JUL)
Bridges(PBB) during extreme heat/weather (H&S) | Extreme heat on boarding bridges has become a significant challenge and major health and safety risk. Cleaning staff have fainted on two separate occasions. Multiple reports of staff feeling ill due to the heat Pax complaints with some feeling faint and boarding operations disrupted. | AOC (30 JUL) | Update 30 JUL: Short-Term Mitigation requests by AOC : Request implementation of temporary cooling solutions (fans, portable AC units, etc.) until a permanent fix is in place. Long-Term Solutions Recommendation by AOC: Review and upgrade of bridge temp control systems to ensure safe temperatures for staff and passengers 27 AUG: Item remain open ahead of the winter season, addressing freezing conditions on bridges during snow and cold events UPDATE 24 SEP: All BRIDGE Items to remain open pending | Open
VGDS | 27 AUG:VGDS at gate 171 is behaving erratically, causing 5 flights to brake suddenly. The system indicates 2-3 meters remaining, then abruptly stops, leading to aircraft overshooting the line and engines being too close to the bridge. This is a safety concern. | LH (27 AUG) | 27 AUG: follow up with GTAA (issue reported by LH) 29 OCT: Closed | Ready
GPU INOP | • Gate 173 GPU – multiple failures and a secondary portable GPU not available at the gate. GPU tripping is constant • Gate B12 – repetitive GPU tripping as well as PCA malfunctioning. | 24 Jun | Update 27 AUG: No update provided - Pending follow up UPDATE 24 SEP: Gates Affected: 171, 173, and B12.GPUs continue to trip during operations. Need for portable GPU units, which are often delivered without fuel, compounding delay ==> Request updates from GTA on repair timelines and fueling protocols for portable units. | Open
Escalators T1 | Escalator 173 not working, delaying pax offload. | Porter (30 APR) | presented to GTAA for Follow up Update Jun 24: Update to be provided during today's meeting Update 27 AUG: GTAA Continuing to improve monitoring software (i.e. critical units, sectors) Update given during meeting (GTAA Presentation) UPDATE 24 SEP: Item closed - Elevator now working | Ready
People movers - Out of service (Jonthan Lock) | Congestion that is aggravated by surrey’s during peak hours, further impacted due to many People Movers are our of service | 24 Jun | Update 30 JUL: GTAA presented an update during the meeting (Presentation shared with AOC) New IT upgrade will allow to extract the performance of each unit for close follow up - GTAA to update | Open
Elevator at C36 | Elevator is fully functional , yet requires additional work on wall enclosure to bring into good service. | AOC tabled 22 Apr | Sue to follow up - Update Jun 24: Technical drawings received, quote received, awaiting financial approvals. Update 27 AUG: GTAA Continuing to improve monitoring software (i.e. critical units, sectors) Update given during meeting (GTAA Presentation) Update 24 SEP: The funding for elevator BH33 has been approved and maintenance is in the process of onboarding the contractor. Amaury will share a schedule once available | TBD
AIRPORT OPS /
OSS Identifier - Effective 31 MAR and Air Carrier Readiness | GTAA originally accepted PTM as an interim solution, was later refused. Concern from carriers about readiness and the need for interim solutions, i.e. PTM Challenges with timeline for integrating barcode identifiers by air carriers and the associated cost. BARCODE indicator is strictly a request from GTAA and deadline is also GTAA decision | AOC (Tabled 26MAR) | Update 26 Mar: GTAA to respond to AOC on why YYZ is only airport in Canada pressing the OSS identifier. GTAA to reach out to other airports for further inquiries on local processes and deadlines. Air Carriers are pressing for PTM process as an intermediate solution, GTAA to review. GTAA requested to come back with update on processes at April AOC Update 30 Apr: No other Airports in Canada are using PTM. AFKL to collaborate with GTAA on PTM project and possibility of use testing Update Jun 24: testing is still under way with AF/KLM Update 27 AUG: No updates Update 24 SEP: No updates | TBD
ITD - SPILL | 24 JUN: Porter reported lack of signage re-directing pax when SPILL is closed .30JUL Porter Airlines has requested a stationed TSR for guidance in place of relying solely on signage, to assist with passenger flow and security, particularly during peak early morning arrivals. | PD (30 JUL) | Update 30 JUL: Javier to organize a walkaround with Brittany and Porter to assess issues impacting early morning arrivals. AOC + GTAA Schedule a follow-up meeting to discuss findings and develop solutions. Update 27 AUG: Pending updates Update 24 SEP: No resources to have an OSR stand at Node B during off hours of SPIL. GTAA suggested to add a sign that can be deployed in the Node in addition to the sign that's currently at the entrance. The sign can advise the hours and direct passengers to follow signs for arrivals during those hours. | Open
ITD - PROGRAM Onboarding | Program Hold Operational impact: Several carriers are planning to introduce new flights in Q3 and Q4 and are awaiting onboarding at T3 | PD /TS (30 JUL) | Update 30 JUL: AOC Requested an update from GTAA or CBSA on the status and timeline for reopening the SBI gate/area Update 27 AUG: Program soon to be relaunched- updates to follow at next meeting UPDATE 24 SEP: CBSA has just restarted the onboarding process and has resumed risk assessments. This is the first step to onboarding a new route and/or airline which is a positive sign.
T3 International Baggage Hall access after 22:30 | Access Change and Operational Impact ==>As per recent changes to T3 international baggage hall access route, agents are no longer permitted to use the standard entry and must use the AT level access through departure security. Detour takes 15–20 minutes per agent, significantly impacting operational efficiency, particularly during late-night operations | AA (30 JUL) | Update 30 JUL: AOC is looking official communication from CBSA/GTAA regarding the rationale for the new access procedure and expected duration of this change. GTAA to follow up and advise if there are any alternative access options or expedited processes to minimize staff downtime and operational impact. 27 AUG:Pending follow up update 24 SEP: Root cause attributed to CBSA Staffing level. GTAA is following up with CBSA to explore possible workarounds. AOC will keep the item open and monitor for updates. | Open
IFC Bussing | Request to increase bus frequency between the hours of 1500-1800 where there are multiple wide body aircraft operating at the same time Update 27 AUG-LH reported significant delays and safety concerns at E83 gate area due to IFC busing, leading to passenger overflow in the lounge and potential falling hazards from stairs. | 24 Jun | GTAA follow up required Update UPDATE 24 SEP: Avoid planning of 2 wide bodies side by side - To keep open pending additional safety measures to manage the bussing bay in T1 not meant to hold more then 1 wide body | Open
Security / B.Scott
Bridge Doors - Security Impact and Involvement | Many issues with keeping doors open. Staff RAIC are being suspended forcing doors to remain open // Gate 17 broken for last 6 months | Porter (30 APR) | presented to GTAA for Follow up - Update Jun 24: Asked GTAA to address in B. Scott presentation - are we still seeing fines? UPDATE 24 SEP: CLOSED as no further issues noted in recent period | Ready
SWING Doors | AA escalating issue at various levels =>Multiple deficiencies identified during a recent walkaround in various locations: B11 and A08 Stanchion issues reported; American Airlines A07: Additional concerns noted as gaps found near swing doors, posing a security risk as items could potentially be introduced into secure zone. | AA (30 JUL) | Update 30 JUL: GTAA: Request to include the airlines in the Security Committee GTAA: Need to compile a list of all locations with similar deficiencies. Prioritize repairs or installation of additional security measures (e.g., stanchion adjustments, gap closures). UPDATE 24 SEP: A8 door alarm fixed, other security items remains pending | Open
NPS 100% Screening - Effective 31 MAY 2025 | GTAA Airport readiness to implement upcoming NPS regulations, requiring 100% NPS screening | AOC (Tabled 26FEB) | Update 26 Mar: Involved stakeholders continues to prepare for the phased implementation of enhanced screening measures. Stress tests are ongoing to assess operational ability to meet these requirements. Requirement for 100% screening is planned for 31 May 2025. Update 30 Apr: Testings are ongoing, AOC requested feedback from GTAA on test results and airport readiness . JUNE 24: waiting for confirmation if GTAA can share data from testing. Update 27 AUG: Deadline pushed to 2026 UPDATE 24 SEP: Canada passes are causing delays at screening points (ASP T3) | Open
AIRSIDE OPS / G. Henderson
STAIRS - Ramp | Concern raised by CX re the height of stairs used for Water uplift on wide body aircraft ==> Stairs are often used in a workaround manner (turned sideways or backwards) to reach the required height, creating a fall hazard. The workaround also brings the stairs dangerously close to sensitive fuselage areas. Item presented to GTAA during the meeting for follow up | CX (30 JUL) | Update 30 JUL: CX requesting a review of the current equipment provided for ramp operations. =>Suggest procurement of appropriately-sized, purpose-built stairs for water/lav servicing on widebody aircraft. =>Urgent need to address this issue to comply with H&S standards and to prevent potential injuries. =>GTAA to inquire and advise possibility to permit carriers to bring and use own compliant stairs if suitable airport equipment is not available Update 27 AIG: GTAA is looking into Update 27 AUG: work in progress UPDATE 24 SEP:GTAA is conducting a risk management assessment., remains work in progress | Open
FOD | FOD issues are trending - UPAK bins are noted often as overflowing. Concern echoed by airlines auditors on site visits (Tabled by KE/WG/UA and supported by all AOC) Concern raised with lack of proactive action noted by UPAK during recent high wind advisory. Cans were full, open and some overflowing | AOC (Tabled 26FEB) | Update 26 Mar: Tabled at AOSC GTAA to provide updates through AOC on the installation of new compactor bins. GTAA to continue addressing ramp cleanliness and FOD issues and wildlife mitigation at the waste transfer station. Update 30 Apr: UPAK improvement action plan in place, in addition to a working group. Item is being addressed at AOSC, to be kept also on AOC action log for close follow up Update June 24: Updated at ACC next steps for Upak contract // Request from BA for focus cleaning of chutes wheels due to accumulation of garbage. | Open
| Significant FOD presence, particularly in Terminal 3 (T3), remains a major issue and noted in recent audit. Current measure of garbage removal and increasing number of bins proved to be insufficient. GTAA reliance on calls is reactive remains problematic, indicating a need for a more proactive approach. | CX (30 JUL) | GTAA is requested to implement proactive FOD management strategies, not just respond to calls. Regular sweeps and visible cleaning staff should supplement (not replace) the call-based reporting system. Request for GTAA to deploy additional pickers and cleaners on-site at T3. Recommendation: Need for a proactive FOD management plan to GTAA, including routine patrols and dedicated FOD removal staff, to ensure ongoing cleanliness and safety in T3. •Update 27 Aug: Action Item: possibility of embedding ramp garbage removal into the new common handler contract. UPDATE 24 SEP: Proposal is under review by the technical working group. Awaiting feedback from GTAA and confirmation on whether ramp cleaning will be added to the RFP | Open
IT John Thompson
NEW ITEMS - 24 SEP | Emirates (EK) raised concerns about lengthy EMS assessment protocols during medical calls at the gate. Impact: Delays in emergency response due to extensive questioning before dispatch. Action raised with GTA and EMS to review streamlining procedures for urgent cases. | AOC
NEW ITEMS - 24 SEP | Delta Incident Debrief Pending No formal debrief or learnings shared from the Delta incident. Action: Request GTAA to provide incident summary and operational takeaways for carrier awareness and training. | AOC
NEW ITEMS - 24 SEP | LEE Restaurant’s patio setup encroaches on boarding gate space, causing congestion during peak departures. Action: Request removal or relocation of patio structure to restore passenger flow and gate access | ACO T1
NEW ITEMS - 24 SEP | New Cleaning provider T3 Only - Transition Period between BEST and DEXTERRA / Airlines requesting what is the cleaning SCOPE /STANDARDS // Airlines requested contact and info | AOC
GTAA | Winter Readiness planning: GTA to share winter readiness plans, including: Equipment maintenance. De-icing protocols. Bridge canopy inspections. | GTAA
LTO - GTAA | GTAA (Larry Schack) requires 4 finalists + 2 alternates for ground handling RFP evaluation. Deadline: October 3rd. Requirement: Balanced representation from Terminal 1 and Terminal 3. Action: AOC to nominate candidates for evaluation panel. | GTAA