## Sheet1
Hot Water Cabinet Heater Prefunctional Checklist
Project: |  | ENERSYS STEAM BOILER REPLACEMENT
CUH No.: |  | UH-1 |  | Serving: |  | ART STORAGE 41A
Section 1 - Submittal / Approvals
Submittal. The above HVAC Equipment and subsystems critical to them are complete and ready for functional performance testing. The installation/ start-up checklist items are complete and have been checked off only by the parties having direct knowledge of the event, as marked below, respective to each responsible contractor. The prefunctional checklist is submitted for approval, subject to a list of outstanding items remaining to be completed. This checklist will be updated upon the completion of any outstanding items. None of the outstanding items (if listed) preclude safe and relieable functional performance tests from being conducted.
Date
The items on the Prefunctional Checklist are to be completed as part of the startup and initial checkout prior to the start of any functional performance testing. This checklist does not take the place of the equipment manufacturer's recommended checkout and startup procedures. Contractors asigned responsibility for specific sections of the checklist will be responsible to verify that checklist items by their subcontractors are complete and checked off. Contractor coulmns on the checklist sheets refer to the contractor responsible to verify that the item has been completed. A/E-Architect/Engineer, ATC-Automatic Temperature Controls Contractor, CA-Commissioning Agent, EC-Electrical Contractor, MC-Mechancial Contractor, TAB-Test and Balance Contractor.
Approvals. This filled out, completed checklist has been reviewed. Its completion is approved with any exceptions noted below.
Commissioning Agent |  |  |  |  | Date |  | Owners Representative |  |  |  |  | Date
Eastern Air Balance Corporation
Hot Water Cabinet Heater Prefunctional Checklist
Project: |  | ENERSYS STEAM BOILER REPLACEMENT
CUH No.: |  | UH-1 |  | Serving: |  | ART STORAGE 41A
All items listed on this sheet are to be performed by the Automatic Temperature Controls (ATC) Contractor
Section 5 - ATC Device and Point Checkout
The performance of the following procedures is required to be completed and documented for every point in the ATC System. The checkout procedures listed as part of this document are not intended to be a substitute for the startup and checkout procedures recommended by the manufacturer. Initial and date each item when completed. Enter any comments for deficient items.
Definitions: Hardware Check - (WIRE) - Verify that the wiring of each control point or device is correct. (ACTU) - Verify full movement of the actuator through the full range of movement or travel. (ADDR) - Verify that the control point has been properly addressed. Software Check - (LOAD) - For all ATC devices verify that current software program with correct setpoints has been loaded. Device Calibration - (DEVCAL) - ATC device range / stroke calibration. This applies to all controlled devices including valve actuators, damper actuators, pumps, fans, etc. Simulate minimum and maximum signal values. Verify minimum and maximum controller output values. (SENSLOC) - Verify that all ATC Sensors have been installed in a location away from any cause of erratic operation. (SENSCAL) - Sensor calibration. Field calibrate or verify calibration of all sensors, using a hand held measuring device. Provide NIST calibration certificates for all instumentation used for sensor calibration.
(BAS) -Building Automation System reading or displayed value. (INSTRU) - Calibrated instrument reading or displayed value. (OFFSET) -Programmed offset to correct point calibration.
Point I.D. | Device Type | Hardware Check | [5 empty] | Sensor Calibration |  |  | Date | Initials
|  | WIRE | ACTU | ADDR | LOAD | DEVCAL | SENSLOC | BAS | INSTRU | OFFSET