## Sheet1
Heating Hot Water Piping
Project: | ENERSYS STEAM BOILER REPLACEMENT
Section 1 - Submittal / Approvals
Submittal. The above HVAC Equipment and subsystems critical to them are complete and ready for functional performance testing. The installation/ start-up checklist items are complete and have been checked off only by the parties having direct knowledge of the event, as marked below, respective to each responsible contractor. The prefunctional checklist is submitted for approval, subject to a list of outstanding items remaining to be completed. This checklist will be updated upon the completion of any outstanding items. None of the outstanding items (if listed) preclude safe and reliable functional performance tests from being conducted.
Mechanical Contractor |  | Date
The items on the Prefunctional Checklist are to be completed as part of the startup and initial checkout prior to the start of any functional performance testing. This checklist does not take the place of the equipment manufacturer's recommended checkout and startup procedures. Contractors assigned responsibility for specific sections of the checklist will be responsible to verify that checklist items by their subcontractors are complete and checked off. Contractor columns on the checklist sheets refer to the contractor responsible to verify that the item has been completed. A/E-Architect/Engineer, ATC-Automatic Temperature Controls Contractor, CA-Commissioning Agent, EC-Electrical Contractor, MC-Mechanical Contractor, TAB-Test and Balance Contractor.
Approvals. This filled out, completed checklist has been reviewed. Its completion is approved with any exceptions noted below.
Commissioning Agent |  | Date |  | Owners Representative |  |  | Date
Eastern Air Balance Corporation
Heating Hot Water Piping Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Section 2 - Requested Documentation Submitted
One (1) Electronic Copy of the requested documentation listed below shall be provide to the Commissioning Authoriry by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Required Documentation |  | Date | Contractor |  | Initials | Comments
Manufacturers Product Data Sheets |  |  | MC
Copy of HW System Flushing & Cleaning Plan |  |  | MC
Notes:
Section 3 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for heating hot water piping system as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  | Date | Contractor |  | Initials | Comments
Pipe fittings complete and pipes properly supported |  |  | MC
No apparent leakage at any pipe fittings. |  |  | MC
Required seismic anchoring installed (if required) |  |  | MC
Heating hot water piping properly labeled. |  |  | MC
Heating hot water piping properly insulated. |  |  | MC
Strainers cleaned and in place. |  |  | MC
Test Ports (P/T) installed per specifications. |  |  | MC
Heating Hot Water Piping System has been flushed and cleaned in accordance with submitted plan. |  |  | MC
All air vents at high points of system functional. |  |  | MC
All hydrostatic pipe testing completed / reports attached. |  |  | MC
Heating Hot Water Piping System has been flushed and filled. |  |  | MC
Heating Hot Water Piping Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
Section 3 - Installation Documentation Record (continued)
The following Prefunctional Checklist items are to be completed and signed of on for heating hot water piping system as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  | Date | Contractor |  | Initials | Comments
Heating Hot Water System Chemical Treatment plan implemented. |  |  | MC
Heating Hot Water System water treatment report submitted. |  |  | MC
All valve tags permanently affixed. |  |  | MC
All control valves (ATC) installed in proper direction. |  |  | MC
Temperature / Pressure Sensors and Gages installed per specifications and detail drawings. |  |  | MC
Notes