## Sheet1
Air Handling Unit Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
AHU No.: | RTU-1 | Serving: |  | Adminstration
Section 1 - Submittal / Approvals
Submittal. The above HVAC Equipment and subsystems critical to them are complete and ready for functional performance testing. The installation/ start-up checklist items are complete and have been checked off only by the parties having direct knowledge of the event, as marked below, respective to each responsible contractor. The prefunctional checklist is submitted for approval, subject to a list of outstanding items remaining to be completed. This checklist will be updated upon the completion of any outstanding items. None of the outstanding items (if listed) preclude safe and relieable functional performance tests from being conducted.
Mechanical Contractor |  |  | Date
The items on the Prefunctional Checklist are to be completed as part of the startup and initial checkout prior to the start of any functional performance testing. This checklist does not take the place of the equipment manufacturer's recommended checkout and startup procedures. Contractors asigned responsibility for specific sections of the checklist will be responsible to verify that checklist items by their subcontractors are complete and checked off. Contractor coulmns on the checklist sheets refer to the contractor responsible to verify that the item has been completed. A/E-Architect/Engineer, ATC-Automatic Temperature Controls Contractor, CA-Commissioning Agent, EC-Electrical Contractor, MC-Mechancial Contractor, TAB-Test and Balance Contractor.
Approvals. This filled out, completed checklist has been reviewed. Its completion is approved with any exceptions noted below.
Commissioning Agent |  |  | Date |  | Owners Representative |  |  |  |  | Date
Eastern Air Balance Corporation
Air Handling Unit Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
AHU No.: | RTU-1 | Serving: |  | Adminstration
Section 2 - Requested Documentation Submitted
One (1) Electronic Copy of the requested documentation listed below shall be provided to the Commissioning Authority by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Required Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Manufacturers Product Data Sheets |  |  |  | MC
Manufacturers Performance Data (Fan Curves) |  |  |  | MC
Manufacturers Installation Manual |  |  |  | MC
Manufacturers Operation / Maintenance Manual |  |  |  | MC
Manufacturers Wiring Diagram for Power & Controls |  |  |  | MC
Manufacturers Troubleshooting Guide |  |  |  | MC
Notes:
Section 3 - Model Verification
The following information is to be provided by the contractor indicated. Initial and date when completed. Enter any comments for deficient items. 1 = as specified, 2 = as submitted, 3 = as installed.
Required Documentation |  |  | RTU-1 |  | Contractor |  | Date | Initials | Comments
AHU Manufacturer |  | 1
|  | 2 | Trane |  | CA |  | 2020-06-10 | DTR
|  | 3 |  |  | MC
AHU Model Number |  | 1
|  | 2 | OADG017C1-CAB10G |  | CA |  | 2020-06-10 | DTR
|  | 3 |  |  | MC
AHU Serial Number |  | 3 |  |  | MC
Notes:
Air Handling Unit Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
AHU No.: | RTU-1 | Serving: |  | Adminstration
Section 4 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for each AHU as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
AHU has been permanently labeled. |  |  |  | MC
Unit casing is in good condition, doors close & seal properly. |  |  |  | MC
All shipping bolts have been removed, fan mountings checked. |  |  |  | MC
Fan vibration isolation properly installed. |  |  |  | MC
Flex connections at unit tight & in good condition. |  |  |  | MC
All unit components are accessible for normal maintenance activities. |  |  |  | MC
All unit internal thermal insulation installed per specs. |  |  |  | MC
Filters installed. ( ) Yes ( ) No ( ) Quantity |  |  |  | MC
Replacement Filter Size ( )" x ( )" x ( )" Thick |  |  |  | MC
Final strainers are clean and in place. |  |  |  | MC
Supply / Return duct system complete. All GRD's installed. |  |  |  | MC
All volume dampers installed per drawings and left in the fully open position. |  |  |  | MC
Notes:
Air Handling Unit Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
AHU No.: | RTU-1 | Serving: |  | Adminstration
Section 4 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for each RTU as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
AHU Supply Fan VFD wired to controlled equipment. |  |  |  | MC
AHU Supply Fan VFD size (HP) matches Supply Fan motor size (HP). |  |  |  | MC
AHU Supply Fan VFD is located away from excessive temperature. |  |  |  | MC
AHU Supply Fan VFD is located away from excessive moisture. |  |  |  | MC
AHU Supply Fan VFD has been fully programmed and a written copy of all programmed operating parameters is provided. |  |  |  | MC
Notes:
Air Handling Unit Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
AHU No.: | RTU-1 | Serving: |  | Adminstration
Section 4 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for each RTU as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Hot Water Piping is complete. |  |  |  | MC
Hot Water Piping is properly supported. |  |  |  | MC
Hot Water Piping is properly insulated. |  |  |  | MC
Hot Water Piping is properly labeled. |  |  |  | MC
Strainers installed and cleaned. |  |  |  | MC
Hot Water system flushed & cleaned. |  |  |  | MC
Coil face clean / fins in good condition. |  |  |  | MC
Hot Water Coil ATC Valve installed. |  |  |  | MC
Hot Water Coil flow measuring device (circuit setter) has been installed and is in the full open position. |  |  |  | MC
Supply fan discharge plenum free of debris. |  |  |  | MC
Return plenum free of debris. |  |  |  | MC
Return Air / Outside Air / Exhaust Air dampers operate through full range of control. |  |  |  | MC
Notes:
Air Handling Unit Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
AHU No.: | RTU-1 | Serving: |  | Adminstration
Section 6 - Operational Checks
The following Prefunctional Checklist items are to be completed and signed of on for each AHU as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
No excessive Supply Fan noise or vibration. |  |  |  | MC
No excessive Exhaust Fan noise or vibration. |  |  |  | MC
Amperage Check Supply Fan
Motor Rated Amperage = Amps |  |  |  | MC
Actual Amperage L1 / L2 = Amps |  |  |  | MC
Actual Amperage L1 / L3 = Amps |  |  |  | MC
Actual Amperage L2 / L3 = Amps |  |  |  | MC
Rated Motor Service Factor = |  |  |  | MC
Rated Motor S.F. Amperage = Amps |  |  |  | MC
Verify that the actual operating motor amperage is less than the rated motor amperage. |  |  |  | MC
Notes: