## Sheet1
Hydronic Cabinet Heater Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
CH No.: | CH-1 | Serving: |  | Vestibule 13H
Section 1 - Submittal / Approvals
Submittal. The above HVAC Equipment and subsystems critical to them are complete and ready for functional performance testing. The installation/ start-up checklist items are complete and have been checked off only by the parties having direct knowledge of the event, as marked below, respective to each responsible contractor. The prefunctional checklist is submitted for approval, subject to a list of outstanding items remaining to be completed. This checklist will be updated upon the completion of any outstanding items. None of the outstanding items (if listed) preclude safe and relieable functional performance tests from being conducted.
Mechanical Contractor |  |  | Date
The items on the Prefunctional Checklist are to be completed as part of the startup and initial checkout prior to the start of any functional performance testing. This checklist does not take the place of the equipment manufacturer's recommended checkout and startup procedures. Contractors asigned responsibility for specific sections of the checklist will be responsible to verify that checklist items by their subcontractors are complete and checked off. Contractor coulmns on the checklist sheets refer to the contractor responsible to verify that the item has been completed. A/E-Architect/Engineer, ATC-Automatic Temperature Controls Contractor, CA-Commissioning Agent, EC-Electrical Contractor, MC-Mechancial Contractor, TAB-Test and Balance Contractor.
Approvals. This filled out, completed checklist has been reviewed. Its completion is approved with any exceptions noted below.
Commissioning Agent |  |  | Date |  | Owners Representative |  |  |  |  | Date
Eastern Air Balance Corporation
Hydronic Cabinet Heater Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
CH No.: | CH-1 | Serving: |  | Vestibule 13H
Section 2 - Requested Documentation Submitted
One (1) Electronic Copy of the requested documentation listed below shall be provided to the Commissioning Authority by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Required Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Manufacturers Product Data Sheets |  |  |  | MC
Manufacturers Installation Manual |  |  |  | MC
Manufacturers Operation / Maintenance Manual |  |  |  | MC
Manufacturers Parts List for Cabinet Heaters |  |  |  | MC
Manufacturers Wiring Diagrams |  |  |  | MC
Manufacturers Troubleshooting Guide |  |  |  | MC
Notes:
Section 3 - Model Verification
The following information is to be provided by the contractor indicated. Initial and date when completed. Enter any comments for deficient items. 1 = as specified, 2 = as submitted, 3 = as installed.
Required Documentation |  |  | CH-1 |  | Contractor |  | Date | Initials | Comments
Cabinet Heater Manufacturer |  | 1
|  | 2 | Trane |  | CA |  | 2020-06-10 | DTR
|  | 3 |  |  | MC
Cabinet Heater Model Number |  | 1
|  | 2 | FFEB0601AAWD0F |  | CA |  | 2020-06-10 | DTR
|  | 3 |  |  | MC
Cabinet Heater Serial Number |  | 3 |  |  | MC
Notes:
Hydronic Cabinet Heater Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
CH No.: | CH-1 | Serving: |  | Vestibule 13H
Section 4 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for each Cabinet Heater as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Cabinet Heater has been permanently labeled. |  |  |  | MC
All Cabinet Heater components are accessible for maintenance. |  |  |  | MC
Cabinet Heater has sufficient clearance / access to allow for proper service and maintenance. |  |  |  | MC
All hot water piping connections to the Unit Heater have been completed. |  |  |  | MC
All thermal insulation has been properly installed per the specifications. |  |  |  | MC
Hot water piping has been properly labeled per the specifications. |  |  |  | MC
Hot water piping system flushing and chemical treatment has been completed. |  |  |  | MC
Strainers installed and cleaned. |  |  |  | MC
Notes:
Hydronic Cabinet Heater Prefunctional Checklist
Project: | ENERSYS STEAM BOILER REPLACEMENT
CH No.: | CH-1 | Serving: |  | Vestibule 13H
Section 4 - Installation Documentation Record
The following Prefunctional Checklist items are to be completed and signed of on for each Cabinet Heater as part of the initial system startup and checkout. This startup and checkout must be performed and completed prior to the start of any work by the TAB Contractor, and any functional performance testing. This checklist should be used as a supplement , and is not intended to take the place of the manufacturers recommended startup and checkout procedures. Each of the items listed is to be completed by the contractor indicated. Initial and date when completed. Enter any comments for deficient items.
Installation Documentation |  |  | Date | Contractor |  | Initials |  | Comments
Fan and motor are properly aligned. |  |  |  | MC
Fan intake area is clear of debris. |  |  |  | MC
The ATC Control Valve for the cabinet heater has been installed. |  |  |  | MC
The flow measuring device (circuit setter) has been installed and is in the full open position. |  |  |  | MC
Notes: